## Introduction
1. INTRODUCTION
The Service Delivery and Budget Implementation Plan (SDBIP) is a detailed annual performance (operational) plan for implementing services using the approved budget for 2022/23. This annual service delivery plan is called the SDBIP and is based on the approved IDP and Budget.
SDBIP serves as a contract between the municipality and the community on the services that the municipality commits to deliver over the twelve (12) months. It also helps to hold the municipality and its management accountable for the performance on the mentioned programmes and projects.
The Municipal Finance Management Act and the guiding MFMA circular requires the following to be included in the SDBIP of a municipality:
· Monthly projection of revenue to be collected for each source
· Monthly projections of expenditure (operating and capital) and revenue for each vote
· Quarterly projections of service delivery targets and performance indicators for each vote
· Ward information for the delivery of a specific service
1.1. BACKGROUND
MFMA prescribes that each municipality must compile its SDBIP. The Mayor of the municipality is required to approve the SDBIP within 28 days after the approval of the budget and table the same at a Municipal Council meeting and made public no later than 14 days after approval for information.
National Treasury’s MFMA Circular No.13 further states that the SDBIP is a layered plan, once the top-layer targets have been set as in this document, the various departments of the municipality develop the next lower-level.
The organization of the SDBIP is in terms of the prescribed Key Performance Areas:
§ Basic Service Delivery
§ Municipal Institutional Development and Transformation
§ Local Economic Development (LED)
§ Municipal Financial Viability and Management
§ Good Governance and Public Participation
§ Social Services as the sixth Key Performance Area for the municipality
1.1 MONITORING AND EVALUATION
The Municipal Council has adopted Performance Management Policy (PMP) and Framework for the 2020/21. The performance management system makes provisions for the Quarterly and Mid-year performance reporting and reviews on the implementation of the SDBIP.
The key focus areas and service delivery targets for the 2020/21 are outlined in the following sections of this plan.
1.3
Vision
“A developmental and responsive municipality”
Mission
“to promote sustainable development by ensuring service delivery in an equitable manner prioritizing community needs and good governance”
1.5
Good ethics
Fairness
Integrity
Accountability
Efficiency
Thoughtfulness
Trustworthiness
Signed By
…………………………………………
Her Worship the Mayor

## Technical Services
IDP NO. | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGET | [11 empty] | TOTAL BUDGET
[6 empty] | Quarter 1 |  | Means of verification | Quarter 2 |  | Means of verification | Quarter 3 |  | Means of verification | Quarter 4 |  | Means of verification
[6 empty] | Target | Budget |  | Target | Budget |  | Target | Budget |  | Target | Budget
Objective: To provide basic services through infrastructure development in an environmental friendly manner
1.1 | Basic Service Delivery | Construction of 10,3km of Malola Access Road in Ward 25 | This indicator is a roll over from 2021-2022. Project at 95% as at end of FY | 1.1.1.1. 100% completion of 10,3km of Malola Access Road in Ward 25 | 100% completion of 10,3km of Malola Access Road by 30 June 2023 | N/A | N/A | N/A | Stage 2 (100%) Final Completion Certificate} by 30 December 2022. | 150000 | Final completion certificate | Stage 2 (100%) Final Completion Certificate} by 31 March 2023. | 150000 | Final completion certificate | N/A | 0 | N/A | 150000 | Final completion certificate
1.1 | Basic Service Delivery | Construction of 5km of Bukazi Access Road in Ward 12 | Technical report is completed. | 1.1.1.2. 20% completion of 5km of Bukazi Access Road in Ward 12 | 20% completion of 5km of Bukazi Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1370726.35 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2022. | 2056089.53 | Site meeting minutes and attendance register, Monthly reports | Stage 1 (10%)Contractor establishment by 31 March 2023 | 1370726.35 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 June 2023 | 2056089.53 | Site meeting minutes and attendance register, Monthly reports | 8300004 | Site meeting minutes and attendance register, Monthly reports
1.1 | Basic Service Delivery | Construction of 7km of Singembeni Access Road in Ward 32 | Technical report is completed | 1.1.1.3. 20% completion of 7km of Singembeni Access road in Ward 32 | 20% completion of 7km of Singembeni Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1255287.01 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2022. | 1882930.52 | Site meeting minutes and attendance register, Monthly reports | Stage 1 (10%). Contractor establishment by 31 March 2023. | 1255287.01 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 June 2023. | 1882930.52 | Site meeting minutes and attendance register, Monthly reports | 6999996 | Site meeting minutes and attendance register, Monthly reports
1.1 | Basic Service Delivery | Construction of 15km of Mathe to Gqina Access Road in Ward 31 | Technical report is completed | 1.1.1.4. 95% completion of 15km of Mathe to Gqina Access Road in Ward 31 | 95% completion of 15km of Mathe to Gqina Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 977858.75 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2022. | 4800000 | Site meeting minutes and attendance register, Monthly reports | Stage 3 (85%) Tipping of gravel by 31 March 2023 | 2400000 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (95%). Processing of wearing course and installation of pipes by 30 June 2023 | 3822141.25 | Practical completion certificate | 12000000 | Practical completion certificate
1.1 | Basic Service Delivery | Construction of 13km of Mavaleleni Access Road in Ward 02 | Technical report is completed | 1.1.1.5. 95% completion of 13km of Mavalela Access Road in Ward 02 | 95% completion of 13km of Mavaleleni Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1289092.87 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2022. | 1933639.31 | Site meeting minutes and attendance register, Monthly reports | Stage 3 (80%) Tipping of gravel by 31 March 2023 | 2255914.52 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (95%). Processing of wearing course and installation of pipes by 30 June 2023 | 1721353.3 | Practical completion certificate | 7200000 | Practical completion certificate
1.1 | Basic Service Delivery | Construction of 7km of Maqadini Access Road in Ward 05 | Technical report is completed | 1.1.1.6. 95% completion of 7km of Maqadini Access Road in Ward 05 | 95% completion of 7km of Maqadini Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1219929.39 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2022. | 1829894.09 | Site meeting minutes and attendance register, Monthly reports | Stage 3 (70%) Tipping of gravel by 31 March 2023 | 2134876.44 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (95%). Processing of wearing course and installation of pipes by 30 June 2023 | 1615300.08 | Practical completion certificate | 6800000 | Practical completion certificate
1.1 | Basic Service Delivery | Construction of 30m of Qhamangweni bridge in ward 11 | Technical report is completed | 1.1.1.7. 40% completion of Qhamangweni Bridge in Ward 11 | 40% completion of Qhamangweni Access Road by 30 June 2023 | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1281231.22 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (40%) 40% completion -Base foundation slab completed by 30 December 2022. | 1921846.84 | Site meeting minutes and attendance register, Monthly reports | Stage 1 (10%). Contractor establishment by 30 September 2022. | 1281231.22 | Site meeting minutes and attendance register, Monthly reports | Stage 2 (40%) 40% completion -Base foundation slab completed by 30 December 2022. | 1921846.84 | Site meeting minutes and attendance register, Monthly reports | 7299990 | Site meeting minutes and attendance register, Monthly reports
1.1 | Basic Service Delivery | Construction of 2,4km of Nyasa Road in Ward 01 | Technical report is completed | 1.1.1.8. 20% completion of 2.4km of Nyasa Road in Ward 01 | 20% completion of 2,4km of Nyasa AR by 30 June 2024 | N/A | 0 | N/A | N/A | 0 | NA | N/A | 0 | N/A | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2023 | 1273422.295 | Monthly reports | 1273422.295 | Monthly reports
1.1 | Basic Service Delivery | Construction of 3.9km of Zihagwini to Mbhayi in Ward 04 | Technical report is completed | 1.1.1.9. 20 % completion of 3.9km Zihagwini Access Road in Ward 04 | 20% completion of 3.9km Zihagwini Access Road by 30 June 2024 | N/A | 0 | N/A | N/A | 0 | NA | N/A | 0 | N/A | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2023 | 1273422.295 | Monthly reports | 1273422.295 | Monthly reports
1.1 | Basic Service Delivery | Construction of 5km of Ngqayimbana (New Rest ) Road in Ward 09 | Technical report is completed | 1.1.1.10. 20 % completion of 5km of Ngqayimbana (New Rest ) AR in Ward 09 | 20% completion of 5km of Ngqayimbana (New Rest ) AR by 30 June 2024 | N/A | 0 | N/A | N/A | 0 | NA | N/A | 0 | N/A | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2023 | 3820266.885 | Monthly reports | 3820266.885 | Monthly reports
1.1 | Basic Service Delivery | Construction of 5km of Kanana Extension Road in Ward 17 | Technical report is completed | 1.1.1.11. 20% completion of 5km of Kanana Extension Road in Ward 17 | 20% completion of 5km of Kanana Extension Road by 30 June 2024 | N/A | 0 | N/A | N/A | 0 | NA | N/A | 0 | N/A | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2024 | 2801529.049 | Monthly reports | 2801529.049 | Monthly reports
1.1 | Basic Service Delivery | Construction of 5km of Noteku AR in Ward 28 | Technical report is completed | 1.1.1.12. 20% completion of 5km of Noteku Road in Ward 28 | 20% completion of 5km of Noteku Road by 30 June 2024 | N/A | 0 | N/A | N/A | 0 | NA | N/A | 0 | N/A | Stage 2 (20%) -Clear and grub Roadbed preparation by 30 December 2025 | 2139349.4556 | Monthly reports | 3565582.426 | Monthly reports
1.1 | Basic Service Delivery | Application for funding for the Planning of Lusikisiki Internal Streets Phase 3 | Phase 1 & 2 completed | 1.1.2.1 100% attainment of funding approval from COGTA by30 June 2023 | 100% attainment of funding approval from COGTA by 30 June 2023 | 25% completion -Preparation of business plan by 30 September 2022 | 125000 | Business plan | 50% completion -Presentation to Pre-DAC for funding by 30 December 2022 | 125000 | Pre-DAC presentation, attendance register & minutes | 50% completion -Presentation to Pre-DAC for funding by 31 March 2023 | 125000 | Pre-DAC presentation, attendance register & minutes | 100% completion -Funding approved by 30 June 2023 | 250000 | Approval letter | 500000 | Approval letter
1.1 | Basic Service Delivery | Application for funding for the planning of Flagstaff Internal Streets- Phase 2 | Phase 1 completed | 1.1.2.2 100% attainment of funding approval from COGTA by 30 June 2023 | 100% attainment of funding approval from COGTA by 30 June 2024 | 25% completion -Preparation of business plan by 30 September 2022 | 125000 | Business plan | 50% completion -Presentation to Pre-DAC for funding by 30 December 2022 | 125000 | Pre-DAC presentation, attendance register & minutes | 50% completion -Presentation to Pre-DAC for funding by 31 March 2023 | 125000 | Pre-DAC presentation, attendance register & minutes | 100% completion -Funding approved by 30 June 2023 | 250000 | Approval letter | 500000 | Approval letter
1.1 | Basic Service Delivery | Maintenance of 110km of gravel access roads in 32 wards | 1021.4 km of gravel roads maintained | 1.1.4.1. 110 km of roads maintained by 30 June 2023 | 110km of roads maintained by 30 June 2023 | Appointment of the contractor, site establishment completed by 30 September 2022 | 0 | Appointment letter | 53km of roads maintained by 30 December 2022 | 2000000 | Progress report | 105km of roads maintained by 31 March 2023 | 2000000 | Completion certificates | 110km of roads maintained by 30 June 2023 | 1000004 | Completion certificates | 5000004 | Completion certificates
1.1 | Basic Service Delivery | Rehabilitation of 3,4km of Mathunzini Access Road in Ward 04 | 1021,4km of gravel roads | 1.1.4.2. 100% completion of 3,4km of Mathunzini Access Road in Ward 04 | 100% completion of 3,4km of Mathunzini Access Road by 30 June 2023 | N/A | N/A | N/A | Stage 2 (60%) -Site establishment, Roadbed preparation , tipping and processing of gravel material by 30 December 2022. | 200000 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (100%). Final completion by 30 March 2023 | 309760.5 | Completion Certificate | N/A | N/A | N/A | 509760.5 | Completion Certificate
1.1 | Basic Service Delivery | Rehabilitation of surfaced roads in ward 15 Lusikisiki Town | 3328m2 was maintained in the last FY | 1.1.4.3. 1000m2 of roads rehabililated by 30 June 2023 | 1000m2 of roads rehabililated by 30 June 2023 | Appointment of the contractor, site establishment completed by 30 September 2022 | 0 | Appointment letter | 200m2 of roads rehabililated by 30 December 2022 | 155250 | Progress report | 1000m2 of roads rehabililated by 30 June 2023 | N/A | Completion Certificate | N/A | N/A | N/A | 517500 | Completion Certificate
1.1 | Basic Service Delivery | Rehabilitation of 5km of Sphezini to Mbhandango Access Road in Ward 07 | 1021,4km of gravel roads | 1.1.4.4. 100% completion of 5km of Sphezini to Mbhandango Access Road in Ward 03 | 100% completion of 5km of Sphezini to Mbhandango Access Road by 30 June 2023 | N/A | N/A | N/A | Stage 2 (60%) -Site establishment, Roadbed preparation , tipping and processing of gravel material by 30 December 2022. | 200000 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (100%). Final completion by 31 March 2023 | 370894.5 | Completion Certificate | N/A | N/A | N/A | 570894.5 | Completion Certificate
1.1 | Basic Service Delivery | Rehabilitation of 3,4km of Norhatshaza to Mbhayi Access Road in Ward 03 | 1021,4km of gravel roads | 1.1.4.5. 100% completion of 3,4km of Norhatshaza to Mbhayi Access Road in Ward 03 | 100% completion of 3,4km of Norhatshaza to Mbhayi Access Road by 30 June 2023 | N/A | N/A | N/A | Stage 2 (60%) -Site establishment, Roadbed preparation , tipping and processing of gravel material by 30 December 2022. | 450000 | Site meeting minutes and attendance register, Monthly reports | Stage 4 (100%). Final completion by 31 March 2023 | 766838 | Completion Certificate | N/A | N/A | N/A | 1216838 | Completion Certificate
1.1 | Basic Service Delivery | Rehabilitation of 10,3km of Mangquzu Access Road in Ward 10 | 1021,4km of gravel roads | 1.1.4.6. 100% completion of 10,3km of Mangquzu Access Road in Ward 10 | 100% completion of 10,3km of Mangquzu Access Road by 30 June 2023 | N/A | N/A | N/A | N/A | N/A | N/A | Stage 1 (10%) -Site establishment by 31 March 2023. | 600000 | Monthly Report | Stage 4 (100%) project by 30 June 2023 | 600000 | Monthly Report | R1 616 027.00 | Monthly Report
1.1 | Basic Service Delivery | Rehabilitation of 2,5km of Xhurhana to Ndungunyeni Access Road in Ward 13 | 1021,4km of gravel roads | 1.1.4.7. 100% completion of 2,5km of Xhurhana to Ndungunyeni Access Road in Ward 13 | 100% completion of 2,5km of Xhurhana to Ndungunyeni Access Road in Ward 13 by 30 June 2023 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 0 | Monthly Report | Stage 4 (100%) project by 30 June 2023 | 850000 | Monthly Report | 850000 | Monthly Report
1.1 | Basic Service Delivery | Construction of 0,23ha of Ward 2 Multipurpose sports Field - Phase 2 in Mavaleleni village | Project at 40% as at end of FY | 1.1.5.1. 60% completion of 0,23ha of Ward 2 Multipurpose sports field-Phase 2 at Mavaleleni village in ward 02 | 60% completion of 0,23ha of Ward 2 Multipurpose field -Phase 2 by 30 June 2023 | Project at (50%) Fencing completed by 30 September 2022 | 500000 | Progress report | Project at (60%) steel fixing completed by 30 December 2022 | 500000 | Progress report | Project at (50%) Fencing completed by 31 March 2023 | 500000 | Progress report | Project at (60%) steel fixing completed by 30 June 2023 | 500000 | Progress report | 2000000 | Progress report
1.1 | Basic Service Delivery | Construction of 0,23ha of Ward 2 Multipurpose sports Field - Phase 1 in Kwa- Ntshantsha village | Project at 95% as at end of FY | 1.1.5.2. 100% completion of 0,23ha of Ward 2 Multipurpose sports field- Phase 1 at Kwa-Ntshantsha village by 30 June 2023 | 100% completion of 0,23ha of Ward 2 Multipurpose field -Phase 1 by 30 June 2023 | Project at (100%) sportsfield completed by 30 September 2022 | 1000000 | Progress report and Practical Completion Certificate | N/A | 0 | N/A | N/A | 0 | N/A | Project at (100%) sportsfield completed by 30 June 2023 | 1000000 | Progress report and Practical Completion Certificate | 1000000 | Progress report and Practical Completion Certificate
1.1 | Basic Service Delivery | Construction of 0,11ha of Ward 26 Multi - purpose Sports Field, at Jikindaba village | Project at 47% as at end of FY | 1.1.5.3. 95% completion of 0.11ha of Ward 26 Multipurpose sports field by 30 June 2023 at Jikindaba village | 95% completion of 0.11ha of Ward 26 Multipurpose sports field by 30 June 2023 | Project at (80%) Grandstand completed by 30 September 2022 | 400002 | Progress report | Project at (80%) Change rooms completed by 30 December 2022 | 400002 | Progress report | Project at (80%) Change rooms completed by 31 March 2023 | 400002 | Progress report | Project at 95% grand stand stand completed by June 2023 | 400002 | Practical completion | 8000004 | Practical completion
1.1 | Basic Service Delivery | Completion of a (40m2) Public Toilets in Ward 6 Flagstaff Town | Progress was 70% as at 2020/21 FY. The contractor was terminated for poor performance and site abondonment. The project will be re-advertised and completed in the current FY | 1.1.6.1. 100% completion of (40m2) Flagstaff Public Toilets Phase 1 by 30 June 2023 | 100% completion of (40m2) Public Toilets Phase 1 in ward 6 in Flagstaff by 30 June 2023 | N/A | 0 | N/A | Appointment of contractor by 30 September 2022 | 250000 | Progress report | Project at (10%) - contractor establishment by 31 March 2023 | 250000 | Progress report | Project at (100%) - roof structucture, fencing, doors and windows, plumbing and cleaning complete by 30 June 2023 | 500000 | Completion certificate | 500000 | Completion certificate
1.1 | Basic Service Delivery | Completion of Phase 1 Public Toilets in ward 15 in Lusikisiki Town | Progress was 70% as at 2020/21 FY. The contractor was terminated for poor performance and site abondonment. The project will be re-advertised and completed in the current FY | 1.1.6.2. 100% completion of (40m2) Lusikisiki Public Toilets Phase1 by 30 June 2023 | 100% completion of (40m2) Public Toilets Phase 1 in ward 15 in Lusikisiki by 30 June 2023 | N/A | 0 | N/A | Appointment of contractor by 30 September 2022 | 250000 | Progress report | Project at (10%) - contractor establishment by 31 March 2023 | 150000 | Progress report | Project at (100%) - roof structucture, fencing, doors and windows, plumbing and cleaning complete by 30 June 2023 | 350000 | Completion certificate | 500000 | Completion certificate
1.1 | Basic Service Delivery | Planning of Ward 31 Community Hall with floor size 412 m2 in Ward 31 | 32 Community Halls constructed | 1.1.7.1 100% attainment of funding approval for Ward 31 Community Hall from COGTA by 30 June 2023 | 100% attainment of funding approval for Ward 31 Community Hall (412m2) by June 2023 | 25% completion -Preparation of business plan by 30 September 2022 | 200000 | Business plan | 50% completion -Presentation to Pre-DAC for funding by 30 December 2022 | 0 | Pre-DAC presentation, minutes & attendance register | 50% completion -Presentation to Pre-DAC for funding by 31 March 2023 | 0 | Pre-DAC presentation, minutes & attendance register | 100% completion -Funding approved by 30 June 2023 | 300000 | Approval letter | 500000 | Approval letter
1.1 | Basic Service Delivery | Planning of New Rest Community Hall with floor size 412 m2 in Ward 19 | 32 Community Halls constructed | 1.1.7.2. 100% attainment of funding approval for Ward 19 Community Hall from COGTA by 30 June 2023 | 100% attainment of funding approval for Ward 19 Community Hall (412m2) by June 2023 | 25% completion -Preparation of business plan by 30 September 2022 | 200000 | Business plan | 50% completion -Presentation to Pre-DAC for funding by 30 December 2022 | 0 | Pre-DAC presentation, minutes & attendance register | 50% completion -Presentation to Pre-DAC for funding by 31 March 2023 | 0 | Pre-DAC presentation, minutes & attendance register | 100% completion -Funding approved by 30 June 2023 | 300000 | Approval letter | 500000 | Approval letter
1.1 | Basic Service Delivery | Construction of Lusikisiki Town Hall (Phase 2) with floor size 2500m2 in Ward 19 at Lusikisiki Town | Phase 1 completed | 1.1.8.1. 60% construction of Lusikisiki Town Hall (Phase 2) with floor size 2500m2 in Ward 19 at Lusikisiki Town by June 2023 | 60% completion of construction of Lusikisiki Town Hall (Phase 2) by 30 June 2023 | Appointment of the contractor, Project at (10%) site establishment by 30 September 2022 | 0 | Appointment letter and progress report | Project at 30% Plumbing and electrical works by 30 December 2022 | 1500000 | Progress report | Project at 30% Plumbing and electrical works by 31 March 2023 | 1000000 | Progress report | Project at (60%) Superstructure completed by 31 March 2023 | 500000 | Progress report and practical completion certificate | 3000000 | Progress report and practical completion certificate
1.1 | Basic Service Delivery | Construction of Flagstaff Town Hall (Phase 2) with floor size 2500m2 in Ward 06 | Phase 1 completed | 1.1.8.2. 100% construction of Flagstaff Town Hall- (Phase 2) with floor size 2500m2 in Ward 06 by June 2023 | 100% completion of construction of Flagstaff Town Hall (Phase 2) by 30 June 2023 | Appointment of the contractor, Project at (10%) site establishment by September 2022 | 500000 | Appointment letter and progress report | Project at 30% Plumbing and electrical works by 30 December 2022 | 500000 | Progress report | Project at (75%) Superstructure completed by 31 March 2023 | 1500000 | Progress report | Project at (100%) Paving and fencing completed by 30 June 2023 | 1000000 | Progress report and practical completion certificate | 3500000 | Progress report and practical completion certificate
1.1 | Basic Service Delivery | Renovations of New Flagstaff Offices with floor size 7554m2 | Flagstaff New Offices on Practical completion | 1.1.9.1. 20% completion of renovations of New Flagstaff Offices with floor size of 7554m2 in Ward 6 at Flagstaff Town by 30 June 2023 | 20% completion of Renovations of New Flagstaff Offices with floor size of 7554m2 in Ward 6 by June 2023 | Appointment of the contractor, Project at (10%) site establishment by 30 September 2022 | 1000000 | Appointment letter and progress report | Project at 30% Water proofing and air conditioners and ceilling by December 2022 | 2000000 | Progress report | Project at (5%) Preparation of technical report, tender document and advert by 31 March 2023 | 1000000 | Progress report | Project at (20%) site establishment and commencement of the works by 30 June 2023 | 2500000 | Appointment and Progress report | 3500000 | Appointment and Progress report
1.1 | Basic Service Delivery | Construction of Lusikisiki Municipal Offices in Ward 19 at Lusikisiki town with floor size of 7440 m2 | Designs are completed | 1.1.9.2. 10% construction of 7440 m2 of Lusikisiki Municipal Offices in Ward 19 at Lusikisiki town by June 2023 | 10% completion of Lusikisiki Municipal Offices in Ward 19 by 30 June 2023 | Appointment of the contractor by 30 September 2022 | 0 | Approved final designs and appointment letter | Project at 15% Site Establishment and demolitions completed 30 December 2022 | 4500000 | Progress report | Preparation of re-advert for construction of Municipal Offices | 0 | Advert | Project at 10% Site establishment by 30 June 2023 | 6000000 | Appointment Letter and Progress report | 30000000 | Appointment Letter and Progress report
1.1 | Basic Service Delivery | Construction of stage for the Hombe community hall in ward 20 with floor size of 40 m² | Renovations were completed but ward cllr and community requested the construction of a stage | 1.1.10.1. 100% completion of stage for the Hombe community hall in ward 20 with floor size of 40 m² by June 2023 | 100% completion of 40 m² of Stage in Ward 20 by 30 June 2023 | N/A | R0.00 | N/A | Project at (10%) Appointment of the contractor, site establishment by 30 September 2022 | 45000 | Appointment Letter and Progress report | Preparation of re-advert for construction of Hombe Stage | 0 | Advert | Project at 100% upgrading completed by 30 June 2023 | 450000 | Progress report and practical completion certificate | 450000 | Progress report and practical completion certificate
1.1 | Basic Service Delivery | 250m Fencing of at Flagsaff ClubHouse in Ward 06 | Flagstaff Clubhouse has been vandalized and is not fenced | 1.1.10.2. 100% Completion of fencing at Flagstaff Clubhouse in Ward 06 | 100% Completion of fencing at Flagstaff Clubhouse by 30 June 2023 | Project at 10% Appointment of the contractor, site establishment by 30 September 2022 | 200000 | Appointment Letter and Progress report | Project at 50% fencing by 30 December 2022 | 1000000 | Progress report | Project at 10% Appointment of the contractor, site establishment by 31 March 2023 | 200000 | Appointment Letter and Progress report | Project at 100% Fencing completed by 31 March 2023 | 200000 | Appointment Letter and Progress report | 2000000 | Appointment Letter and Progress report
1.1 | Basic Service Delivery | 200m Fencing of Information Center in Ward 06 at Flagstaff | Information Centre has been vandalized and is not fenced | 1.1.10.3. 100% Completion of fencing of Information Center in Ward 06 at Flagstaff | 100% completion of fencing of the Information Center by 30 June 2023 | Project at 10% Appointment of the contractor, site establishment by 30 September 2022 | 200000 | Appointment Letter and Progress report | Project at 50% fencing by 30 December 2022 | 1800000 | Progress report and practical completion certificate | Project at 10% Appointment of the contractor, site establishment by 31 March 2023 | 200000 | Appointment Letter and Progress report | Project at 100% Fencing completed by 31 March 2023 | 200000 | Appointment Letter and Progress report | 2000000 | Appointment Letter and Progress report
1.1 | Basic Service Delivery | Renovation of sports field in wards 19 Joe Slovo) | Contractor appointed, project at 90% | 1.1.10.4. 100% completion of renovations of sports field in wards 19 Joe Slovo | 100% completion of Renovations of by 30 June 2023 | Stage 1 (95%) planting of grass by 30 December 2022. | 200000 | Progress report | N/A |  | N/A | Stage 1 (80%) planting of grass by 31 March 2023 | 200000 | Progress report | Stage 3 (100%) Final Completion of renovations by 30 June 2023. | 577293.63 | Completion certificate | 250000 | Completion certificate
1.1 | Basic Service Delivery | Renovation of sports field in ward 9 Sigubudwini | Contractor appointed, project at 92% | 1.1.10.5. 100% completion of renovations of sports field in ward 9 Sigubudwini | 100% completion of Renovations of by 30 June 2023 | Stage 1 (95%) planting of grass by 30 December 2022. | 200000 | Progress report | N/A |  | N/A | Stage 1 (80%) planting of grass by 31 March 2023 | 200000 | Progress report | Stage 3 (100%) Final Completion of renovations by 30 June 2023. | 50000 | Completion certificate | 350000 | Completion certificate
1.1 | Basic Service Delivery | Approved designs for 10 Highmast lights in Ward 9,14,18,19,20,22,27 ,17,04 and 32 at Ndukundeni, Ngobozana High School, Mayalweni, Robert Ngobozana,Mthathambi,Goso Clinic , Holly Cross Hospital,Kanana ,Magwambu and Cwija villages | 75 highmast lights constructed to date | 1.1.11.1. 100% Completion of approved designs for 10 High Mast Lights in Ward 9,14,18,19,20,22,27 ,17,04 and 32 at Ndukundeni, Ngobozana High School, Mayalweni, Robert Ngobozana,Mthathambi,Goso Clinic , Holly Cross Hospital,Kanana ,Magwambu and Cwija villages by 30 June 2023 | 100% Completion of approved designs for 10 High Mast Lights by 30 June 2023 | Appointment of the consultant by 30 September 2022 | 50000 | Appointment letter and approved design report | Project at 100% Designs approved | 450004 | Final approved designs | Preparation of business plan by 31 June 2023 | N/A | Appointment letter and Approved Business Plan | Project at 100% Designs complete by 30 June 2023 | 500000 | Approved designs | 500004 | Approved designs
1.1 | Basic Service Delivery | Construction of 16 streetlights in ward 19 in Ngobozana village | Designs in place | 1.1.12.1. 100% completion of the construction of 16 streetlights in wards 19 in Ngobozana by 30 June 2023 | 100% completion of 16 streetlights constructed by 30 June 2023 | 10% completion of Appointment of the contractor and site establishment by 30 September 2022 | 50000 | Appointment letter and progress report | 15% of 16 streetlights constructed by 30 December 2022 | 50004 | Progress report | Project at 10% - Site establishment by 31 March 2023 | 150000 | Appointment letter and progress report | Project at 100% - 16 streetlights constructed by 30 June 2023 | 1750000 | Completion certificate | 2000000 | Completion certificate
1.1 | Basic Service Delivery | Connection of 338h/h in ward 6 and 7 | 53085hh/h connected | 1.1.12.2. 100% Installation of 338h/h in ward 6 and 7 by June 2023 | 100% of 338h/h connected by June 2023 | Appointment of the contractor by 30 September 2022 | 0 | Appointment Letter | Project at 20%- site establishment and 100h/h connections installed by 30 December 2022 | 500000 | Progress report | Project at 60% - 200h/h/connections installed by 30 March 2023 | 1200000 | Progress report | Project at 100% - 338h/h/connections installed and energised by 30 June 2023 |  | Completion Certificate | 8000000 | Completion Certificate
1.1 | Basic Service Delivery | Maintenance of 100 streetlights in Ward 06,15 and 19 at Flagstaff town ,Lusikisiki town and Arthur Homes | 100 streetlights maintained | 1.1.14.1. 100% maintainance of 100 streetlights in Ward 06,15 and 19 at Flagstaff town ,Lusikisiki town and Arthur Homes by June 2023 | 100% of 100 streetlights maintained by 30 June 2023 | 10% completion of Appointment of the contractor and site establishment by 30 September 2022 | 100000 | Appointment letter and progress report | 15% of 100 streetlights maintained by 30 December 2022 | 0 | Progress report and completion certificate | Project at 10% - Site establishment by 31 March 2023 | 100000 | Appointment letter and progress report | Project at 100% - 100 streetlights maintained by 30 June 2023 | 900000 | Completion certificate | 1000000 | Completion certificate
1.1 | Basic Service Delivery | Replacement of 01 highmast light in Ward 15 at Lusikisiki town | Project was not achieved in the previous FY due to the Circular by Treasury. | 1.1.15.1 100% completion of 01 Highmast light replaced in Ward 15 in Lusikisiki town by June 2023 | 100% of 01 Highmast light replaced by 30 June 2023 | Appointment of the contractor by 30 September 2022 | 65000 | Appointment letter | Project at 100% 01 highmast light replaced by 30 December 2022 | 585000 | Completion certificate | Project at 10% - Site establishment by 31 March 2023 | 150000 | Appointment letter and progress report | Project at 100% - 01 highmastlight replaced by 30 June 2023 | 0 | Completion certificate | 650000 | Completion certificate
1.3 | Local Economic Development | Creation of 200 jobs through local labour employment | 409 Jobs created in previous FY | 1.3.1. Number of jobs created through local labour employment | 200 jobs created by 30 June 2023 | 50 jobs created by 30 September 2022 | N/A | Labour forms | 100 jobs created by 30 December 2022 |  | Labour forms | 150 jobs created by 31 March 2023 |  | Labour forms | 200 jobs created by 30 June 2023 |  | Labour forms | 0 | Labour forms
[7 empty] | ` | `
1.2.1
PROJECT NAME: | Training and workshop for employees
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Training and workshop for employees
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | N/A
SOURCE OF FUNDING: | N/A
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure that the employees are aware of the requirements for spending and reporting of grants | [5 empty] | . Attendance of trainings and workshops
Key Milestones | [5 empty] | Responsible Official | Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Attendance of workshops and training | [5 empty] | L.S. Tshangela and M.Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 0; 4th Quarter 3: N/A
1.3.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Xhopozo milie
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Fencing of Xhopozo milie fields ward 30
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site establishment and Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire and erection of dropers | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of gate and conner supporters | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 100000 | 150000 | 1st Quarter 1: 100000; 1st Quarter 3: 150000; 4th Quarter 2: 500000; 4th Quarter 3: Equitable share
1.3.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Luqhoqhweni Milie fields
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Fencing of Luqhoqhweni milie fields ward 29
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 31741.26
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
. Site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site establishment and Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire and erection of dropers | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of gate and conner supporters | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 100000 | 95223.79 |  | 122188.83 |  |  | 4th Quarter 2: 317412.62; 4th Quarter 3: Equitable share
1.3.3 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Khanyisa agricultural project
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Fencing of Khanyisa agricultural projects ward 16
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 450000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire and erection of dropers | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of gate and conner supporters | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 100000 | 100000 |  | 100000 | 100000 | 50000 | 4th Quarter 2: 450000; 4th Quarter 3: Equitable share
1.3.4 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Jaca milie fields
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Fencing of Jaca milie fields ward 30
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 170000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire and erection of dropers | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Streching of wire | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of gate and conner supporters | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 70000 |  |  |  | 100000 |  | 4th Quarter 2: 170000; 4th Quarter 3: Equitable share
1.3.5 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Khanyisa agricultural project
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Khanyisa Borehole projects ward 16
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 332672.23
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Geo investigation | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Drilling for bore hole | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Installation of pipes to boreholes | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Construction of elevated tank | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Laying of pipes and sprinklers,testing of water | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 100000 |  | 100000 | 1332672.23 |  |  | 4th Quarter 2: 1532672.23; 4th Quarter 3: Equitable share
1.3.6 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Khabingele agricultural project
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Khabingele Borehole projects ward 28
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 332672.23
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site establishment and clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Geo investigation | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Drilling for bore hole | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Installation of pipes to boreholes | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Construction of elevated tank | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Laying of pipes and sprinklers,testing of water | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 100000 |  | 100000 | 1332672.23 |  |  | 4th Quarter 2: 1532672.23; 4th Quarter 3: Equitable share
1.3.7 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Inguquko agricultural project
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovation of inguquko agricultural projects ward
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 700000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
· Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
. Excavating for trenches | [5 empty] | P.Nqezo | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
. Concrete in footing and brick wall in foindation | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
. Installation of pipes to boreholes | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
. Construction of Block walls | [5 empty] | P.Nqezo | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2
. Plaster and roofing | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 70000 |  | 200000 | 200000 | 230000 |  | 4th Quarter 2: 700000; 4th Quarter 3: Equitable share
1.3.8 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2
PROJECT NAME: | Xura red meat project
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovation of Xura red meat projects ward 17
PROJECT START DATE: | 10/08/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 1
· Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 1
. Excavating for trenches | [5 empty] | P.Nqezo
. Concrete in footing and brick wall in foindation | [5 empty] | P.Nqezo
. Installation of pipes to boreholes | [5 empty] | P.Nqezo | bar: 1st Quarter 3
. Construction of Block walls | [5 empty] | P.Nqezo | bar: 1st Quarter 3 to 2nd Quarter 1
. Plaster and roofing | [5 empty] | P.Nqezo | bar: 2nd Quarter 1
. Practical handover | [5 empty] | P.Nqezo
. Final site handover | [5 empty] | B.Tshitshi | bar: 2nd Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 60000 |  | 200000 | 100000 | 240000 |  | 4th Quarter 2: 600000; 4th Quarter 3: Equitable share
PROJECT NAME: | Electrification of 100 h/h at Sigubudwini ext Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING SIGUBUDWINI OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 1958147.0874
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 1000000 |  | 3rd Quarter 3: 958147.09; 4th Quarter 2: 1958147.09; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 120 h/h at Ngqayimbana Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NGQAYIMBANA OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 2349776.5048
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  | 117488.83 | 0 |  | 4th Quarter 2: 117488.83; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 41 h/h at Ndukudeni Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NDUKUDENI OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 802840.3058
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 40142.0153 | [5 empty] | 4th Quarter 2: 40142.0153; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 56 h/h at Fama Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING FAMA OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 598484.56
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 29924.228 | [5 empty] | 4th Quarter 2: 29924.228; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 57 h/h at Ntongwana Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NTONGWANA OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 609171.7843
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 30458.5892 | [5 empty] | 4th Quarter 2: 30458.5892; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 20 h/h at Vabetsho Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING VABETSHO OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 213744.4857
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 10687.2243 | [5 empty] | 4th Quarter 2: 10687.2243; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 12 h/h at Luphandlasi Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING LUPHANDLASI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 264000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 158400 |  |  | 105600 |  | 4th Quarter 2: 264000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 15 h/h at Jaca Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING JACA OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 198000 |  |  | 132000 |  | 4th Quarter 2: 330000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 21 h/h at Mhlanjeni Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MHLANJENI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 462000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 277200 |  |  | 184800 |  | 4th Quarter 2: 462000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 3 h/h at Meyisi Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MEYISI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 66000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 39600 |  |  | 26400 |  | 4th Quarter 2: 66000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 15 h/h at Bala Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING BALA OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 198000 |  |  | 132000 |  | 4th Quarter 2: 330000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 3 h/h at Ntlakweskolo Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NTLAKWESKOLO OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 66000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 39600 |  |  | 26400 |  | 4th Quarter 2: 66000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 7 h/h at Gqina Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING GQINA OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 154000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 92400 |  |  | 61600 |  | 4th Quarter 2: 154000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 24 h/h at KuMathe Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING KUMATHE OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 528000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 316800 |  |  | 211200 |  | 4th Quarter 2: 528000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 18 h/h at OK Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING OK EXT OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 396000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 237600 |  |  | 158400 |  | 4th Quarter 2: 396000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 5 h/h at Sihlehleni Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING SIHLAHLENI OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 110000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 66000 |  |  | 44000 |  | 4th Quarter 2: 110000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 14 h/h at Cumngce Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING CUMNGCE OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 308000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 184800 |  |  | 123200 |  | 4th Quarter 2: 308000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 100 h/h at Luthulini Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING LUTHULINI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 550000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 330000 |  |  | 220000 |  | 4th Quarter 2: 550000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 100 h/h at Mkhumbi Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MKHUMBI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 220000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 132000 |  |  | 88000 |  | 4th Quarter 2: 220000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 100 h/h at Gcinilifu Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING GCINILIFU OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 220000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 132000 |  |  | 88000 |  | 4th Quarter 2: 220000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Electrification of 15 h/h at Mtshekelweni Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MTSHEKELWENI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Labeling | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· CNC inspection | [5 empty] | M. Gqada
· Outages | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 2nd Quarter 3
· Close-out | [5 empty] | M. Gqada | bar: 2nd Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 198000 |  |  | 132000 |  | 4th Quarter 2: 330000; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Preliminary design of 549 h/h to be electrified in 2018/19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | PRE-ENGINEERING OF WARD 8, 30 & 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 1483835.272
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Pre-liminary design | [5 empty] | . Monthly reports
· Survey | [5 empty] | . Design approval
· Detailed design | [5 empty] | . Constrcution drawings
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Pre-marketing | [5 empty] | M. Gqada
· Pre-liminary design | [5 empty] | M. Gqada
· Survey | [5 empty] | M. Gqada
· Detailed design | [5 empty] | M. Gqada
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 741917.636 |  | 148383.5272 |  | 593534.1088 | 4th Quarter 2: 1483835.272; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Pre-engineering at Wards 6,7,8 and 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | PRE-ENGINEERING OF WARD 6,7,8 and 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/03/2019
TOTAL APPROVED BUDGET: | 1483835.272
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Pre-liminary design | [5 empty] | . Monthly reports
· Survey | [5 empty] | . Design approval
· Detailed design | [5 empty] | . Constrcution drawings
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Pre-marketing | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Pre-liminary design | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Survey | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Detailed design | [5 empty] | M. Gqada | bar: 2nd Quarter 3 to 3rd Quarter 1
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 741917.636 |  | 148383.5272 |  | 593534.1088 | 4th Quarter 2: 1483835.272; 4th Quarter 3: INEP
PROJECT NO.
PROJECT NAME: | Construction of 10 high mast lights at Ward 5, 7,26, 14, 17, 21, 27, 30, 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Erection of high masts at ward 5, 7,26, 14, 17, 21, 27, 30, 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 6500000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Erection of high mast | [5 empty] | . Monthly reports
· Connection to point of supply | [5 empty] | . Completion certificate
· Commissioning | [5 empty] | .
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Custing of foundation and ordering of steel | [5 empty] | M. Gqada | bar: 1st Quarter 1
· Erection of high mast | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Connection to point of supply | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Handover | [5 empty] | M. Gqada | bar: 2nd Quarter 1
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 6200000 |  | 300000 |  |  | 4th Quarter 2: 6500000; 4th Quarter 3: MIG
PROJECT NO.
PROJECT NAME: | Ben Mali SSS Ward 19, Siwali SSS Ward 21, Palmerton SSS Ward 17, Botha Sigcau SSS Ward 18, Mayibenye SSS Ward 5, Flagstaff Comprehensive Ward 7, Vulindlela SSS Ward 2, Zwelibongile SSS Ward 32, Mdutshane SSS Ward 8, Sangoni SSS Ward 13
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Erection of high masts at ward 19, 21, 17, 18, 5, 7, 2, 32, 8 & 13
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/03/2019
TOTAL APPROVED BUDGET: | 7150000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Erection of high mast | [5 empty] | . Monthly reports
· Connection to point of supply | [5 empty] | . Completion certificate
· Commissioning | [5 empty] | .
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Custing of foundation and ordering of steel | [5 empty] | M. Gqada | bar: 1st Quarter 1
· Erection of high mast | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Connection to point of supply | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Handover | [5 empty] | M. Gqada | bar: 2nd Quarter 1
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 350000 |  | 6000000 |  |  | 1st Quarter 1: 800000; 4th Quarter 2: 7150000; 4th Quarter 3: MIG
PROJECT NO.
PROJECT NAME: | Pre-engineering of streetlights at ward 6, Pre-engineering of high mast lights at ward 6
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of streetlights at ward 6, Pre-engineering of high mast lights at ward 6
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/03/2019
TOTAL APPROVED BUDGET: | 2000000
SOURCE OF FUNDING: | STR
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Design for streetlights and highmast lights | [5 empty] | . Monthly reports
. Detailed design
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Pre-design profiling | [5 empty] | M. Gqada
· Preliminary design | [5 empty] | M. Gqada
· Detailed design | [5 empty] | M. Gqada
M. Gqada
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 800000 | 700000 |  |  | 200000 |  | 4th Quarter 2: 1700000; 4th Quarter 3: STR
PROJECT NO.
PROJECT NAME: | Pre-engineering of streetlights at ward 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of streetlights at ward 19
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/03/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Design for streetlights and highmast lights | [5 empty] | . Monthly reports
. Detailed design
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Pre-design profiling | [5 empty] | M. Gqada
· Preliminary design | [5 empty] | M. Gqada
· Detailed design | [5 empty] | M. Gqada
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 300000 |  |  | 200000 |  |  | 4th Quarter 2: 500000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Repair 110 public lights at Ward 6, 15 & 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Repair 110 public lights at Ward 6, 15 & 19
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 750000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired streetlights | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Ordering of material | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Repairs | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· Inspection | [5 empty] | M. Gqada
·
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 150000 |  | 600000 |  |  | 4th Quarter 2: 750000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Repair of high mast light at Ward 6, 15 & 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Repair of high mast light at Ward 6, 15 & 19
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 60000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired streetlights | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Repairs | [5 empty] | M. Gqada | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 15000 |  |  | 15000 |  | 1st Quarter 3: 15000; 3rd Quarter 3: 15000; 4th Quarter 2: 60000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Repair of 2 non working light at Ward 15 & 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Repair of 2 non working light at Ward 15 & 19
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired streetlights | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Ordering of material | [5 empty] | M. Gqada | bar: 1st Quarter 3
· Repairs | [5 empty] | M. Gqada | bar: 2nd Quarter 1
· | [5 empty] | M. Gqada
·
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 200000 | 400000 |  |  |  |  | 4th Quarter 2: 600000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Maintenance of Buildings electricity
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Maintenance of Buildings electricity
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired building wiring | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Ordering of material | [5 empty] | M. Gqada
· Repairs | [5 empty] | M. Gqada | bar: 1st Quarter 3
· | [5 empty] | M. Gqada
·
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 150000 |  |  | 150000 |  | 1st Quarter 3: 100000; 3rd Quarter 3: 100000; 4th Quarter 2: 500000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Maintenance of Buildings electricity
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Maintenance of Buildings electricity
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired building wiring | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Repairs | [5 empty] | M. Gqada | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
·
·
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 150000 |  |  | 150000 |  | 1st Quarter 3: 100000; 3rd Quarter 3: 100000; 4th Quarter 2: 500000; 4th Quarter 3: ES
PROJECT NO.
PROJECT NAME: | Maintenance of standby generator
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Maintenance of standby generator Ward 6
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
· Repaired building wiring | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Repairs | [5 empty] | M. Gqada | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
·
·
·
Projections per milestone | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 200000 |  |  | 100000 |  | 1st Quarter 3: 100000; 3rd Quarter 3: 100000; 4th Quarter 2: 500000; 4th Quarter 3: ES
PROJECT NO.
PROJECT 1.1.18.2
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT |  |  |  |  | 2nd Quarter 1: PROJECT MANAGER
PROJECT NAME: |  | DIESEL TANK | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
PROJECT: |  | CONSTRUCTION OF DISIEL TANK | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
PROJECT STARTING DATE: |  | 04-09-2018 | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
PROJECT COMPLETION DATE: |  | 2019-06-28 | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
TOTAL APPROVED BUDGET: |  | R2 000 000.00 | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
SOURCE OF FUNDING |  | Equitable Share | bar: 1st Quarter 1; 1st Quarter 3 to 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1; 4th Quarter 3
Project Objectives | [6 empty] | 1st Quarter 2: Project Key Performance Indicators
. To ensure desiel bulk storage is within the premises and is safe | [6 empty] | 1st Quarter 2: Elevated Diesel Tank
· To create short term job opportunities | [6 empty] | 1st Quarter 2: EPWP report
Time Frames
Key Milestones | [6 empty] | 1st Quarter 2: Responsible | 3rd Quarter |  |  | 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Site clearance | [7 empty] | P.Nqezo
· Concrete footings | [7 empty] | P.Nqezo
· Assemblisment of tank | [7 empty] | P.Nqezo
· fixing of engen and pumps | [7 empty] | P.Nqezo
· testing and inpection by the energy deparment | [7 empty] | P.Nqezo
· Practical Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  |  | 300000 | 200000 | 200000 | 300000 | 400000 |  | 200000 |  | 300000 |  |  | 300000
PROJECT 1.2.1
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | TRAINING AND WORKSHOPS FOR MUNICIPAL EMPLOYEES
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | TRAINING AND WORKSHOPS FOR MUNICIPAL EMPLOYEES
PROJECT STARTING DATE: |  | 2018-07-02
PROJECT COMPLETION DATE: |  | 2019-06-28
TOTAL APPROVED BUDGET: |  | N/A
SOURCE OF FUNDING |  | N/A
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure that the employees are aware of the requirements for spending and reporting of grants | [7 empty] | Attendence of training and workshops
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Attendence of training and workshops | [7 empty] | L.S. Tshangela and M.Gqada
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  |  | 0
PROJECT 1.3.1
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT (PLANT UNIT) | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | XHOPOZO FENCING
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | FENCING OF LUQHOQHWENI MAIZE FIELD
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | R200 000.00
SOURCE OF FUNDING |  | Equitable Share
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of fencing at luqhoqhweni project | [7 empty] | · Fenced maze field
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.2
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT (PLANT UNIT) | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | LUQHOQHWENI FENCING
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | FENCING OF LUQHOQHWENI MAIZE FIELD
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | R130 000.00
SOURCE OF FUNDING |  | Equitable Share
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of fencing at luqhoqhweni project | [7 empty] | · Fenced maze field
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.3
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | KHANYISA VEG AND POULTRY
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | FENCING OF KHANYISA VEG AND POULTRY
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | R500 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of fencing at khanyisa veg and poultry project | [7 empty] | · Fenced veg and poultry yard
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.4
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | KHANYISA PROJECT
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | DRILLING OF KHANYISA BOREHOLE
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | R200 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
· To ensure provision of water to khanyisa veg and poultry | [7 empty] | · Drilling of bore holes
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Hydrological investigatio | [7 empty] | P.Nqezo
· Site clearance | [7 empty] | P.Nqezo
· Drilling of bore hole | [7 empty] | P.Nqezo
· Installation of pipes | [7 empty] | P.Nqezo
Pumping and testing of water | [7 empty] | P.Nqezo
Construction of pump house | [7 empty] | P.Nqezo
Construction of irrigation system | [7 empty] | P.Nqezo
Testing of water and irrigation system | [7 empty] | P.Nqezo
Final Walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.5
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | KHABINGELE BORE HOLE
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | DRILLING OF KHABINGELE BORE HOLE
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | R200 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
· To ensure provision of water to khabingele veg and poultry | [7 empty] | · Drilling of bore holes
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Hydrological investigatio | [7 empty] | P.Nqezo
· Drilling of bore hole | [7 empty] | P.Nqezo
· Installation of pipes | [7 empty] | P.Nqezo
. Pumping and testing of water | [7 empty] | P.Nqezo
. Construction of pump house | [7 empty] | P.Nqezo
. Constructio of irrigation system | [7 empty] | P.Nqezo
. Practical work over | [7 empty] | B.Tshitshi
. Final work over | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.6
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | JACA WARD 30 FENCING
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | FENCING OF OF JACAWARD 30 MAIZE FIELDS
PROJECT STARTING DATE: |  | 2018-07-04
PROJECT COMPLETION DATE: |  | 2018-09-29
TOTAL APPROVED BUDGET: |  | 170000
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
· To ensure provision of fencing at ward 30 | [7 empty] | · Fenced maze fields
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.7
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | INGUQUKO AGRI CO-OP
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | INGUQUKO AGRI CO-OP RENOVATION AND ALTERATION
PROJECT STARTING DATE: |  | 04-09-2018
PROJECT COMPLETION DATE: |  | 2018-12-14
TOTAL APPROVED BUDGET: |  | R700 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of rennovation and alteration of the project | [7 empty] | · Rennovation
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | P.Nqezo
· preparation of walls for painting | [7 empty] | P.Nqezo
· Construction of walls and plastering | [7 empty] | P.Nqezo
· installation of new doors and windows | [7 empty] | P.Nqezo
· rennovation of roof | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Practical Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.8
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | BUILDING RENOVATION XHURA PROJECT
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | RENNOVATION OF XHURHA RED MEAT PROJECT
PROJECT STARTING DATE: |  | 04-09-2018
PROJECT COMPLETION DATE: |  | 2018-12-14
TOTAL APPROVED BUDGET: |  | R600 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of rennovation and alteration of the project | [7 empty] | · Rennovations
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· preparation of walls for painting | [7 empty] | P.Nqezo
· Construction of walls and plastering | [7 empty] | P.Nqezo
· installation of new doors and windows | [7 empty] | P.Nqezo
· rennovation of roof | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | CONSTRUCTION OF PLANT SITE
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | CONSTRUCTION OF PLANT SITE
PROJECT STARTING DATE: |  | 2019-03-01
PROJECT COMPLETION DATE: |  | 2019-06-30
TOTAL APPROVED BUDGET: |  | R650 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of rennovation and alteration of the project | [7 empty] | Construction
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
P.Nqezo
Reduction of levels | [7 empty] | P.Nqezo
Casting of concrete | [7 empty] | P.Nqezo
signage installation | [7 empty] | P.Nqezo
Cleaning of site | [7 empty] | P.Nqezo
P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.10
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | IINFORMAL TRADING SUPPORT
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | IINFORMAL TRADING SUPPORT
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: |  | 2 000 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of rennovation and alteration of the project | [7 empty] | · Rennovations
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· preparation of walls for painting | [7 empty] | P.Nqezo
· Construction of walls and plastering | [7 empty] | P.Nqezo
· installation of new doors and windows | [7 empty] | P.Nqezo
· rennovation of roof | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.11
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | FENCING OF WARD 07 MILLIE FIELDS
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | FENCING OF WARD 07 MILLIE FIELDS
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: |  | 200 000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
· To ensure provision of fencing at ward 30 | [7 empty] | · Fenced maze fields
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
PROJECT 1.3.12
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER
PROJECT NAME: |  | IINFORMAL TRADING SUPPORT
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | IINFORMAL TRADING SUPPORT
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: |  | 4 000 000.00
SOURCE OF FUNDING |  | GRANT FUNDING FROM DEPARTMENT OF SMALL BUSINESS DEVELOPMENT
Project Objectives | [7 empty] | Project Key Performance Indicators
. To ensure provision of rennovation and alteration of the project | [7 empty] | · Rennovations
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible | [10 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  | 1 | 2 | 3 | 1 | 2 | 3
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2
· Site Establishment | [7 empty] | B.Tshitshi
· Clearing and Grubbing | [7 empty] | P.Nqezo
· Excavation for poles | [7 empty] | P.Nqezo
· installation of fencing poles | [7 empty] | P.Nqezo
· installation of fencing wires and gate | [7 empty] | P.Nqezo
· Genarall Cleaning | [7 empty] | P.Nqezo
· preparation of walls for painting | [7 empty] | P.Nqezo
· Construction of walls and plastering | [7 empty] | P.Nqezo
· installation of new doors and windows | [7 empty] | P.Nqezo
· rennovation of roof | [7 empty] | P.Nqezo
· Final Completion walkover | [7 empty] | B.Tshitshi
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure
Note on D38: Sinazo S. Gono: revise this to reflect current status. The project was report as 100% complete 2 FYs back

## Milestones Technical Services
PROJECT 1.1.1.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | MALOLA ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 16-08-2021
PROJECT COMPLETION DATE: |  |  | 03-06-2022
TOTAL APPROVED BUDGET: |  |  | 3600000
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Malola | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Protection works and installation of signs | [8 empty] | B.Tshitshi
Practical Completion Walkover | [8 empty] | B.Tshitshi
· Project Close-out | [8 empty] | B.Tshitshi | bar: 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 | 2000000 |  |  | 1600000 | [14 empty] | 3600000
PROJECT 1.1.1.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | BUKAZI ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 01-09-2022
PROJECT COMPLETION DATE: |  |  | 30-04-2023
TOTAL APPROVED BUDGET: |  |  | 8300004
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Bukazi | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Clear and Grub, Road bed Preparation | [8 empty] | B.Tshitshi
Installation of pipes | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Tipping of gravel material | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Processing of Gravel material | [8 empty] | B.Tshitshi
Construction of headwalls and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 830000.4 |  |  | 830000.4 |  |  | 1660000.8 | [6 empty] | 1660000.8 |  |  | 4980002.4
PROJECT 1.1.1.3
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | SINGEMBENI ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 05-09-2022
PROJECT COMPLETION DATE: |  |  | 03-05-2023
TOTAL APPROVED BUDGET: |  |  | 6999996
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Singembeni | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Clear and Grub, Road bed Preparation | [8 empty] | B.Tshitshi
Installation of pipes | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Tipping of gravel material | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Processing of Gravel material | [8 empty] | B.Tshitshi
Construction of headwalls and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 699999.6 |  |  | 699999.6 |  |  | 1399999.2 | [6 empty] | 1399999.2 |  |  | 4199997.6
PROJECT 1.1.1.4
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | MATHE TO NGQINA ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 05-09-2022
PROJECT COMPLETION DATE: |  |  | 15-06-2023
TOTAL APPROVED BUDGET: |  |  | 12000000
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mathe to Ngqina | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Clear and Grub, Road bed Preparation | [8 empty] | B.Tshitshi
Installation of pipes | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Tipping of gravel material | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Processing of Gravel material | [8 empty] | B.Tshitshi
Construction of headwalls and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 1200000 |  |  | 1200000 |  |  | 2400000 | [6 empty] | 2400000 |  |  | 7200000
PROJECT 1.1.1.5
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | MAVELELENI ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 02-09-2022
PROJECT COMPLETION DATE: |  |  | 20-06-2023
TOTAL APPROVED BUDGET: |  |  | 7200000
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mavaleleni | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Clear and Grub, Road bed Preparation | [8 empty] | B.Tshitshi
Installation of pipes | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Tipping of gravel material | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Processing of Gravel material | [8 empty] | B.Tshitshi
Construction of headwalls and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 720000 |  |  | 720000 |  |  | 1440000 | [6 empty] | 1440000 |  |  | 4320000
PROJECT 1.1.1.6
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | MAQADINI ACCESS ROAD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 02-09-2022
PROJECT COMPLETION DATE: |  |  | 20-04-2023
TOTAL APPROVED BUDGET: |  |  | 6800004
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mavaleleni | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Clear and Grub, Road bed Preparation | [8 empty] | B.Tshitshi
Installation of pipes | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Tipping of gravel material | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Processing of Gravel material | [8 empty] | B.Tshitshi
Construction of headwalls and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 680000.4 |  |  | 680000.4 |  |  | 1360000.8 | [6 empty] | 1360000.8 |  |  | 4080002.4
PROJECT 1.1.1.7
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | QHAMANGWENI BRIDGE IN WARD 11
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 02-09-2022
PROJECT COMPLETION DATE: |  |  | 20-04-2023
TOTAL APPROVED BUDGET: |  |  | 7299990
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of Qhamangweni Bridge in ward 11 | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Site Establishment | [8 empty] | B.Tshitshi
Base foundation completed | [8 empty] | B.Tshitshi
columns and precast culverts completed | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
top slab and wing walls completed | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Approacing slab and bollards | [8 empty] | B.Tshitshi
Gabions and installation of road signs | [8 empty] | B.Tshitshi
Practical Completion walkover | [8 empty] | B.Tshitshi
Project Close-out | [8 empty] | B.Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 729999 |  |  | 2189997 |  |  | 1459998 | [6 empty] | 1459998 |  |  | 5839992
PROJECT 1.1.2.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | ACQUIRE FUNDING FOR LUSIKISIKI INTERNAL STREETS
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 02-07-2022
PROJECT COMPLETION DATE: |  |  | 20-03-2023
TOTAL APPROVED BUDGET: |  |  | 500000
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of Funding for Lusikisiki Internal Streets | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Preparation of Bussiness plan | [8 empty] | B.Tshitshi
Presentation to Pre-DAC for Funding | [8 empty] | B.Tshitshi
Funding Approved | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 0 |  |  | 0 |  |  | 500000 | [6 empty] | 0 |  |  | 500000
PROJECT 1.1.2.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | ACQUIRE FUNDING FOR FLAGSTAFF INTERNAL STREETS
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 02-07-2022
PROJECT COMPLETION DATE: |  |  | 20-03-2023
TOTAL APPROVED BUDGET: |  |  | 500000
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of Funding for Flagstaff Internal Streets | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Preparation of Bussiness plan | [8 empty] | B. Tshitshi
Presentation to Pre-DAC for Funding | [8 empty] | B. Tshitshi
Funding Approved | [8 empty] | B. Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 0 |  |  | 0 |  |  | 500000 | [6 empty] | 0 |  |  | 500000
PROJECT 1.1.3.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | ACQUIRE FUNDING FOR SURFACING OF 0.5KM R61 ROAD PHASE 2 IN WARD 6 AT FLAGSTAFF TOWN
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 30-08-2022
PROJECT COMPLETION DATE: |  |  | 20-06-2023
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of Surfacing of 0,5km R61 Road Phase 2 in Ward 6 at Flagstaff Town | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Appointment of Contractor and Site establishment | [8 empty] | B.Tshitshi
Pavement layers and sealants | [8 empty] | B.Tshitshi
Paving and kerbing completed | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Protection works road marking and road signs completed | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Practical completion walk over | [8 empty] | B.Tshitshi
Close out
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  |  | 0
PROJECT 1.1.3.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | ACQUIRE FUNDING FOR COMPLETION OF Surfacing of 0,5km R61 Road Phase 2 in Ward 6 at Flagstaff Town
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | ROADS:ROAD CONSTRUCTION
PROJECT STARTING DATE: |  |  | 30-08-2022
PROJECT COMPLETION DATE: |  |  | 20-06-2023
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of Surfacing of 0,5km R61 Road Phase 2 in Ward 6 at Flagstaff Town | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Appointment of Contractor and Site establishment | [8 empty] | B.Tshitshi
Pavement layers and sealants | [8 empty] | B.Tshitshi
Paving and kerbing completed | [8 empty] | B.Tshitshi | bar: 3rd Quarter 1 to 3rd Quarter 3
Protection works road marking and road signs completed | [8 empty] | B.Tshitshi | bar: 4th Quarter 1 to 4th Quarter 3
Practical completion walk over | [8 empty] | B.Tshitshi
Close out
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 0 |  |  | 0 |  |  | 0 | [6 empty] | 0 |  |  | 0
PROJECT 1.1.3.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N Ntloko
PROJECT NAME: |  |  | TRANSPORT HUB
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R1,500,000.00
SOURCE OF FUNDING |  |  | OTP
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of proper transport hub | [8 empty] | · Constructed transport Hub
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service provider | [8 empty] | A.Hlehliso
· Site Establishment | [8 empty] | A.Hlehliso
· Excavations | [8 empty] | A.Hlehliso | bar: 3rd Quarter 1
· Fencing | [8 empty] | A.Hlehliso | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0.00 | 0 |  | R50,000.04 | 0 | R825,000.66 | R825,000.66 | R825,000.66 | R0.00 | R825,000.66 |  | R825,000.66 |  | R0.00 |  |  | R825,000.66 |  |  | R5,000,004.00
PROJECT 1.1.4.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N Ntloko
PROJECT NAME: |  |  | MAINTENANCE OF 160KM OF GRAVEL ACCESS ROADS IN 32 WARDS
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | EARTHWORKS:EARTHWORKS
PROJECT STARTING DATE: |  |  | 2022-09-17
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R5,000,004.00
SOURCE OF FUNDING |  |  | EQUITABLE SHARE
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure maintance of access roads to all 32 wards | [8 empty] | · Maintained operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Blading/Grading | [8 empty] | OP.Zide
· Hauling and Tipping | [8 empty] | OP.Zide | bar: 3rd Quarter 1
· Processing of gravel material | [8 empty] | OP.Zide | bar: 3rd Quarter 1 to 4th Quarter 2
· Cleaning of stormwater pipes | [8 empty] | OP.Zide | bar: 3rd Quarter 3 to 4th Quarter 2
· Genarall Cleaning | [8 empty] | OP.Zide | bar: 4th Quarter 1 to 4th Quarter 2
· Final Completion walkover | [8 empty] | A.Hlehliso | bar: 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0.00 | 0 |  | R50,000.04 | 0 | R825,000.66 | R825,000.66 | R825,000.66 | R0.00 | R825,000.66 |  | R825,000.66 |  | R0.00 |  |  | R825,000.66 |  |  | R5,000,004.00
PROJECT 1.1.4.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N Ntloko
PROJECT NAME: |  |  | REHABILITATION OF SURFACED ROADS IN WARD 06 FLAGSTAFF TOWN
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | PAVEMENTS: PAVEMENTS
PROJECT STARTING DATE: |  |  | 2022-10-07
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R828,000.00
SOURCE OF FUNDING |  |  | EQUITABLE SHARE
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure maintance of surfaced roads | [8 empty] | · Maintained operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Preparation of the road | [8 empty] | OP.Zide
· Filling of base course | [8 empty] | OP.Zide
· Pouring of asphalt and compacting | [8 empty] | OP.Zide
· Road Markings and installation of road signs | [8 empty] | OP.Zide
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 | R0 |  | 0 | R92,000.00 | R92,000.00 | R92,000.00 | R92,000.00 | R92,000.00 | R92,000.00 |  | R0 |  | R138,000.00 |  |  | R138,000.00 |  |  | R828,000.00
PROJECT 1.1.4.3
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N Ntloko
PROJECT NAME: |  |  | REHABILITATION OF SURFACED ROADS IN WARD 15 LUSIKISIKI TOWN
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | PAVEMENTS: PAVEMENTS
PROJECT STARTING DATE: |  |  | 2022-10-07
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R517,500.00
SOURCE OF FUNDING |  |  | EQUITABLE SHARE
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure maintance of surfaced roads | [8 empty] | · Maintained operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Preparation of the road | [8 empty] | OP.Zide
· Filling of base course | [8 empty] | OP.Zide
· Pouring of asphalt and compacting | [8 empty] | OP.Zide
· Road Markings and installation of road signs | [8 empty] | OP.Zide
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 | R0 |  | 0 | R86,250.00 | 0 | R86,250.00 | R0 | R86,250.00 | R0 |  | 0 |  | R86,250.00 |  |  | R86,250.00 |  |  | R517,500.00
PROJECT 1.1.5.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 2 MULTI-PURPOSE SPORTSFIELD PHASE 2
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:SPORTS FACILITY
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R1,000,004.00
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision sports field in ward 2 | [8 empty] | · Operational Sports field
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Fencing Completed | [8 empty] | L.Mgudu
· Steel Fixing Completed | [8 empty] | L.Mgudu
· Brickwork and roofstructure complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 3
· Athiletic Track Complete | [8 empty] | A.Hlehliso | bar: 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 | R0 |  | R500 000 |  |  | R500 000 |  |  | R500 000 | [6 empty] | R500,004.00 |  |  | R1,000,004.00
PROJECT 1.1.5.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 2 MULTI-PURPOSE SPORTSFIELD PHASE 1
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:SPORTS FACILITY
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-09-30
TOTAL APPROVED BUDGET: |  |  | R1,000,004.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision sports field in ward 2 | [8 empty] | · Operational Sports field
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Practical Completion stage | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R1 000 000 | [15 empty] | R1,000,000.00
PROJECT 1.1.5.3
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 26 SPORTS FIELD
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:SPORTS FACILITY
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-12-30
TOTAL APPROVED BUDGET: |  |  | R800,000.00
SOURCE OF FUNDING |  |  | MIG
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision sports field in ward 26 | [8 empty] | · Operational Sports field
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Construction of grandstand and changerooms | [8 empty] | L.Mgudu
· Practical Completion stage | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R300 000 |  |  | R 500 000 | [12 empty] | R800,000.00
PROJECT 1.1.6.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 06 PUBLIC TOILETS PHASE 1
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-12-30
TOTAL APPROVED BUDGET: |  |  | R500,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper public toilets in ward 6 | [8 empty] | · Operational Public tiolets
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of the contractor | [8 empty] | L.Mgudu
· Site Establishment | [8 empty] | L.Mgudu
· Completion of Works | [8 empty] | L.Mgudu
· Practical Completion stage | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R100 000 |  |  | R 400 000 | [12 empty] | R400,000.00
PROJECT 1.1.6.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 15 PUBLIC TOILETS PHASE 1
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-12-30
TOTAL APPROVED BUDGET: |  |  | R500,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper public toilets in ward 15 | [8 empty] | · Operational Public tiolets
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of the contractor | [8 empty] | L.Mgudu
· Site Establishment | [8 empty] | L.Mgudu
· Completion of Works | [8 empty] | L.Mgudu
· Practical Completion stage | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R100 000 |  |  | R 400 000 | [12 empty] | R500,000.00
PROJECT 1.1.7.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | WARD 31 COMMUNITY HALL PLANNING
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-03-30
TOTAL APPROVED BUDGET: |  |  | R500,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper community hall | [8 empty] | · Operational Community Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment and Preparation of business plan | [8 empty] | A.Hlehliso
· Presentation at COGTA | [8 empty] | A.Hlehliso
· Funding Approved | [8 empty] | N.Ntloko | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R100 000 |  |  | R 400 000 | [12 empty] | R500,000.00
PROJECT 1.1.7.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | NEW REST COMMUNITY HALL PLANNING
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-03-30
TOTAL APPROVED BUDGET: |  |  | R500,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper community hall | [8 empty] | · Operational Community Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment and Preparation of business plan | [8 empty] | A.Hlehliso
· Presentation at COGTA | [8 empty] | A.Hlehliso
· Funding Approved | [8 empty] | N.Ntloko | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R100 000 |  |  | R 400 000 | [12 empty] | R500,000.00
PROJECT 1.1.8.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | LUSIKISIKI TOWNHALL PHASE 2
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R3,000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper town hall | [8 empty] | · Operational Town Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Plumbing and electrical works complete | [8 empty] | L.Mgudu
· Superstructure Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 2
· Fencing and paving Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 3 to 4th Quarter 2
· Practical Completion Stage | [8 empty] | A.Hlehliso | bar: 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R300 000 |  | R200 000 | R 700 000 |  | R500 000 |  |  | R200 000 |  | R 300 000 |  |  | R300 000 |  |  | R3 000,000.00
PROJECT 1.1.8.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | FLAGSTAFF TOWNHALL PHASE 2
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R3,000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper town hall | [8 empty] | · Operational Town Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Plumbing and electrical works complete | [8 empty] | L.Mgudu
· Superstructure Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 2
· Fencing and paving Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 3 to 4th Quarter 2
· Practical Completion Stage | [8 empty] | A.Hlehliso | bar: 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R300 000 |  | R200 000 | R 700 000 |  | R500 000 |  |  | R200 000 |  | R 300 000 |  |  | R300 000 |  |  | R3 000,000.00
PROJECT 1.1.9.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | RENOVATIONS OF NEW MUNICAPAL OFFICES
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R8,000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper of municipal offices | [8 empty] | · Operational Municipal Offices
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider and site establishment | [8 empty] | L.Mgudu
· Installation of air conditioners and water proofing | [8 empty] | L.Mgudu
· Construction of paving and sub-soil drainage | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 2
· Renovations of the auditorium | [8 empty] | L.Mgudu | bar: 3rd Quarter 3 to 4th Quarter 2
· Practical Completion Stage | [8 empty] | A.Hlehliso | bar: 4th Quarter 2 to 4th Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  | R 1 000 000.00 |  | R300 000 | R500 000 | R200 000 | R 700 000 | R 1000 000 | R500 000 | R1 000 000 |  | R200 000 |  | R 300 000 |  |  | R800 000 |  |  | R8 000,000.00
PROJECT 1.1.9.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | LUSIKISIKI NEW MUNICAPAL OFFICES
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R30,000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper of municipal offices | [8 empty] | · Operational Municipal Offices
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Site Establishment and clearing | [8 empty] | L.Mgudu
· Setting out and foundations complete | [8 empty] | L.Mgudu
· Concrete Basis Complete | [8 empty] | L.Mgudu
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  | R 4 000 000.00 |  | R1 000 000 | R2 000 000 | R1 000 000 | R 4 700 000 | R 1000 000 | R3 300 000 | R4 000 000 |  | R2 000 000 |  | R 3 000 000 |  |  | R4 000 000 |  |  | R30 000,000.00
PROJECT 1.1.10.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | HOMBE COMMUNITY HALL STAGE
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-12-30
TOTAL APPROVED BUDGET: |  |  | R450,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper of community hall | [8 empty] | · Operational Community Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Site Establishment and clearing | [8 empty] | L.Mgudu
· Construction of stage | [8 empty] | L.Mgudu
· Practical Completion Stage | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R200 000 |  |  | R250 000 | [12 empty] | R450,000.00
PROJECT 1.1.10.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | MAINTENANCE AND RENOVATIONS CLUB-HOUSE
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-03-30
TOTAL APPROVED BUDGET: |  |  | R 2 000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper of community hall | [8 empty] | · Operational Community Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Site Establishment and | [8 empty] | L.Mgudu
· Renovations Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 2
· Practical Completion Stage | [8 empty] | A.Hlehliso | bar: 3rd Quarter 2 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R200 000 |  | R500 000 | R250 000 |  | R550 000 | R500 000 | [9 empty] | R2 000,000.00
PROJECT 1.1.10.3
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N.Ntloko
PROJECT NAME: |  |  | MAINTENANCE AND RENOVATIONS INFORMATION CENTRE
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | OUTDOOR FACILITIES:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-03-30
TOTAL APPROVED BUDGET: |  |  | R 2 000,000.00
SOURCE OF FUNDING |  |  | ES
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision proper of community hall | [8 empty] | · Operational Community Hall
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of Service Provider | [8 empty] | L.Mgudu
· Site Establishment and | [8 empty] | L.Mgudu
· Renovations Complete | [8 empty] | L.Mgudu | bar: 3rd Quarter 1 to 3rd Quarter 2
· Practical Completion Stage | [8 empty] | A.Hlehliso | bar: 3rd Quarter 2 to 3rd Quarter 3
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure |  |  |  | R200 000 |  | R500 000 | R250 000 |  | R550 000 | R500 000 | [9 empty] | R2 000,000.00
PROJECT NO. | 1.1.11.1
PROJECT NAME: |  | Designs of 10 high mast lights at Ndukundeni ward 09,Ngobozana SSS ward 14,Mayalweni ward 18, Robert Ngobozana ward 19,Mthathambi ward 20,Goso Clinic ward 22,Holy Cross Hosipital ward 27,Kanana ward 17,Magwambu ward 04 and Cwija ward 32.
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | Designs of high masts at ward 09,14,18,19,20,22,27,17,04 and 32
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/09/2022
TOTAL APPROVED BUDGET: |  | 500004
SOURCE OF FUNDING: |  | EP
Project Objectives | [6 empty] | Project Key Performance Indicators
· Design for highmast lights | [6 empty] | . Monthly reports
. Final design documents
Key Milestones | [6 empty] | Responsible Official | Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
. Preliminary designs | [6 empty] | S.Mzaza | bar: 1st Quarter 1 to 1st Quarter 2
.Final design Package | [6 empty] | A. Hlehliso | bar: 1st Quarter 3
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 166668 | 166668 |  |  | 166668 |  | 4th Quarter 2: 500004; 4th Quarter 3: EP
PROJECT NO. | 1.1.12.1
PROJECT NAME: |  | Installation of 16 streetlights at ward 19
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | Installation of streetlights at ward 19
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/09/2022
TOTAL APPROVED BUDGET: |  | 500000
SOURCE OF FUNDING: |  | ES
Project Objectives | [6 empty] | Project Key Performance Indicators
· Installation for streetlights | [6 empty] | . Monthly reports
. Completion certificate
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
. Site establisment | [6 empty] | S.Mzaza | bar: 1st Quarter 1 to 1st Quarter 2
. Delivery of material | [6 empty] | S.Mzaza | bar: 1st Quarter 3
. Construction stage | [6 empty] | S.Mzaza | bar: 2nd Quarter 1
. Completion of Certificate | [6 empty] | A.Hlehliso | bar: 2nd Quarter 2
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | [7 empty] | 4th Quarter 2: R500 000.00; 4th Quarter 3: ES
PROJECT NO. | 1.1.12.3
PROJECT NAME: |  | Installation of 22 streetlights at ward 6
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | Installation of streetlights at ward 6
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/09/2022
TOTAL APPROVED BUDGET: |  | R1000 000.00
SOURCE OF FUNDING: |  | STR
Project Objectives | [6 empty] | Project Key Performance Indicators
· Design for streetlights | [6 empty] | . Monthly reports
Completion certificate
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
. Site establisment | [6 empty] | S.Mzaza | bar: 1st Quarter 1 to 1st Quarter 2
. Delivery of material | [6 empty] | S.Mzaza | bar: 1st Quarter 3
. Construction stage | [6 empty] | S.Mzaza | bar: 2nd Quarter 1
. Completion of certificate | [6 empty] | A.Hlehliso | bar: 2nd Quarter 2
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 333333.33 | 333333.33 |  | 333333.33 |  |  | 4th Quarter 2: R1000 000.00; 4th Quarter 3: STR
PROJECT NO. | 1.1.13.1
PROJECT NAME: |  | Electrification of 133 h/h in Ward 18 (Fama,Vabetsho and Ntongwana)
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | ELECTRIFIYING OF WARD 18
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/09/2022
TOTAL APPROVED BUDGET: |  | R350,000.00
SOURCE OF FUNDING: |  | ES
Project Objectives | [6 empty] | Project Key Performance Indicators
· Energizing | [6 empty] | . Monthly reports
· Close-out | [6 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [6 empty] | S.Mzaza | bar: 1st Quarter 1 to 1st Quarter 2
· Energizing | [6 empty] | S.Mzaza | bar: 1st Quarter 3
· Close-out | [6 empty] | A.Hlehliso | bar: 1st Quarter 3
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | R 150,000 | R 200,000 |  |  |  |  | 4th Quarter 2: R 350,000; 4th Quarter 3: ES
PROJECT NO | 1.1.14.1
PROJECT NAME: |  | Repair 100 public lights at Ward 6, 15 & 19
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | Repair 100 public lights at Ward 6, 15 & 19
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/09/2022
TOTAL APPROVED BUDGET: |  | R1000 000.00
SOURCE OF FUNDING: |  | ES
Project Objectives | [6 empty] | Project Key Performance Indicators
· Repaired streetlights | [6 empty] | . Monthly reports
. Completion certificate
.
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Ordering of material | [6 empty] | S.Mzaza | bar: 1st Quarter 1
· Repairs | [6 empty] | S.Mzaza | bar: 1st Quarter 2 to 2nd Quarter 1
· Completion certificate | [6 empty] | A.Hlehliso | bar: 2nd Quarter 2
·
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 333333.33 | 333333.33 |  |  | 333333.33 |  | 4th Quarter 2: R 100 000.00; 4th Quarter 3: ES
PROJECT NO. | 1.1.15.1
PROJECT NAME: |  | Replacement of 1 high mast lights at Ward 15
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM: |  | Erection of high masts at ward 15
PROJECT START DATE: |  | 01/07/2022
PROJECT COMPLETION DATE: |  | 30/10/2022
TOTAL APPROVED BUDGET: |  | 650000
SOURCE OF FUNDING: |  | ES
Project Objectives | [6 empty] | Project Key Performance Indicators
· Erection of high mast | [6 empty] | . Monthly reports
· Connection to point of supply | [6 empty] | . Completion certificate
· Commissioning | [6 empty] | .
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Custing of foundation and ordering of steel | [6 empty] | S.Mzaza | bar: 1st Quarter 1 to 1st Quarter 2
· Erection of high mast | [6 empty] | S.Mzaza | bar: 1st Quarter 3
· Connection to point of supply | [6 empty] | S.Mzaza | bar: 2nd Quarter 1
· Handover | [6 empty] | A.Hlehliso | bar: 2nd Quarter 1
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 216666.66 |  | 216666.66 |  | 216666.66 |  |  | 4th Quarter 2: 650000; 4th Quarter 3: ES
PROJECT 1.1.16.1
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT |  |  |  |  | 2nd Quarter 1: PROJECT MANAGER |  | Director Technical Services: N Ntloko
PROJECT NAME: |  |  | INSTALLATION OF SMASH AND GRAB
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | Flagstaff New Municipal offices
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2022-09-30
TOTAL APPROVED BUDGET: |  |  | R1 500.000
SOURCE OF FUNDING |  |  | EQUITABLE SHARE
Project Objectives | [7 empty] | 1st Quarter 2: Project Key Performance Indicators
· To ensure maintance of offices
· To create short term job opportunities
Time Frames
Key Milestones | [7 empty] | 1st Quarter 2: Responsible
[8 empty] | 1st Quarter 2: Official; 2nd Quarter 3: 1st Quarter; 4th Quarter 2: 2nd Quarter |  |  |  | 3rd Quarter |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Appointment of service provider | [8 empty] | W. Vundle
Installation Complete | [8 empty] | W.Vundle
Project Complete | [8 empty] | A.Hlehliso
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 | R0 |  | 0 | 0 | 0 | 1 500.000 | R0 | 0 | R0 |  | 0 |  | 0 |  |  | 0 |  |  | R1 500.000
PROJECT 1.2.2
DEPARTMENT |  |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: N. Ntloko
PROJECT NAME: |  |  | ACQUIRE FUNDING FOR MIG EXPENDITURE
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  |  | MIG EXPENDITURE
PROJECT STARTING DATE: |  |  | 30-07-2022
PROJECT COMPLETION DATE: |  |  | 30-06-2023
TOTAL APPROVED BUDGET: |  |  | 62127000
SOURCE OF FUNDING |  |  | MIG EXPENDITURE
Project Objectives | [8 empty] | Project Key Performance Indicators
· To ensure provision of MIG EXPENDITURE | [8 empty] | · Operational Road
· To create short term job opportunities | [8 empty] | · EPWP report
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
Expenditure reporting | [8 empty] | B. Tshitshi
Projections Per Milestone | Budget Projections
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  |  | 15531750 |  |  | 15531750 |  |  | 15531750 | [6 empty] | 15531750 |  |  | 62127000

## Corporate Services
IDP No. | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY PERFORMANCE INDICATOR | ANNUAL TARGET | Quarter 1 |  | MEANS OF VERIFICATION | Quarter 2 |  | MEANS OF VERIFICATION | Quarter 3 |  | MEANS OF VERIFICATION | Quarter 4 |  | MEANS OF VERIFICATION | TOTAL BUDGET | MEANS OF VERIFICATION
[6 empty] | Target | Budget |  | Target | Budget |  | Target | Budget |  | Target | Budget
Objective: To promote institutional transformation and organisational development
2.1 | Institutional Transformation and Organizational Development | Ensure sound maintenance of ICT Systems | ICT policies available as a guide | 2.1.1. Percentage monitoring of systems (website (Once off), Munsoft(Mimecast) Pay Day) | 100% | 40% | 688400 | System Monitoring Report and screenshots | 60% | 688400 | System Monitoring Report and screenshots | 80% | 688400 | System Monitoring Report and screenshots | 100% | 688400 | System Monitoring Report and screenshots | 2 622 500 | System Monitoring Report and screenshots
2.1 | Institutional Transformation and Organizational Development | Acquisition of ICT tools of trade. | ICT policies available as a guide | 2.1.2. Number of Computers, printers and projectors | 31 computers, 5 Printers and 3 projectors | N/A | N/A | N/A | 30 Computers | N/A | Delivery Note | N/A | N/A | N/A | 26 laptops 5 Printers and 3 projectors | 1669250 | Delivery Note | 1669250 | Delivery note
2.2 | Institutional Transformation and Organizational Development | Acquisition of ICT softwares | ICT policies available as a guide | 2.1.4. Number of ICT Softwares (Teamviewer, PDF converter, Microsoft Office). | 4 | N/A | N/A | N/A | N/A | N/A | N/A | 2 | 2570250 | Delivery Note | 2 | 2570250 | Delivery note | 5140500 | Delivery note
2.2 | Institutional Transformation and Organizational Development | Provision and improvement of customer care services | Complaints are received through the Presidential Hotline and suggestion boxes | 2.1.5. Percentage of complaints resolved | 100% | 100% | N/A | Complaints Register | 100% | N/A | Complaints Register | 100% | N/A | Complaints Register | 100% | N/A | N/A | N/A | Complaints registwer
2.2 | Institutional Transformation and Organizational Development | Provision of reception services | Employees are provided with access codes monitored monthly | 2.1.6. Number of Telephone Management reports to be generated | 4 | 1 | 684850 | Telephone Report | 1 | 684850 | Telephone Report | 1 | 684850 | Telephone Report | 1 | 684850 | Telephone Report | 2739400 | Telephone usage report
2.2 | Institutional Transformation and Organizational Development | Acquisition of Digital signboards and installation of Telephone system | The digital signboards will be use for advertisements | 2.1.7. Number of Digital Signboards | 1 | N/A | N/A | N/A | 2 | N/A | Delivery note and Installation certificate | N/A | N/A | N/A | 1 | 1.000000,00 | Delivery note and Installation certificate | 1.000000,00 | Delivery note and Installation certificate
2.2 | Institutional Transformation and Organizational Development | Acquisition of diaries and Desk top calenders | The diaries are for the council and the calenders are for the officials | 2.1.8. Percentage of diaries and desk top calenders to be procured | 1 | N/A | N/A | N/A | 1 | 600000 | Delivery Note | N/A | N/A | N/A | N/A | N/A | N/A | 600000 | Deliver note
| Institutional Transformation and Organizational Development | Provision of an electronic document management system | Document management is currently being done manually at the Flagstaff offices | 2.1.10. Number of electronic document management systsems to be procured | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 1700000 | Appointment letter, Delivery note and Installation certificate | 1700000 | Appointment letter, Delivery note and Installation certificate
2.2 | Institutional Transformation and Organizational Development | Provision of office furniture | Furniture is procured when there is a need. Bulk purchase will be done when the Lusikisiki Offices are complete | 2.1.12. Number of Office Furniture Purchases | 2 | N/A | 0 | N/A | 1 | 525000 | Delivery Note | N/A | 0 | N/A | 1 | 525000 | Delivery Note | 1050000 | Delivery note
2.2 | Institutional Transformation and Organizational Development | Provision of cleaning material | Cleaning material is procured quarterly | 2.1.13. Number of times cleaning material is procured | 4 | 1 | 262500 | Delivery Note | 1 | 262500 | Delivery Note | 1 | 262500 | Delivery Note | 1 | 262500 | Delivery Note | 1050000 | Delivery note
| Institutional Transformation and Organizational Development | Provision of office stationery | stationery is procured quarterly | 2.1.14 Number of times office stationery is procured | 2 | N/A | 0 | N/A | N/A | 0 | N/A | 1 | 262500 | Delivery Note | 1 | 262500 | Delivery Note | 1050000 | Delivery note
2.2. | Institutional Transformation and Organizational Development | Administration of employee leave | Leave Policy available as guide | 2.2.1. Number of ESS Reports to be generated | 4 | 1 | 0 | 1 ESS Report | 1 | 0 | 1 ESS Report | 1 | 0 | ESS Report | 1 | 0 | ESS Report | 0 | 4 Payday ESS generated report
2.2. | Institutional Transformation and Organizational Development | Administration of employee benefits | Pension fund Rules in Place and SALGBC collective agreements available as guide | 2.2.2. Number of reports on terminated employees / Councillors | 4 | 1 | 0 | Report of terminated empoyees or councillors | 1 | 0 | Report of terminated empoyees or councillors | 1 | 0 | Report of terminated empoyees or councillors | 1 | 0 | Report of terminated empoyees or councillors | 0 | 1. Report of terminated employees from payday
2.2. | Good Governance and public participation | Policy development & Review | Policy review session of the Municipality is undertaken annually | 2.2.3. Percentage of formulated, reviewed and adopted policies to be distributed and posted on the website | 100% | 0% | 0 |  | 50% | N/A | Attandance register and report for employee consultations | 0% | N/A |  | 100% | N/A | Attandance register and report for employee consultations,Council Resolution | 54337.5 | Council Resolution and adoption of policies
2.2. | Institutional Transformation and Organizational Development | Review of organizational structure | Organisational Structure is reviewed annually | 2.2.4. Number of times organizational structure is reviewed, adopted and signed | 1 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1 | N/A | Council Resolution and copy of the signed taff establishment | N/A | 1. Council Resolution of the adopted Staff Establishment. 2. signed staff establishment structure
2.2. | Institutional Transformation and Organizational Development | Recruitment and Selection | Recruitment is done as per the Recruitment Policy and approved orgnizational structure | 2.2.5. Percentage of budgeted vacant posts to be filled as per approved bulletin | 100% | 25% | 54337.5 | 1.Issued Vacancy Bulletin | 50% | 108675 | 1.Issued Vacancy Bulletin | 75% | 163012.5 | 1.Issued Vacancy Bulletin | 100% | 217350 | 1.Issued Vacancy Bulletin | 217350 | 4 Issued Bulletin
2.2. | Institutional Transformation and Organizational Development | Development of new and changed job description and alignment with the staff establishment | Organisational Structure in place. OD & IPMS Section in place | 2.2.6. Percentage of new and changed Job Descriptions developed | 100% | 100% | N/A | 1. Report on new/ changed drafted job discription. 2. Copies of job descriptions | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1. Report on drafted new/ changed job discription. 2. Copies of job descriptions
2.2. | Institutional Transformation and Organizational Development | Facilitate the Implementation of employee study bursaries. | Functional training Committee and Training and Develoment Policy | 2.2.7 Number of employees offered bursaries | 25 employees to be awarded by 30 June 2023 | 15 | 315000 | 1 report of study assistance beneficieries and copy of advert | N/A | N/A | N/A | 25 | 315000 | 1 report of study assistance beneficieries and copy of advert | N/A | N/A | N/A | 630000 | 1 report of study assistance beneficieries and copy of advert
2.2. | Institutional Transformation and Organizational Development | Provision of tertiary bursaries to deserving students that performed exceptionally/outstandingly | Policy for Bursary Scheme for students in rare skills | 2.2.8. Number of students allocated with bursaries for scarce skills | 5 | 0 | N/A | 0 | N/A | N/A | N/A | 5 | 525000 | 1. Copy of issued advert 2. Proof of Payment 3. Signed bursary aggrements | N/A | N/A | N/A | 525000 | 1. Copy of issued advert 2. Proof of Payment 3. Signed bursary aggrements
2.2. | Institutional Transformation and Organizational Development | Employee Wellness Counseling Services and Support | EAP unit is fully functional. 30 referrals have been undertaken in previous FY | 2.2.9. Number of referrals / consultation provided | 30 | 5 | 40753.12 | Statistics Report | 10 | 40753.12 | Statistics Report | 20 | 40753.12 | Statistics Report | 30 | 40753.12 | Statistics Report | 163012.5 | Statistics Report
2.2. | Institutional Transformation and Organizational Development | Implementation of Physical Wellness Programs | Annual events are held in promotion of employee wellness | 2.2.10. Number of sports activities to be conducted | 2 | 1 | 364061.25 | Attendance register and report | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 208080.02 | attendance register and report | 572269.27 | attendance register and report
2.2. | Institutional Transformation and Organizational Development | Sitting of Employee Wellness Meetings. 4 meetings held in previous FY | Wellness committee seats quarterly | 2.2.11. Number of wellness committee meetings to be held | 4 | 1 | N/A | Attendance registers and minutes | 1 | N/A | Attendance registers and minutes | 1 | N/A | Attendance registers and minutes | 1 | 0 | Attendance registers and minutes | N/A | 1. Attendance Register 2. Minutes of the meeting
2.2. | Institutional Transformation and Organizational Development | Sitting of the Employee Wellness Management programs | EAP Policy and wellness committee in place | 2.2.12. Number of events and workshops to be organized | 8 workshops and 2 events | 2 workshop, 1 event | N/A | Attendance registers and report | 2 workshop | 131577.16 | Attendance registers and report | 2 workshop, 1 event | 186377.15 | Attendance registers and report | 2 workshop | N/A | Attendance registers and report | 317954.31 | 1. Attendance Register 2. Workshop and Event Reports
2.2. | Institutional Transformation and Organizational Development | Maintenance of safety equipment | OHS policy in place as guide. Maintainance is done annually | 2.2.13 Number of services (Maintenance) done to safety equipment | 1 | 0 | N/A | N/A | 1 | 78750 | Copy of invoices and Service report | 1 | 78750 | Copy of invoices and Service report | N/A | N/A | N/A | 78750 | 1. Copy of Invoice & Service Report
2.2. | Institutional Transformation and Organizational Development | Procurement of safety equipment and PPEs. | Availability of Basic Safety Equipment | 2.2.14. Number of safety equipment to be procured | 2 | 0 | N/A | N/A | 1 | 591281.25 | 1. Copy of Invoice 2. Copy of delivery note | 0 | N/A | N/A | 1 | 591281.25 | 1. Copy of Invoice 2. Copy of delivery note | 1182562.5 | 1. Copy of Invoice 2. Copy of delivery note
2.2. | Institutional Transformation and Organizational Development | Sitting of Occupational Health and Safety Committee meetings | Health and Safety Committee convenes quarterly and when need arises. 5 meetings held in previous FY | 2.2.15. Number of Health and Safety Committee meetings to be held | 4 | 1 | 10200 | 1. Attendance Register 2. Minutes of the meeting | 1 | 10200 | 1. Attendance Register 2. Minutes of the meeting | 1 | 10200 | 1. Attendance Register 2. Minutes of the meeting | 1 | 10200 | 1. Attendance Register 2. Minutes of the meeting | N/A | 1. Attendance Register 2. Minutes of the meeting
2.2. | Institutional Transformation and Organizational Development | Facilitation of fire drill exercise for fire fighters and refresher training first aiders | Fire fighters and first aiders in place | 2.2.16. Number of fire drill exercise for fire fighters and refersher training for first aiders | 2 Fire Drills and 1 training | N/A | N/A | N/A | 1. Fire Drill Exercise | N/A | Attendance Registers Fire Drill Exercesice Report | N/A | N/A | N/A | 1 firedrill, 1 training | N/A | Attendance Registers Fire Drill Exercesice Report and attendance register and report for the training | N/A | 1. Attendance Registers 2. Fire Drill Exercesice Report 3. Training report
2.2. | Institutional Transformation and Organizational Development | Sitting of the EE Committee meeting | Employment Equity Policy in place. Approved EE Plan and Functional EE Committee in place | 2.2.17. Number of EE Committee meetings to be held | 4 | 1 | N/A | 1. Attendance Register 2. Minutes of the meeting | 1 | N/A | 1. Attendance Register 2. Minutes of the meeting | 1 | N/A | 1. Attendance Register 2. Minutes of the meeting | 1 | N/A | 1. Attendance Register 2. Minutes of the meeting | N/A | 1. Attendance Register 2. Minutes of the meeting
2.2. | Institutional Transformation and Organizational Development | Coordinate the implementation of Employment Equity awareness campaigns. | Employment Equity Policy in place. Approved EE Plan and Functional EE Committee in place | 2.2.18. Number of employment equity awareness campaigns to be held | 1 | N/A | N/A | N/A | 1 | N/A | 1. Attendance Register 2. Report | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 1. Attendance Register 2. Statistical Report
2.2. | Institutional Transformation and Organizational Development | Facilitate the submission of jobs for grading. | Job Evaluation Committee in place. Signed job descriptions in place | 2.2.19. % of Job description reviewed and resubmitted for grading | 100% | N/A | N/A | N/A | 50% of job grading maintenance results implemented. | 100000 | Attendance register of the job evaluation committee and reports | 100% of job grading maintenance results implemented. | 50 000.00 | Attendance register of the job evaluation committee and reports | N/A | N/A | N/A | N/A | Attendance register of the job evaluation committee and reports
2.2 | Institutional Transformation and Organizational Development | Training of the Workplace Services and Restructuring Committee | OD and IPMS Unit in place. Worplace Services and Restructuring Committee functioning. | 2.2.20. Number of trainings for committee members | 1 | N/A | N/A | N/A | N/A | N/A | N/A | 1 | 21000 | Attendance registers and report | N/A | N/A | N/A | N/A | Attendance register and report
2.2. | Institutional Transformation and Organizational Development | Sitting of the WPSRC meeting | Workplace Services and Restructuring committee in place. | 2.2.21 Number of WPSRC meetings to be held | 4 | 1 | N/A | Attendance registers and report | 1 | N/A | Attendance registers and report | 1 | N/A | Attendance registers and report | 1 | N/A | Attendance registers and report | N/A | Attendance registers and report
2.3 | Local Economic Development | Facilitate the training of SMMEs | Adopted Workplace Skills Plan, Training and Development Policy | 2.2.22 Number of SMME members to be trained | 20 | N/A |  | N/A | N/A | N/A | N/A | 20 | 262500 | Attendance registers and report | N/A | N/A | N/A | 262500 | 1. Attendance Register 2. Report on trainings conducted
2.4. | Financial Viability | Coordinate the dispensation of funds received from LGSETA towards identified training | Municipality recieves an annual grant from LGSETA | 2.2.23. Number of times payments towards the LGSETA Mandatory Grant are received | 2 | NA | NA | NA | 1 | N/A | 1.IHLM Bank Statement 2. Report from LGSETA | NA | NA | NA | 1 | N/A | 1.IHLM Bank Statement 2. Report from LGSETA | 120000 | 1.IHLM Bank Statement 2. Report from LGSETA
2.5 | Good Governance and public participation | Sitting of the Local Labour Forum | Local labour forum ( LLF) & Labour Relations unit in place | 2.2.24.Number of Local labour forum meetings to be convened | 4 | 1 | 8150 | Attendance registers and report | 1 | 8150 | Attendance registers and report | 1 | 6575 | Attendance registers and report | 1 | 9727.5 | Attendance registers and report | 32602.50 | 1. Attendance Register 2. Report of the meeting
2.5 | Good Governance and public participation | Sitting of Labour Relations roadshows | Labour Relations unit in place and policies, regulations and procedures in place. | 2.2.25. Number of Labour relations Roadshows to be conducted | 2 | N/A | N/A | N/A | 1 | 0 | Attendance registers and report | N/A | N/A | N/A | 1 | N/A | Attendance registers and report | N/A | 1.Attendance Register 2. Statistical workshop report
2.5 | Good Governance and public participation | Coordination of trainings for communities, councilors and employees | 150 employees and councillors were trained | 2.2.26. Percentage of training interventions for communities, councillors and employees as per the Workplace Skills Plan | 100% | 20% | 600000 | Attendance registers and report | 50% | 1400000 | Attendance registers and report | 80% | 1600000 | Attendance Register and Report | 100% | 2000000 | Attendance Register and Report | 2000000 | 1. Attendance Register 2. Report on trainings conducted
5.1 | Good Governance and Public Participation | Facilitation of the signing of performance agreements | PMS policy in place. Signed performance agreements in 2021/22 | 2.2.27. Number of performance agreements signed by senior and middle managers | 23 | 23 | 0 | Signed Performance agreements | NA | NA | NA | 6 | N/A | Signed Performance agreements | NA | N/A | N/A | R0.00 | Signed Performance agreements
5.1 | Good Governance and Public Participation | Facilitation of the sitting of performance reviews | PMS policy in place | 2.2.28. Number of times performance reviews are held for middle management | 2 | 1 | 157500 | Attendance register and report | NA | NA | NA | 1 | 157500 | Attendance register and report | NA | NA | NA | 315000 | Attendance register and report

## Milestones Corporate Services
Objective: To promote institutional transformation and organisational development
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Human Resource Administration
INSTITUTION: |  |  | Ingquza Hill Local Municipality
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | Nil
Project Objectives |  |  | Project Key Performance Indicators
To promote institutional transformation and organisational development |  |  | Leave Management report generated and conciliated with the attendance register.
Time Frames
Key Milestones |  |  | Responsible
|  |  | Official | [8 empty] | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Leave reconciliation and management |  |  | Jakavu | [8 empty] | 1 |  |  |  |  | 1 |  |  |  |  | 1 |  |  |  | 1
Process benefits for terminated employees |  |  | Jakavu
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [23 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 |  |  | 3
|  |  |  | X1 Report |  |  | X1 Report |  |  | X1 Report | [5 empty] | X1 Report |  |  | Nil | [5 empty] | Nil
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Recruitment and Selection
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 217350
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
To Promote institutional transformation and organisational development | [8 empty] | Percentage of budget vacant posts to be filled.
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Advertising of vacant budget posts | [8 empty] | Mbangatha
Interview and selection processes | [8 empty] | Mbangatha
Screening of recommended candidates | [8 empty] | Mbangatha
Appointment of successful candidate | [8 empty] | Mbangatha
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Bulletin Adverts |  | 54337.5 |  |  | 108675 |  |  | 163012.5 |  |  |  | 217350 | [7 empty] | 217350 | [6 empty] | Equitable share
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [12 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Employee Assistance Programme
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 1 486 800
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Implementation of the Employee Wellness Strategy | [8 empty] | Number of referrals\consultation resolved
Number of wellness committee meetings conducted
Number of event\workshop organized
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter |  |  |  | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[15 empty] | 1 | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3
To have one on one session with affected employee or councilor and refer to external psychologist when necessary | [8 empty] | BAM
Convene a meeting for Wellness Committee to get employees involved in EAP Programme | [8 empty] | BAM
Organise World Aids Day for employees and councilors | [8 empty] | BAM
Organise substance abuse workshop | [8 empty] | BAM
Organise Wellness Day for employees and councilors | [8 empty] | BAM
Organise Cancer Awareness Workshop | [8 empty] | BAM
Organise Physical Wellness activities | [8 empty] | BAM
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [27 empty] | Source of Finance
| 1st Quarter |  |  |  | 2rd Quarter |  |  | 3th Quarter |  |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
one on one session with affected employee or councilor and refer to external psychoogist when necessary |  | 13912.5 |  |  |  | 13912.5 |  |  | 13912.5 |  |  |  |  | 13912.5 | [7 empty] | 55650 | [6 empty] | Equitable Share
Organise world Aids Day Event for Employees and councilors | [6 empty] | 85575 | [14 empty] | 85575 | [6 empty] | Equitable Share
Orginise Wellness Day for employees and councilors | [6 empty] | 85575 | [14 empty] | 85575 | [6 empty] | Equitable Share
Physical Wellness Activities. |  |  |  | 630000 | [13 empty] | 630000 |  |  |  | 1 260 000 | [6 empty] | Equitable Share
DEPARTMENT | Corporate Services | [11 empty] | PROJECT MANAGER | [12 empty] | Ms. M Matubatuba
PROJECT NAME: | LABOUR RELATIONS ACTIVITIES
INSTITUTION: | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 32602.50
SOURCE OF FUNDING | Equitable share
Project Objectives | [10 empty] | Project Key Performance Indicators
Adherence to labour relations practice guided by labour relations act as amended | [10 empty] | No of local labour forum meetings convened
Municipal systems act and existing policies | [10 empty] | No of labour relations workshops and roadshows conducted
Time Frames
Key Milestones | [10 empty] | Responsible
[11 empty] | Official |  |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [7 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[16 empty] | 1 |  |  | 2 | 3 | 1 |  | 2 |  | 3 |  |  | 1 |  | 2 | 3 |  |  | 1 |  | 2 | 3
convene local labour forum meetings for sound labour relations | [10 empty] | Ndlala
conduct roadshows and workshops in partnership with SALGA and CCMA | [10 empty] | Ndlala
Roadshows | [10 empty] | Ndlala
Projections Per Milestone |  | Budget Projections in multiples of R1000 (xR1000) | [29 empty] | Source of Finance
|  | 1st Quarter |  |  |  | 2nd Quarter |  | 3rd Quarter | [6 empty] | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 |  | 2 |  | 3 | 1 |  | 2 |  | 3 |  |  | 1 | 2 |  |  |  | 3
Organising of Local Labour Forum |  |  |  | 8150.62 |  |  |  |  | 8150.62 |  |  |  |  | 8150.62 | [7 empty] | 8150.62 |  |  |  |  | 32602.5 | [7 empty] | Equitable share
Organising Periodic Induction | [6 empty] | 25000 | [10 empty] | 25000 | [8 empty] | 50000 | [7 empty] | Equitable share
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | POLICY REVIEW
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | Nil
SOURCE OF FUNDING |  |  | Nil
Project Objectives | [8 empty] | Project Key Performance Indicators
Policy Review | [8 empty] | % of formulated, reviewed and adopted policies to be distributed and posted on the website.
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
List of submitted policies to be formulated, reviewed by departments | [8 empty] | Ndlala
Meeting with departments and relevant committee for consultations | [8 empty] | Ndlala
Adoption of formulated, reviewed and adopted policies to be distributed and posted on the website by the council | [8 empty] | Ndlala
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Nil | [26 empty] | Nil
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | OCCUPATIONAL HEALTH AND SAFETY
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 78750
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Implementation of the Employee Wellness Strategy | [8 empty] | Number of services (Maintenance) done to safety equipment
number of Safety Equipment to be Procured
Number of Health and Safety Committee meeting
Number of fire drill exercise and refresher training to fire fighters
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct service of safety equipment | [8 empty] | Mtshengu
Procurement of Personal Protective Equipment and glue for pasting symbolic signs | [8 empty] | Mtshengu
Initiate health and safety meeting for compliance with Health and Safety Act | [8 empty] | Mtshengu
Conduct fire drill exercise for fire fighters’ | [8 empty] | Mtshengu
Conduct refresher training to fire fighters’ | [8 empty] | Mtshengu
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Servicing of safety equipment | [11 empty] | 36750 | [7 empty] | 36750 | [6 empty] | Equitable shares
Facilitate procurement of protective clothing |  | 5500 |  |  | 5500 |  |  | 51000 |  |  |  | 5500 | [7 empty] | 20000 | [6 empty] | Equitable shares.
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | TRAINING OF EMPLOYEES AND COUNCILLORS
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R2000 000.00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
.Implementation of learnerships, Skills programme, on the job training, succession, planning related training through workplace skills plan. | [8 empty] | Signed attendance registers by learners
Evaluation report from HRD.
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Submission of signed pre-requisition to SCM arranging soliciting of Service Provider. | [8 empty] | Ntotho
Implementation of training programmes. | [8 empty] | Ntotho
Draft and Submit applications for Discretionary grants to SETAs and monitoring of mandatory grant reimbursement. | [8 empty] | Ntotho
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Implementation of training programme |  | R |  |  |  |  | 300000 |  |  | 800000 |  | R |  |  |  |  | 500000 |  |  | 2 000 000 | [6 empty] | Equitable shares
400000
DEPARTMENT |  |  | Corporate Services | [6 empty] | PROJECT MANAGER | [10 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Bursary for Community Members
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2023-07-01
PROJECT COMPLETION DATE: |  |  | 2022-06-30
TOTAL APPROVED BUDGET: |  |  | 600000
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Implementation of Community Bursary through workplace skills plan | [8 empty] | Signed Contract agreement by all parties
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Issuing of advert to all communication channels | [8 empty] | Ntotho
Convening Training selection committee meetings to select | [8 empty] | Ntotho
Writing acceptance letters to the selected beneficiaries | [8 empty] | Ntotho
Arrange payments for successful applicants | [8 empty] | Ntotho
Request results from beneficiaries for their progress | [8 empty] | Ntotho
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [8 empty] | 600000 | [10 empty] | 600000 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Study Assistance for Employees
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | R630 000 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Implementation of study assistance to employees through workplace skills plan | [8 empty] | Signed study assistance agreements by all parties.
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Issuing of advert to all employees | [8 empty] | Ntotho
Convening Training selection committee meeting to select | [8 empty] | Ntotho
Writing acceptance and regret letters to the applications | [8 empty] | Ntotho
Arrange payments for successful applicants | [8 empty] | Ntotho
Request results from beneficiaries for their examinations and assignments | [8 empty] | Ntotho
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [8 empty] | R315 000,00 | [10 empty] | 630000 | [6 empty] | Equitable shares
R315 000,00
DEPARTMENT | Corporate Services |  | PROJECT MANAGER | [5 empty] | Ms. M Matubatuba
PROJECT NAME: | ORGANISATIONAL DEVELOPMENT AND IPMS
INSTITUTION: | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 315000
SOURCE OF FUNDING | General Revenue
Project Objectives |  | Project Key Performance Indicators
To promote institutional transfomation and organisation development |  | Adopted and signed Organisational structure and council resolution.
% of drafted Job Descriptions
Number of workplace services and restructuring committee meeting to be held
% of final outcomes reports of job evaluation maintenance phase implemented.
Facilitate the annual training of the workplace services and restructuring committee
Time Frames
Key Milestones |  | Responsible
|  | Official |  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter | [6 empty] | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 |  |  | 1 |  | 2 |  | 3 |  | 1 |  | 2 |  | 3
Benchmark and develop Draft Job Description for new positions. |  | Mkhize
Facilitate the perfomance assessment of middle managers |  | Mkhize
Convening the workplace services and restructuring committee meeting |  | Mkhize
Facilitate the implementation of TASK JE maintenance phase final outcomes results |  | Mkhize
Annual training of the workplace services and restructuring committee |  | Mkhize
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [12 empty] | Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Project expenditure | 0 | 0 | 0 | 0 |  | 200000 | 0 | 50000 | 0 |  |  | 65000 | 315000 | General Revenue
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Sound monitoring of ICT system
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 2 622 400 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Sound Monitoring of ICT system | [8 empty] | Percentage monitoring of system
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | M. Skhonza
Draft terms of reference
Acquire system
monitor system perfomence and upgrade
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure |  |  |  | 688 400.00 |  |  | 688 400.00 |  |  | 688 400.00 | [6 empty] | 688 400.00 |  |  | 2 622 400 00 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Acquisition of ICT infrastructure
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 844 300 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Acquisition of ICT infrastructure | [8 empty] | number of Computers, printers and projectors purchased
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | M. Skhonza
Draft Specifications
Submit prerequsitions
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 700 00 | [9 empty] | 144 300 00 |  |  | 844 300 00 | [6 empty] | Equitable shares+A326A316:AE344
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Acquisition of ICT infrastructure
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 128518500
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Number of ICT Servers to be procured and public wifi installed | [8 empty] | Number of ICT Servers to be procured and public wifi installed
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | M. Skhonza
Draft Specifications
Submit prerequsitions
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 128518500 | [12 empty] | 128518500 | [6 empty] | Equitable share
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Acquisition of ICT infrastructure
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 5140 250 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Number of ICT softwares procured | [8 empty] | Number of ICT softwares procured
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | M. Skhonza
Draft Specifications
Submit prerequsitions
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 2570 250 00 | [9 empty] | 2570 250 00 |  |  | 5140 500 00 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision and improvement of customer care services
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision and improvement of customer care services | [8 empty] | Percentage of complaints management
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Receive and record complaints | [8 empty] | M. Mfingwana
Verify complaint validity
Redress
Resolve and close complaint
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [26 empty] | Equitable shares
#NAME?
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision Reception services
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 2739 400 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision of reception services | [8 empty] | Number of Telephone Management reports generated
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Attend to incoming call | [8 empty] | M. Mfingwana
monitor telephone usage
attend to walk in
receive and record messages
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure |  |  |  | 6848500 |  |  | 6848500 | [9 empty] | 6848500 |  |  | 2739400 | [6 empty] | Equitable shares
6848500
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Acquisition of Digital signboards and installation of Telephone system
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 600000
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Acquisition of Digital signboards and installation of Telephone system+A451:AE47 | [8 empty] | Number of Digital Signboards and door signs Installation certificate
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Draft Terms of Reference | [8 empty] | M. Mfingwana
Draft specication
Submit prerequisition
Operation and Maitainence
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 600000 | [12 empty] | 600000 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Acquisition of diaries and Desk top calender
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 300000
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Acquisition of diaries and Desk top calender | [8 empty] | Percentage of diaries and desk top calenders procured
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | M. Mfingwana
Draft specication
Submit prerequisition
Receive and distribute
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 300000 | [12 empty] | 300000 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision of Customer care Survey
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision of Customer care Survey | [8 empty] | Number of Surveys conducted
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Drafting of Customer survey form | [8 empty] | M. Mfingwana
Data collection
Data submision
Survey Report
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [19 empty] | 0 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision of Records Management
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 1700000
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision of Records Management | [8 empty] | Number of Surveys conducted
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Populate file plan | [8 empty] | B.Capa
Document transfer
Document recording
Record keeping
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure | [6 empty] | 800 00 | [9 empty] | 900000 |  |  | 1700000 | [6 empty] | Equitable shares
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision of Cleaning services
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 525000
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision of Cleaning services | [8 empty] | Number of reports on signed checklist for cleaning
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Personnel alloction | [8 empty] | B.Capa
Draft cleaning schedule
Monitoring of hourly checklist
Report submisiom
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure |  |  |  | 131 250 00 |  |  | 131 250 00 | [9 empty] | 131 250 00 |  |  | 525000 | [6 empty] | Equitable shares
131 250 00
#NAME?
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Provision of Admin Support Services through purchasing of furniture
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 1 0500 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Provision of Admin Support Services through purchasing of furniture | [8 empty] | Number of Office Furniture Purchases
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | B.Capa
Draft Specification
Submit prerequistion
Receive and distribute
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure |  |  |  | 262500 |  |  | 262500 | [9 empty] | 262500 |  |  | 1 0500 00 | [6 empty] | Equitable shares
262500
DEPARTMENT |  |  | Corporate Services | [7 empty] | PROJECT MANAGER | [9 empty] | Ms. M Matubatuba
PROJECT NAME: |  |  | Purchase of cleaning material
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 1 0500 00
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Purchase of cleaning material | [8 empty] | Number of cleaning material Purchases
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Conduct needs analysis | [8 empty] | B.Capa
Draft Specification
Submit prerequistion
Receive and distribute
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project Implementation expenditure |  |  |  | 262500 |  |  | 262500 | [9 empty] | 262500 |  |  | 1 0500 00 | [6 empty] | Equitable shares
262500

## Planning & Development
IDP NO. | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGETS | [11 empty] | TOTAL BUDGET | MEANS OF VERIFICATION
[6 empty] | Quarter 1 |  |  | Quarter 2 |  |  | Quarter 3 |  |  | Quarter 4
[6 empty] | tar | bud | Means of verification | tar | bud | Means of verification | tar | bud | Means of verification | tar | bud | Means of verification
Objective: To promote local economic development
3.3 | To promote local economic development | Support of farmers with inputs | 4 farmer clusters supported in the previous year | 3.1.1. Percentage of farmers supported with inputs | 100% | 15% | _ | Terms of reference | 60% | 500000 | Progress Report | 100% | 500000 | Closeout report | N/A | 0 | Closeout report | 1000000 | Close out report
3.3 | To promote local economic development | Provision of equipment & machinery for Xhura Wool Growers | Agricultural Strategy available as guide | 3.1.2. Percentage of equipment & machinery to be delivered | 100% | 15% | _ | Terms of reference | 30% |  | Inception report | 100% |  | Delivery note & closeout report | N/A | _ | N/A | 500000 | Delivery note & closeout report
3.1 | To promote local economic development | Provision of equipment & machinery for Sigubudwini wool growers | Agricultural Strategy available as guide | 3.1.3. Percentage of equipment & machinery to be delivered | 100% | 15% | _ | Terms of reference | 30% | 75000 | Progress Report | 70% | 300000 | Delivery note & close out report | 100% | 125000 | Project Completion report | 500000 | Project Completion report
3.3 | To promote local economic development | Provision of animal feed, vaccines & medication | Agricultural Strategy available as guide | 3.1.6. Percentage provision of animal feed, vaccines & medication | 100% | 5% | _ | Terms of reference | 50% | 225000 | Progress Report | 75% | 225000 | Progress report | 100% | 450000 | Closeout report | 450000 | Close out report
| To promote local economic development | Fencing of Xopozo agriculture project | Agricultural Strategy available as guide | 3.1.7. Percentage completion project completion of fencing of Xopozo project | 100% | 49% | R0.00 | Minutes for the meeting to revive the project | 60% | R174 801,60 | Progress Report | 100% | R116 535,00 | Completion Certificate | N/A |  | N/A | R442 414,00 | Completion Certicate
| To promote local economic development | Fencing of jaca project | Agricultural Strategy available as guide | 3.1.8. 100% completion of fencing of Jaca Project | 100% | 100% |  | Completion Certificate | N/A |  | N/A | N/A |  | N/A | N/A |  | N/A |  | Completion Certicate
3.3 | To promote local economic development | Fencing of Mamjazi (ward 17) and Lande (Ward 26) farming projects | 4 farmer clusters supported in the previous year | 3.1.9. Percentage completion of fencing at Majazi and Lande farming projects | 100% | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 100% |  | Monthly progress reports and Completion Certificate | 500000 | Completion Certicate
3.3 | To promote local economic development | Provision of borehole pump and irrigation system at Khabingele Farm in ward 28. | 4 farmer clusters supported in the previous year | 3.1.10. Percentage completion in the provision of borehole pump and irrigation system | 100% | N/A | N/A | N/A | N/A | N/A | N/A | 100% | N/A | N/A | 100% | 250000 | Completion Certificate | 250000 | Completion Certificate
| To promote local economic development | Provision of borehole and irrigation system at Magazi in Ward 20 | 5 farmer clusters supported in the previous year | 3.1.11. Percentage completion in the provision of borehole and irrigation system | 100% | N/A | N/A | N/A | N/A | N/A | N/A | 100% | N/A | N/A | 100% | 250000 | Completion Certificate | 250000 | Completion Certificate
3.3 | To promote local economic development | Sitting of LTO Meetings | Tourism Sector Plan implementation plan | 3.2.1. Number of Local Tourism Organization meetings to be held | 3 | 1 | 40000 | Attendance register, minutes, report | 1 | 40000 | Attendance register and report | 1 | 20000 | N/A | N/A | 0 | N/A | 100000 | Attendance register and minutes of the meetings
3.3 | To promote local economic development | Training of Tourist guides | Implementation of the Tourism Sector Plan | 3.2.2. Number of tourist guides to be trained | 10 | N/A |  | N/A | N/A | _ | N/A | N/A | N/A | N/A | 10 | 300000 | Attendance Register and Report | 300000 | Attendance Register and Report
3.3 | To promote local economic development | Participation in tourism trade shows | Implementation of the Tourism Sector Plan | 3.2.3. Number of tourism trade shows to be attended | 1 | N/A | _ | N/A | N/A | 0 | N/A | N/A | 0 | N/A | 1 | 400000 | Attendance register and report | 400000 | Attendance registers and report
3.3 | To promote local economic development | Procurement of Tourism Marketing Material | Implementation of the Tourism Sector Plan | 3.2.4. Number of times tourism marketing material is procured | 1 | N/A | 0 | N/A | N/A | 0 | N/A | 1 | 300000 | Delivery note | N/A | _ | N/A | 300000 | Delivery note
3.3 | To promote local economic development | Host a Tourism Promotion Annual event | Implementation of the Tourism Sector Plan | 3.2.5. Number of annual tourism events to be held | 1 | N/A |  | N/A | 1 | 1750000 | Concept document, attendance registers and report | N/A | N/A | N/A | 1 | 1750000 | Concept document, attendance registers and report | 1750000 | Concept document, attendance registers and reports
3.3 | To promote local economic development | Sitting of community engagements on aforestation | Implementation of Forestry Development Strategy | 3.3.1. Number of community engagements on aforestation to be held | 4 | 1 | 0 | Attendance Register and report | 1 | _ | Attendance Register and report | 1 | _ | Attendance Register and report | 1 | _ | Attendance Register and report |  | Attendance Register and report
3.3 | To promote local economic development | Conduct fire awareness compaigns | Implementation of Forestry Development Strategy | 3.3.2. Number of fire awareness campaigns to be held | 2 | 1 | 50000 | Attendance Register and report | N/A | 0 | N/A | 1 | 50000 | Attendance Register and report | N/A | 0 | N/A | 100000 | Attendance Register and report
3.3 | To promote local economic development | Support of fishing cooperatives with fishing gear | Implementation of Forestry Development Strategy | 3.3.4. Number of cooperatives supported with fishing gear | 2 | N/A | 0 | N/A | N/A | 0 | N/A | 2 | 300000 | Delivery note, attendance register and report | N/A | _ | N/A | 300000 | Delivery note, attendance register and report
3.3 | To promote local economic development | Support of fishing cooperatives with cold storage and store room facility | Implementation of Forestry Development Strategy | 3.3.5. Number of cooperatives provided with cold storage and store room facility | 1 | 0 | 0 | N/A | N/A | 0 | N/A | 1 | 300000 | Delivery note, attendance register and report | _ | _ | _ | 300000 | Delivery note, attendance register and report
3.3 | To promote local economic development | Capacity Building for SMMEs | Implementation of SMME Strategy | 3.4.1. Number of capacity building sessions for SMMEs conducted | 4 | 1 | 125000 | Attendance Register and Report | 1 | 125000 | Attendance Register and Report | 1 | 125000 | Attendance Register and Report | 1 | 125000 | Attendance register and report | 500000 | Attendance register and report
3.3 | To promote local economic development | Provision of refrigerators to retail enterprises | 32 spaza shops are being supported | 3.4.2. Number of refrigerators to be procured for the 32 spaza shops | 32 refrigerators | N/A |  | N/A | N/A |  | N/A | N/A | 0 | N/A | 32 refrigerators | 2000000 | Delivery note, attendance register and report distribution register | 2000000 | Delivery note, attendance register and report distribution register
3.5 | To promote local economic development | Sitting of LED Cluster meetings | Implementation of SMME Strategy | 3.4.3. Number of LED Cluster meetings to be held | 3 | 1 | 10000 | Attendance Register and minutes | 1 | 10000 | Attendance Register and minutes | 1 | 10000 | Attendance Register and minutes | N/A | N/A | N/A | 40000 | Attendance Register and minutes
3.1 | To promote local economic development | Provision of Hawker Stalls in ward 15 | Implementation of SMME Strategy | 3.4.6. Number of hawker stalls to be provided (Ward 15) | 15 | N/A | N/A | N/A | 0 | 0 | Terms of reference | 0 | _ | Progress report | 15 | 1787000 | Progress report | 1787000 | Delivery note, attendance register and report
3.1 | To promote local economic development | Provision of Hawker Stalls in ward 06 | Implementation of SMME Strategy | 3.4.7. Number of hawker stalls provided (Ward 6) | 15 | N/A | N/A | N/A | 0 | 0 | Terms of reference | 0 | _ | Progress report | 15 | 2000000 | Progress report | 2000000 | Delivery note, attendance register and report
3.3 | To promote local economic development | Capacity building for Cooperatives | Implementation of SMME Strategy | 3.4.8. Number of cooperatives capacitated | 4 | 1 | 25000 | Capacity building report and attendance register | 1 | 25000 | Capacity building report and attendance register | 1 | 25000 | Capacity building report and attendance register | 1 | 25000 | Capacity building report and attendance register | 100000 | Report
3.3 | To promote local economic development | Provision of machinery & equipment for food processing | Implementation of SMME Strategy | 3.4.9. Number of cooperatives supported with machinery and equipment for food processing | 1 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | 0 | N/A | 1 | 1000000 | Delivery note, attendance register and report | 1000000 | Report
3.3 | To promote local economic development | Provision of grant funding to local enterprises | Enterprise Grant Funding Policy as a guide | 3.4.10. Percentage of enterprises provided with grant funding support | 100% | 15% | 0 | TOR and public notice | 30% | 0 | Selection report | 80% |  | Progress report | 100% | 1500000 | Close out report | 1500000 | Closeout report
3.3 | To promote local economic development | Provision of capacity building to emerging SMMEs | SMME Strategy implementation plan | 3.4.11. Number of capacity building sessions to be held | 4 | 1 | 50000 | Attendance register and report | 1 | 50000 | Attendance register and report | 1 | 50000 | Attendance register and report | 2 | 50000 | Attendance register and report | 200000 | Attendance register and report
3.3 | To promote local economic development | Appointment of Panel of Service Providers for LED projects | SMME Strategy implementation plan | 3.4.12. Percentage completion of the appointment of a panel of services providers | 100% | 15% | 0 | TOR | 100% | _ | Appointment of Panel | N/A | _ | N/A | N/A | _ | N/A | 30000 | Appointment Letters
3.3 | To promote local economic development | Review the Spatial Development Framework | Spatial Planning and Land Use Management Act 2013 | 3.5.1. Percentage completion of the review of the SDF | 100% | 15% | 0 | Terms of Reference | 50% | 100000 | Inception Report | 75% | 200000 | First Draft Report | 100% | 100000 | Final reviewed SDF | 400000 | Final reviewed SDF
3.3 | To promote local economic development | Subdivision & Rezoning of Municipal sites | Spatial Planning and Land Use Management Act 2013 | 3.5.2. Percentage completion of the subdivision and rezoning of municipal sites | 100% | 25% | 0 | Terms of Reference | 50% | 87499 | Inception Report | 75% | 174998 | First Draft Report | 100% | 262497 | Final subdivision Layout | 524994 | Final subdivision Layout
3.3 | To promote local economic development | Surveying of Municipal sites | Spatial Planning and Land Use Management Act 2013 | 3.5.3. Percentage completion of the surveying of municipal sites | 100% | 25% | 0 | Terms of Reference | 50% | 62500 | Inception Report | 75% | 125000 | First Draft Report | 100% | 187500 | Final survey Diagram | 250000 | Final Survey Diagram
3.5 | To promote Good Governance | Sitting of the Joint Municipal planning tribunal | Spatial Planninga and Land Use Management Act 2013 | 3.5.4. Number of JMPT meetings to be held | 2 | N/A | 0 | N/A | 1 | 30000 | Minutes and attendance register | N/A | 0 | N/A | 1 | 30000 | Minutes and attendance register | 30000 | Attendance register and Minutes
3.3 | To promote local economic development | Conveyancing of Municipal sites | Spatial Planning and Land Use Management Act 2013 | 3.5.5. Percentage completion of the conveyancing of municipal sites | 100% | 25% | 0 | Terms of Reference | 50% | 130752 | Inception Report | 75% | 261504 | Progress report | 100% | 392256 | Closeout Report | 523008 | Closeout report
3.3 | To promote local economic development | Appointment of Panel of Town Planners | Spatial Planning and Land Use Management Act 2014 | 3.5.6. Percentage completion of the appointment of Town Planners | 100% | 15% | 0 | Terms of Reference | 100% | 0 | Appointment letters | _ | _ | _ | _ | _ | _ | 30000 | Appointment letters
3.3 | To promote local economic development | Appointment of panel of Land Surveyors | Spatial Planning and Land Use Management Act 2015 | 3.5.7. Percentage completion of the appointment of Land Surveyors | 100% | 15% | 0 | Terms of Reference | 100% | 0 | Appointment letters | _ | _ | _ | _ | _ | _ | _ | Appointment letters
3.3 | To promote local economic development | Appointment of panel of Conveyancers | Spatial Planning and Land Use Management Act 2017 | 3.5.8. Percentage completion of the appointment of Conveyancers | 100% | 15% | 0 | Terms of Reference | 100% | _ | Appointment letters | _ | _ | _ | _ | _ | _ | _ | Appointment letters
3.3 | To promote local economic development | Development of Housing Sector Plan | Spatial Planning and Land Use Management Act 2016 | 3.5.9. Percentage completion of Housing Sector Plan | 100% | 15% | 0 | Terms of Reference | 50% | 100000 | Inception Report | 75% | 200000 | Draft Housing Sector Plan report | 100% | 200000 | Final Housing Sector Plan Report | 500000 | Final Housing Sector Plan report
3.3 | To promote local economic development | Appointment of panel of environmental management practitioners | Environmental Management plan on Environmental protection | 3.6.1. Percentage completion of the appointment of environmental management practitioners | 100% | 15% | 0 | Terms of Reference | 100% | _ | Appointment letters | _ | _ | _ | _ | _ | _ | R30 000.00 | Appointmentof the panel
3.3 | To promote local economic development | Conduct awareness campaigns on environmental protection | Environmental Management plan on Environmental protection | 3.6.2 Number of environmental protection campaigns to be held | 3 | 1 | 40000 | Attendance register and report | 1 | 40000 | Attendance register and report | 1 | 40000 | Attendance register and report | _ | _ | _ | R120 000.00 | Attendance register and report
3.5 | Promote Good Governance | Sitting of the Environmental Management Forum | Environmental Management plan on Environmental protection | 3.6.3. Number of EMF meetings to be held | 2 | 1 | 15000 | Attendance register and report | _ | _ | _ | 1 | 15000 | Attendance register and report | _ | _ | _ | R30 000.00 | Report and attendance register
3.3 | To promote local economic development | Conduct Environmental Impact Assessment | Environmental Management plan on Environmental protection | 3.6.4. Percentage completion of EIA | 50% | 15% | _ | Terms of Refence | 25% | N/A | Inception Report |  |  | N/A | 50% | 250000 | Progress Report | 250000 | Progress Report
3.3 | To promote local economic development | Development of Environmental Management Policy | Environmental Management plan on Environmental protection | 3.6.5. Percentage completion of the Environmental Management Policy | 50% | 15% | 0 | Terms of Refence | 25% | 100000 | Inception report | N/A | N/A | N/A | 50% |  | 1st Draft policy and public consultation | 200000 | Final Environmental management plan
3.3 | To promote local economic development | Regulate and monitor building construction | Building Control By- Law,Outdoor Advertising By-Law | 3.6.6. Percentage completion of regulation and monitoring of building construction | 100% | 100% | 0 | Building plans register & inspection report | 100% | 0 | Building plans register & inspection report | 100% | 0 | Building plans register & inspection report | 100% | 0 | Building plans register & inspection report | 0 | Building plans register & inspection report
3.3 | To promote local economic development | Procurement of Building Control Information Sign Boards | Building Control By- Law,Outdoor Advertising By-Law | 3.6.7. Number of Building Control Information Sign Boards to be procured | 10 | 0 | 0 | N/A | 0% | 0 | N/A | 10 | 120000 | Delivery note & close out report | 0% | N/A | N/A | 120000 | Delivery note & close out report
3.3 | To promote local economic development | Conduct awareness campaigns on Building Control By-Laws and Outdoor Advertising By-Laws | Building Control By- Law,Outdoor Advertising By-Law | 3.6.8. Number of awareness campaigns on Building Control By-Laws and Outdoor Advertising By-Laws to be held | 2 | 0 | 0 | N/A | 1 | 150000 | Attendence register & report | 0 | 0 | N/A | 1 | 150000 | Attendence register & report | 300000 | Attendence register & report

## Milestones Planning & Developme
ENVIRONMENTAL MANAGEMENT
1. Appointment of Environmental Management Panel
DEPARTMENT |  | Planning and Development | [10 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: |  | Appointment of Environmental Management Panel
WARD: |  | All wards
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | R30 000.00
Project Objectives
§ To promote local economic development
Time Frames
Key Milestones | [9 empty] | Responsible
[10 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter |  |  | 4th Quarter
[14 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
H.Tshumane
§ Terms of references | [9 empty] | H.Tshumane
Advert | [9 empty] | H.Tshumane
§
Projections Per Milestone | Budget Projections | [23 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 |  | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
§ Advert and appointment of service provider |  |  |  | R30 000.00 | [20 empty] | 3rd Quarter 3: Equitable share
§ Identification of species and inception report
§ Layout Map and species removal report
§ Implementation report
2. Development of Environmental Policy
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | H. Tshumane
PROJECT NAME: |  | Development of Environmental Management Policy
WARD: |  | All wards
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2022-06-30
TOTAL APPROVED BUDGET: |  | R 800 000.00
Project Objectives
§ To promote local economic development
Time Frames | bar: 3rd Quarter 1 to 4th Quarter 2
Key Milestones | [8 empty] | Responsible | bar: 3rd Quarter 1 to 4th Quarter 2
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter | 3rd Quarter 3: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
§ Advert and appointment of service provider | [8 empty] | H. Tshumane
§ Inception report | [8 empty] | H.Tshumane
§ Consultation & fact finding, and submission of draft report | [8 empty] | H. Tshumane | bar: 3rd Quarter 1 to 3rd Quarter 3
§ Final submission of report | [8 empty] | H. Tshumane | bar: 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
§ Advert and appointment of service provider | [23 empty] | 3rd Quarter 3: Equitable share
§ Inception report |  |  |  |  | 200000
§ Consultation & fact finding, and submission of draft report
§ Final feasibility study report | [16 empty] | R600 000
3. Environmental awareness campaigns
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: |  | Environmental awareness campaigns
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | R120 000.00
Project Objectives
§ To support and promote Good Governance & Public Participation
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
§ Preparation of concept document and identification of key stakeholders | [8 empty] | H. Tshumane | bar: 3rd Quarter 1
§ Attending the preparatory meetings for the awareness campaign | [8 empty] | H. Tshumane | bar: 3rd Quarter 1
§ Sending out invitations and submission of requisition for the awareness campaign | [8 empty] | H.Tshumane | bar: 3rd Quarter 1
§ Hold the awareness campaign | [8 empty] | H. Tshumane | bar: 3rd Quarter 2
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
§ Hold the awareness campaign | 40000 |  |  |  | 80000 |  |  | 120000 | [5 empty] | Nil | [7 empty] | R120 000.00 |  | 3rd Quarter 3: Equitable share
4. Environmental Management Forum
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: |  | Environmental Management Forum
WARD: |  | 06 and 15
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | R 30,000.00
Project Objectives
§ To support and promote Good Governance & Public Participation
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
§ Date, Venue reservation and sending out of invitations to stakeholders | [8 empty] | H. Tshumane
§ Preparation and submission of Requisition | [8 empty] | H. Tshumane | bar: 3rd Quarter 1 to 3rd Quarter 3
§ Hold Environmental Management Forum meeting | [8 empty] | H. Tshumane
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
§ Date, Venue reservation and sending out of invitations to stakeholders | [23 empty] | 3rd Quarter 3: Equitable share
§ Preparation and submission of Requisition
§ Hold Environmental Management Forum meeting |  |  | 15000 |  |  | nil |  |  |  | 30000 | [8 empty] | nil
30000
Awareness campaign
DEPARTMENT | Planning and Development | [11 empty] | PROJECT MANAGER | [10 empty] | 3rd Quarter 1: A. Mbarane
PROJECT NAME: | Awareness campaign
WARD: | 6 & 15
VOTE NUMBER:
PROJECT STARTING DATE: | 2022 Financial year
PROJECT COMPLETION DATE: | 2023 Financial year
TOTAL ESTIMATED REVENUE: | 100000
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Basic Service Delivery | [8 empty] | Number of invasion signboards installed
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter | [5 empty] | 2nd Quarter |  |  | 3rd Quarter 3: 3rd Quarter | 4th Quarter
[15 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 | 1 | 2 | 3
Presentation | [8 empty] | L.Thaba
Invitation of Stakeholders | [8 empty] | L.Thaba
Minutes | [8 empty] | L.Thaba
Projections Per Milestone |  | Revenue Projections | [24 empty] | 3: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 |  |  | 2 |  |  | 3
Projections Per Milestone | Budget Projections | 2nd Quarter 2: 150000 |  |  | 0 |  |  |  | 0 |  | 150 000 | [9 empty] | Source of Finance
| 1st Quarter | 2nd Quarter 1: 2nd Quarter | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Progress Report |  | 1st Quarter 2: 0 | [18 empty] | Equitable share
Progress Report |  | 2nd Quarter 2: 0 | [14 empty] | Nil
Progress Report | [21 empty] | Nil
Progress Report | [9 empty] | 0
Closeout Report | [16 empty] | 300000
650000
3. Building Plan Application Mnagement
DEPARTMENT | Planning and Development | [11 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: | Delivery and installation of Building plan applications Management.
WARD: | All 32 Wards.
VOTE NUMBER:
PROJECT STARTING DATE: | 2021-07-01
PROJECT COMPLETION DATE: | 2021-12-01
TOTAL ESTIMATED REVENUE: | 200000
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Basic Service Delivery | [8 empty] | Number of invasion signboards installed
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
[15 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 | 1 | 2 | 3
Terms of reference, Order number. | [8 empty] | L.Thaba
Supply and delivery | [8 empty] | L.Thaba
Installation | [8 empty] | L.Thaba
Projections Per Milestone |  | Revenue Projections | [24 empty] | 3: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 |  |  | 2 |  |  | 3
Delivery and installation of Building plan applications Management. |  | 2nd Quarter 2: 100000 |  |  | 0 |  |  |  | 0 |  | 100000 | [6 empty] | R 200 000.00 | [5 empty] | ES
Regulate the construction of buildings.
DEPARTMENT | Planning and Development | [11 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: | Regulate and monitor the construction of buildings.
WARD: | 6 & 15
VOTE NUMBER:
PROJECT STARTING DATE: | 2022 Financial year
PROJECT COMPLETION DATE: | 2023 Financial year
TOTAL ESTIMATED REVENUE: | 100000
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Basic Service Delivery | [8 empty] | Number of invasion signboards installed
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
Building Plans register | [14 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 | 1 | 2 | 3
Inspection report | [8 empty] | L.Thaba
L.Thaba
L.Thaba
Projections Per Milestone |  | Revenue Projections | [24 empty] | 3: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 |  |  | 2 |  |  | 3
Delivery and installation of Building plan applications Management. |  | 2nd Quarter 2: 0 |  |  | 0 |  |  |  | 0 |  | 0 | [6 empty] | 0 | [5 empty] | ES
Deliver and install Building Control information Sign boards
DEPARTMENT | Planning and Development | [11 empty] | PROJECT MANAGER | [10 empty] | A. Mbarane
PROJECT NAME: | Deliver and install Building Control information Sign boards
WARD: | 6 & 15
VOTE NUMBER:
PROJECT STARTING DATE: | 2022 Financial year
PROJECT COMPLETION DATE: | 2023 Financial year
TOTAL ESTIMATED REVENUE: | 100000
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Basic Service Delivery | [8 empty] | Number of invasion signboards installed
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
[15 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 | 1 | 2 | 3
Terms of reference | [8 empty] | L.Thaba
Advert | [8 empty] | L.Thaba
Appointment and Inception report or programme of works | [8 empty] | L.Thaba
Projections Per Milestone |  | Revenue Projections | [24 empty] | 3: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 |  |  | 2 |  |  | 3
Projections Per Milestone | Budget Projections | 2nd Quarter 2: 0 |  |  | 0 |  |  |  | 0 |  | 120000 | [9 empty] | Source of Finance
| 1st Quarter | 2nd Quarter 1: 2nd Quarter | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Progress Report |  | 1st Quarter 2: 0 | [18 empty] | Equitable share
Progress Report |  | 2nd Quarter 2: 0 | [14 empty] | Nil
Progress Report | [21 empty] | Nil
Progress Report | [9 empty] | 0
Closeout Report | [16 empty] | 120000
650000
LOCAL ECONOMIC DEVELOPMENT
Agricultural Development
DEPARTMENT |  | 1st Quarter 1: Planning and Development |  |  |  |  | PROJECT MANAGER | [10 empty] | B Lugongolo
PROJECT NAME: |  | 1st Quarter 1: Supply & Delivery of vegetable production inputs
WARD: |  | 1st Quarter 1: All Wards
VOTE NUMBER:
PROJECT STARTING DATE: |  | 1st Quarter 1: 2022July
PROJECT COMPLETION DATE: |  | 1st Quarter 1: 2023-06-01
TOTAL APPROVED BUDGET: |  | 1st Quarter 1: 1000000
Project Objectives
To promote local economic development
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter |  |  | 4thQuarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Develop specifaction & Tender Advert | [8 empty] | B. Lugongolo
Appointment of service provider | [8 empty] | B. Lugongolo
Delivery of production inputs
Close out report | [8 empty] | B. Lugongolo | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Equitable share
Delivery of production inputs |  |  |  |  | 500000 | 500000
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | B Lugongolo
PROJECT NAME: |  | Supply & Delivery of animal feeds, vaccines & medication
WARD: |  | All Wards
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022July
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET: |  | 450000
Project Objectives
To promote local economic development
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4thQuarter 1: 4thQuarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Develop specifaction & Tender Advert | [8 empty] | B. Lugongolo
Appointment of service provider | [8 empty] | B. Lugongolo
Supply & Deliver of animal feeds. Vaccines and medication
Close out report | [8 empty] | B. Lugongolo | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Equitable share
Delivery of animal feeds, vaccinations & medication |  |  |  |  | 450000 | 450000
1000000
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2021-07-01
PROJECT COMPLETION DATE: |  | 2022-06-30
TOTAL APPROVED BUDGET: |  | 900000
Project Objectives
§ To promote local economic development
Time Frames
Key Milestones | [9 empty] | Responsible
[10 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 2: 3rd Quarter; 4thQuarter 2: 4th Quarter
[14 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Develop BOQ & Tender advertisment | [9 empty] | B. Lugongolo
Appointment of service provider | [9 empty] | B. Lugongolo
Construction | [9 empty] | B. Lugongolo | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [23 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 |  | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Develop BOQ & Tender advertisment |  |  |  | R0.00 | [20 empty] | 3rd Quarter 3: Equitable share
Appointment of service provider
Construction
[9 empty] | 90000 |  | 110000 | 400000
900000
11 Fencing of mealie fields
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | B Lugongolo
PROJECT NAME: |  | Fencing of maize fields
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2021-07-01
PROJECT COMPLETION DATE: |  | 2022-06-30
TOTAL APPROVED BUDGET: |  | R600 000 00
Project Objectives
§ To promote and support sustainable Spatial development
Time Frames | bar: 3rd Quarter 1 to 4th Quarter 2
Key Milestones/ Activities | [8 empty] | Responsible | bar: 3rd Quarter 1 to 4th Quarter 2
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter | 3rd Quarter 3: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
BOQ development & tender advertismnet | [8 empty] | B. Lugongolo
Appointment of service provider | [8 empty] | B.Lugongolo
Fencing | [8 empty] | B.Lugongolo
Closeout report | [8 empty] | B. Lugongolo | bar: 3rd Quarter 2 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Fencing |  |  |  |  | 75000 |  | 425000 | [14 empty] | 500000 |  | 3rd Quarter 3: Equitable share
Construction of livestock trading kraals & Cages
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | B Lugongolo
PROJECT NAME: |  | Construction of livestock trading kraals & Cages
WARD: |  | 15
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET: |  | R600 000 00
Project Objectives
§ To promote and support livestock farmers
Time Frames
Key Milestones/ Activities | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
BOQ development & tender advertismnet | [8 empty] | B. Lugongolo
Appointment of service provider | [8 empty] | B.Lugongolo
Construction of Kraals & Cages | [8 empty] | B.Lugongolo
Closeout report | [8 empty] | B. Lugongolo | bar: 3rd Quarter 2 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
BOQ development & tender advertismnet
Appointment of service provider
Construction of Kraals & Cages |  |  |  |  | 90000 | 510000
Closeout report | [21 empty] | 600000 |  | 3rd Quarter 3: Equitable share
PROJECT NAME: |  | Cannabis & Soy Bean Processing Feasibility Study
WARD: |  | All
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET: |  | 1000000
Project Objectives
Promotion of the cannabis & hemp sector
Key Milestones/ Activities | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Develop terms of reference & Advert | [8 empty] | B. Lugongolo
Appointment of service provider | [8 empty] | B.Lugongolo
Facilitation of cannabis licensing | [8 empty] | B.Lugongolo
Conduct Feasibility Study & Business Plan | [8 empty] | B.Lugongolo
Closeout report | [8 empty] | B. Lugongolo | bar: 3rd Quarter 2 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Develop terms of reference & Advert | [23 empty] | 3rd Quarter 3: Equitable share
Appointment of service provider
|  |  |  | 67500 |  |  | 382500
Inception report | [23 empty] | 3rd Quarter 2: 450000
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
TOR | [8 empty] | B. Njilo
Advert | [8 empty] | B. Njilo
Stakeholder Consultation | [8 empty] | B. Njilo | bar: 3rd Quarter 1 to 3rd Quarter 3
Draft Forestry Strategy | [8 empty] | B. Njilo | bar: 3rd Quarter 1 to 3rd Quarter 3
Final Forestry Strategy | [8 empty] | B. Njilo | bar: 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
TOR | [23 empty] | 3rd Quarter 3: Equitable share
Advert |  |  |  |  | R15 000 00
Stakeholder Consultation | [9 empty] | R150 000 00
Draft Forestry Strategy | [16 empty] | R185 000 00
Final Forestry Strategy | [21 empty] | R350 000 00
13.Support of Fishing Cooperaives
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | B.E Njilo
PROJECT NAME: |  | Support of Fishing Cooperatives
WARD: |  | Ward 23
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET: |  | 500 000 00
Project Objectives
§ To promote local economic development
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
TOR | [8 empty] | B. Njilo
Advert and appointment of service provider | [8 empty] | B. Njilo
Delivery notification | [8 empty] | B. Njilo | bar: 3rd Quarter 1 to 3rd Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
TOR | [23 empty] | 3rd Quarter 3: Equitable share
Advert and appointment of service provider |  |  | 1500000
Delivery notification | [9 empty] | 485 000 00
R500 000 00
VOTE NUMBER:
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: |  | 400000
Project Objectives
§ To sell the destination at international exhibitions
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Terms of Reference | [8 empty] | M. Zweni
Advert and appointment of service provider | [8 empty] | M. Zweni
Provision logistics for the exhibition | [8 empty] | M.Zweni
Finalising logistics and attending exhibition | [8 empty] | M.Zweni | bar: 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 2
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Terms of Reference
Advert and appointment of service provider | [5 empty] | 25 000.00
Procurement of logistics for the exhibition | [10 empty] | 300000
Finalising logistics and attending exhibition | [16 empty] | 75 000.00
Total | [23 empty] | 3rd Quarter 1: 400 000.00
Branding for Tourism Events
DEPARTMENT |  | Planning and Development |  |  | PROJECT MANAGER |  |  |  | M. Zweni
PROJECT NAME: |  | Branding for Tourism Events
WARD: |  | All
VOTE NUMBER:
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: |  | 300 000.00
Project Objectives |  |  | Project Key Performance Indicators
· To market the destination |  |  | Signed delivery note
Time Frames
Key Milestones |  |  | Responsible
|  |  | Official | 1st Quarter |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 | 1 | 2 | 3 |  | 1 | 2 | 3
Develop specifications |  |  | M. Zweni
Advert & appointment |  |  | M. Zweni
Procurement & delivery |  |  | M. Zweni
Projections Per Milestone | Budget Projections | [12 empty] | Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Terms of Reference |  |  |  | Nil
Advert and appointment |  |  | 15000
Delivery of branding material | [8 empty] | 285 000.00
Tourism Annual Event
DEPARTMENT | Local Economic Development | [9 empty] | PROJECT MANAGER
PROJECT NAME: | Tourism Annual Event
WARD: | All Wards
VOTE NUMBER:
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: | 1 900 000.00
Project Objectives | [8 empty] | Project Key Performance Indicators
To attract tourists to the municipal area
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 3: 4th Quarter
[13 empty] | 1 |  | 2 |  | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
Concept Document | [8 empty] | M. Zweni
Tender Advertisment | [8 empty] | Mr Zweni
Appointment of a service provider | [8 empty] | M. Zweni
Inception Report | [8 empty] | M. Zweni
Procurement of logistics for the event | [8 empty] | M. Zweni
Completion of the event | [8 empty] | M. Zweni
Projections Per Milestone |  | Budget Projections | [21 empty] | 4th Quarter 1: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
Concept Document
Terms of Reference
Advert & Appointment of service provider
Inception Report |  | 1st Quarter 3: 285000
Procurement of logistics for the event |  | 2nd Quarter 1: 1615000
Completion of the event | [20 empty] | 1900000 | [5 empty] | Equitable Share
14. FORESTRY DEVELOPMENT AND FISHERIES
DEPARTMENT |  | 1st Quarter 1: Planning and Development |  | PROJECT MANAGER
PROJECT NAME: |  | 1st Quarter 1: COMMUNITY MOBILISATION
WARD: |  | 1st Quarter 1: 05, 10, 12, 31
VOTE NUMBER:
PROJECT STARTING DATE: |  | 1st Quarter 1: 2022-07-01
PROJECT COMPLETION DATE: |  | 1st Quarter 1: 2023-06-01
TOTAL APPROVED BUDGET: |  | 1st Quarter 1: Nil
Project Objectives | bar: 1st Quarter 1 to 3rd Quarter 1
To strenghthen relations with forestry development communities
Time Frames
Key Milestones |  | 3rd Quarter 2: Responsible
|  | 3rd Quarter 2: Official |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Identify relevant stakeholders | [8 empty] | B.Njilo
Develop itenerary for meetings with stakeholders | [8 empty] | B.Njilo
Hold meetings | [8 empty] | B.Njilo | bar: 3rd Quarter 2 to 3rd Quarter 3
Compile reports | [8 empty] | B.Njilo | bar: 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Consultation with stakeholders
Develop itenerary for meetings with stakeholders
Hold meetings
Compile report
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER
PROJECT NAME: |  | FIRE AWARENESS WORKSHOPS
WARD: |  | 05, 13
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-03-30
TOTAL APPROVED BUDGET:
Project Objectives
To discourage veld and forest fires
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Identify stakeholders | [8 empty] | B.Njilo
Identify dates of awarenesse | [8 empty] | B.Njilo | bar: 3rd Quarter 1
Hold awareness | [8 empty] | B.Njilo | bar: 3rd Quarter 2 to 3rd Quarter 3
Compile reports | [8 empty] | B.Njilo | bar: 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Engagement with stakeholders
Hold meetings
Compile reports
DEPARTMENT |  | Planning and Development | [9 empty] | PROJECT MANAGER | [10 empty] | B.E Njilo
PROJECT NAME: |  | Facilitate EIAs for Forestry projects
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET:
Project Objectives
Community development
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
Tender advert | [8 empty] | B.Njilo
Appointment of service provider | [8 empty] | B.Njilo
Engage stakeholders and inception meeting | [8 empty] | B.Njilo | bar: 3rd Quarter 2 to 3rd Quarter 3
EIA conduct and closeout report | [8 empty] | B.Njilo | bar: 3rd Quarter 1; 4th Quarter 1 to 4th Quarter 3
Projections Per Milestone | Budget Projections | [22 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Tender advert
Appointment of service provider
Engage stakeholders and inception meeting
EIA conduct and closeout report
Closeout report
Total
DEPARTMENT |  | Planning and Development |  |  | PROJECT MANAGER |  |  |  | B.Njilo
PROJECT NAME: |  | Supply and delivery of fishing gear
WARD: |  | 23
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-01
TOTAL APPROVED BUDGET: |  | 300 000.00
Project Objectives |  |  | Project Key Performance Indicators
Time Frames
Key Milestones |  |  | Responsible
|  |  | Official | 1st Quarter |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 | 1 | 2 | 3 |  | 1 | 2
Delelop specifications |  |  | B.Njilo
Advert and appointment |  |  | B.Njilo
Procurement & delivery |  |  | B.Njilo
Projections Per Milestone | Budget Projections | [12 empty] | Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Develop specifications
Advert and appointment
Delivery of fishing gear
DEPARTMENT | Local Economic Development | [9 empty] | PROJECT MANAGER
PROJECT NAME: | Supply and delivery of cold storage and store room facility
WARD: | 23
VOTE NUMBER:
PROJECT STARTING DATE:
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET: | 300 000.00
Project Objectives | [8 empty] | Project Key Performance Indicators
Supply and delivery of cold storage and store room facility
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 3: 4th Quarter
[13 empty] | 1 |  | 2 |  | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
Develop specifications | [8 empty] | B.Njilo
Advert | [8 empty] | B.Njilo
Appointment of service provider | [8 empty] | B.Njilo | bar: 3rd Quarter 2 to 4th Quarter 2
Delivery of cold storage and store room facility | [8 empty] | B.Njilo | bar: 4th Quarter 3
Project Handover
Projections Per Milestone |  | Budget Projections | [21 empty] | 4th Quarter 1: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
Develop specifications
Advert
Appointment of service provider
Delivery of cold storage and store room facility
Completion of the event | [20 empty] | 300000 | [5 empty] | Equitable Share
Total | [20 empty] | 300000
Project Objectives |  | 3rd Quarter 2: Project Key Performance Indicators
To promote Basic Service Delivery |  | 3rd Quarter 2: Number of invasion signboards installed
Time Frames
Key Milestones |  | 3rd Quarter 2: Responsible
|  | 3rd Quarter 2: Official |  |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
[15 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 | 1 | 2 | 3
Terms of reference | [8 empty] | B.Njilo
Advert | [8 empty] | B.Njilo
Appointment and Inception report or programme of works | [8 empty] | B.Njilo
Projections Per Milestone |  | Revenue Projections | [24 empty] | 3: Source of Finance
|  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 |  |  | 2 |  |  | 3
Projections Per Milestone | Budget Projections | 2nd Quarter 2: 300000 |  |  | 0 |  |  |  | 0 | [11 empty] | Source of Finance
| 1st Quarter | 2nd Quarter 1: 2nd Quarter | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
Progress Report |  | 1st Quarter 2: 0 | [18 empty] | Equitable share
Progress Report |  | 2nd Quarter 2: 0 | [14 empty] | Nil
Progress Report | [21 empty] | Nil
Progress Report | [9 empty] | 0
Closeout Report | [16 empty] | 120000
650000
SMME DEVELOPMENT
DEPARTMENT | Planning and Development | [9 empty] | PROJECT MANAGER | [6 empty] | NNN Malupali
PROJECT NAME: | Retail Support Project
WARD: | ALL
VOTE NUMBER:
PROJECT STARTING DATE: | 2021-07-01
PROJECT COMPLETION DATE: | 2022-06-01
TOTAL APPROVED BUDGET: | R 2000 000 00
Project Objectives |  | 1st Quarter 2: Project Key Performance Indicators
· To promote Local Economic Development |  | 1st Quarter 2: · Number of retails supported
· Number of enterprises under mentorship
Time Frames
Key Milestones |  | 1st Quarter 2: Responsible
|  | 1st Quarter 2: Official |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter | [6 empty] | 4th Quarter
[9 empty] | 1 | 2 |  | 3 |  |  | 1 |  | 2 | 3 |  | 1 |  |  | 2 |  | 3 |  | 1 | 2 | 3
Develop specifications |  | 1st Quarter 2: NNN Malupali
Procurement process |  | 1st Quarter 2: NNN Malupali
Delivery of equipment |  | 1st Quarter 2: NNN Malupali
Closeout report |  | 1st Quarter 2: NNN Malupali
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [18 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 3: 2nd Quarter | [5 empty] | 3rd Quarter | [5 empty] | 4th Quarter |  |  |  |  | Total
|  | 1 |  | 2 | 3 | 1 |  | 2 | 3 |  |  |  | 1 | 2 |  | 3 |  |  | 1 |  | 2 | 3
Develop specifications | [25 empty] | Equitable Share
Procurement process |  | 2nd Quarter 2: 1000000 |  | 1000000
Delivery of equipment
Total | [23 empty] | 1 500 000 00
16. Hawker Stalls
DEPARTMENT |  | 1st Quarter 1: Planning and Development; 2nd Quarter 1: PROJECT MANAGER |  | NNN Malupali
PROJECT NAME: |  | 1st Quarter 1: Hawker Stalls
WARD: |  | 1st Quarter 1: Ward 6 & 15
VOTE NUMBER:
PROJECT STARTING DATE: |  | 1st Quarter 1: 2021-07-01
PROJECT COMPLETION DATE: |  | 1st Quarter 1: 2022-06-01
TOTAL APPROVED BUDGET: |  | 1st Quarter 1: 4800000
Project Objectives |  | 1st Quarter 2: Project Key Performance Indicators
· To promote Local Economic Development |  | 1st Quarter 2: Number of Hawker Stalls Purchased
Time Frames
Key Milestones |  | 1st Quarter 2: Responsible
|  | 1st Quarter 2: Official; 1st Quarter 3: 1st Quarter; 2nd Quarter 3: 2nd Quarter |  |  |  | 3rd Quarter |  |  |  | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 | 1 | 2 | 3 |  | 1 | 2 | 3
Develop specifications & tender advert |  | 1st Quarter 2: NNN Malupali
Appointment of service provider |  | 1st Quarter 2: NNN Malupali
Projections Per Milestone | Budget Projections | [12 empty] | Source of Finance
| 1st Quarter | 1st Quarter 3: 2nd Quarter; 2nd Quarter 3: 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Develop specifications & tender advert | [13 empty] | Equitable share
Delivery of hawker stalls |  | 2nd Quarter 2: 2400000 |  | 2400000
17. SMME TRAINING
DEPARTMENT | Local Economic Development | [9 empty] | PROJECT MANAGER | [10 empty] | NNN Malupali
PROJECT NAME: | Training of SMMEs
WARD: | All Wards
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-01
TOTAL APPROVED BUDGET: | 500000
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Local Economic Development
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 |  | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
Identification and Consultation of key stakeholders and role players | [8 empty] | NNN Malupali
Training Preparatory meetings with stakeholders | [8 empty] | NNN Malupali
SMME trainings/ workshop | [8 empty] | NNN Malupali
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [19 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 1: 2nd Quarter | 3rd Quarter |  |  |  | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
Identification and Consultation of key stakeholders and role players | [26 empty] | Equitable Share
Training Preparatory meetings with stakeholders |  | 1st Quarter 3: 125000; 3rd Quarter 2: 125000; 3rd Quarter 3: 125000 |  |  |  | 125000
Total | [20 empty] | 500000
Enterprise Grant Funding
DEPARTMENT | Planning and Development | 3rd Quarter 2: PROJECT MANAGER |  |  | NNN Malupali
PROJECT NAME: | Disbursment of Enterprise Grant Funding
WARD: | All Wards
VOTE NUMBER:
PROJECT STARTING DATE: | 2021-07-01
PROJECT COMPLETION DATE: | 2022-09-30
TOTAL APPROVED BUDGET: | 1500000
Project Objectives | [11 empty] | Project Key Performance Indicators
To promote Local Economic Develpment | [11 empty] | % project completion
Time Frames
Key Milestones | [11 empty] | Responsible |  |  | 1st Quarter |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[12 empty] | Official |  |  | 1 | 2 |  | 3 | 1 | 2 | 3 |  |  | 1 | 2 | 3 |  | 1 | 2 | 3
Issue a call for proposal | [11 empty] | N. Malupali
Capturing of application | [11 empty] | N/Malupali
Disbursments of grant funding | [11 empty] | N. Malupali
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [16 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  |  | 3
Issue a call for proposal |  | 1st Quarter 2: 80 000 00
Capturing of application
Disbursement of grant |  | 2nd Quarter 1: 1500000
TOTAL | [21 empty] | 300 000.00 |  |  |  |  | Equitable Share
18 .Pannel of providers
DEPARTMENT | Planning and Development | [14 empty] | PROJECT MANAGER | [7 empty] | NNN Malupali
PROJECT NAME: | Appointment of a pannel of service providers
WARD: | All Wards
VOTE NUMBER:
PROJECT STARTING DATE: | 2021-07-01
PROJECT COMPLETION DATE: | 2022-12-15
TOTAL APPROVED BUDGET: | 30000
Project Objectives |  | 2nd Quarter 1: Project Key Performance Indicators
To promote Local Economic Development |  | 2nd Quarter 1: % project completion
Time Frames
Key Milestones |  | 2nd Quarter 1: Responsible
|  | 2nd Quarter 1: Official; 3rd Quarter 2: 1st Quarter |  |  |  | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
|  | 3rd Quarter 2: 1; 3rd Quarter 3: 2 |  | 3 |  | 1 |  |  | 2 |  | 3 |  | 1 | 2 | 3 |  |  | 1 | 2 |  | 3
Specifications and tender advert |  | 2nd Quarter 1: N. Maluapli
Appointment of providers |  | 2nd Quarter 1: N. Maluapli
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [17 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 2: 2nd Quarter | 3rd Quarter | [6 empty] | 4th Quarter | [6 empty] | Total
|  | 1 | 2 | 3 |  | 1 | 2 | 3 |  |  | 1 |  | 2 |  | 3 |  |  | 1 |  | 2 |  | 3
Specifications and tender advert |  | 1st Quarter 1: 30000 | [17 empty] | Equitable Share
Appointment of providers
Total | [24 empty] | 300 000 00
20. Coordination of LED Cluster
DEPARTMENT | Planning and Development | [15 empty] | PROJECT MANAGER | [8 empty] | NNN Malupali
PROJECT NAME: | LED Cluster
WARD: | All Wards
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2022-06-30
TOTAL APPROVED BUDGET: | 20000
Project Objectives |  | 3rd Quarter 1: Project Key Performance Indicators
To promote local economic development |  | 3rd Quarter 1: Number of cluster meetings held
Time Frames
Key Milestones |  | 3rd Quarter 1: Responsible
|  | 3rd Quarter 1: Official | 1st Quarter | [6 empty] | 2nd Quarter | [6 empty] | 3rd Quarter | [5 empty] | 4th Quarter
[11 empty] | 1 |  | 2 |  | 3 |  |  | 1 |  | 2 |  | 3 |  | 1 |  |  |  | 2 | 3 |  | 1 | 2 | 3
Sitting of LED Cluster |  | 3rd Quarter 1: N. Malupali
Sitting of LED Cluster |  | 3rd Quarter 1: N. Malupali
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [19 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 2: 2nd Quarter |  | 3rd Quarter | [6 empty] | 4th Quarter | [7 empty] | Total
|  | 1 | 2 | 3 | 1 |  |  |  | 2 | 3 |  | 1 |  | 2 |  | 3 |  |  | 1 |  | 2 |  | 3
Sitting of LED Cluster | [15 empty] | 5 000 00 | [13 empty] | Equitable Share
Sitting of LED Cluster |  | 1st Quarter 1: 50000; 2nd Quarter 3: 5 000 00 | [16 empty] | 20000
DEPARTMENT | Planning and Development | [14 empty] | PROJECT MANAGER | [10 empty] | NNN Malupali
PROJECT NAME: | Cooperatives Support
WARD: | All
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 500 000 00
Project Objectives |  | 3rd Quarter 1: Project Key Performance Indicators
· To promote Local Economic Development |  | 3rd Quarter 1: % project completion
Time Frames
Key Milestones |  | 3rd Quarter 1: Responsible
|  | 3rd Quarter 1: Official | 1st Quarter | [7 empty] | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[11 empty] | 1 |  | 2 | 3 |  |  |  |  | 1 | 2 |  | 3 |  |  | 1 |  |  | 2 | 3 |  | 1 | 2 | 3
Skills Audit |  | 3rd Quarter 1: N. Malupali
Facilitate business information sharing sessions |  | 3rd Quarter 1: N. Malupali
Progress Report |  | 3rd Quarter 1: N. Malupali
Completion certificate |  | 3rd Quarter 1: N. Malupali
Projections Per Milestone |  | 1st Quarter 1: Budget Projections | [19 empty] | Source of Finance
|  | 1st Quarter 1: 1st Quarter; 2nd Quarter 2: 2nd Quarter |  | 3rd Quarter | [5 empty] | 4th Quarter | [5 empty] | Total
|  | 1 | 2 | 3 | 1 |  |  |  | 2 | 3 |  | 1 |  |  | 2 |  | 3 | 1 |  |  | 2 |  | 3
BOQ | [23 empty] | 200000 | [5 empty] | Equitable Share
Advert and appointment |  | 1st Quarter 2: 15000
Progress Report |  | 1st Quarter 3: 200000
Completion certificate |  | 2nd Quarter 3: 185000
1. Appointment of a Panel of Service Providers
DEPARTMENT |  | 1st Quarter 1: Planning and Development |  |  | PROJECT MANAGER | [10 empty] | NNN Malupali
PROJECT NAME: |  | 1st Quarter 1: Appointment of a Panel of service providers
WARD: |  | 1st Quarter 1: All wards
VOTE NUMBER:
PROJECT STARTING DATE: |  | 1st Quarter 1: 2022-07-01
PROJECT COMPLETION DATE: |  | 1st Quarter 1: 2023-06-30
TOTAL APPROVED BUDGET: |  | 1st Quarter 1: R30 000.00
Project Objectives | bar: 1st Quarter 1 to 3rd Quarter 2
§ To promote local economic development
Time Frames
Key Milestones |  | 3rd Quarter 3: Responsible
|  | 3rd Quarter 3: Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [5 empty] | 3rd Quarter |  |  | 4th Quarter
[14 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3 | 1 | 2 | 3
NNN Malupali
§ Terms of references | [9 empty] | NNN Malupali
Advert | [9 empty] | NNN Malupali
§
Projections Per Milestone | Budget Projections | [23 empty] | 3rd Quarter 3: Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 |  | 3 | 1 |  | 2 | 3 |  |  | 1 |  |  | 2 |  | 3
§ Advert and appointment of service provider |  |  |  | R30 000.00 | [20 empty] | 3rd Quarter 3: Equitable share
§ Identification of species and inception report
§ Layout Map and species removal report
§ Implementation report

## BTO
IDP NO. | Financial viability | PROJECT | BASELINE | KEY PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGET | [11 empty] | TOTAL BUDGET | MEANS OF VERIFICATION ( POE)
[6 empty] | Quarter |  | MEANS OF VERIFICATION | Quarter 2 |  | MEANS OF VERIFICATION | Quarter 3 |  | MEANS OF VERIFICATION | Quarter |  | MEANS OF VERIFICATION
[6 empty] | 1 | [8 empty] | 4
[6 empty] | tar | bud |  | tar | bud |  | tar | bud |  | tar | bud
Objectives:
4.1. | Finacial Viability and Management | Preparation and submission of annual budget in compliance with budget circular | Approved budget with the required supporting documents by 31 May 2021 | 4.1.1. Number of Prepared and adopted of funded Budget by 31 March 2023 | 1 | N/A | N/A | N/A | N/A | 0 | N/A | 1 | N/A | Council Resolution & A Schedule | N/A | 0 | N/A | 0 | Council Resolution & A Schedule
4.1. | Finacial Viability and Management | Preparation and submission of adjustment budget by 28 February 2023 | Approved adjustment budget with the required supporting documents by 28 February 2022 | 4.1.2. Number of prepared and adopted of adjusted budget | 1 | N/A | N/A | N/A | N/A | 0 | N/A | 1 | N/A | Budget Summary and Council Resolution | N/A | 0 | N/A | 0 | Budget Summary and Council Resolution & B Schedule
4.1. | Finacial Viability and Management | Preparation and submission of section 71 financial monthly reports | The municipality complies with section 71 of the MFMA. 12 Monthly reports submitted | 4.1.3. Number of S71 reports submitted to the Treasury with 10 working days. | 12 | 3 | 0 | Section 71 report signed by CFO and screenshot as proof of submission | 3 | 0 | Section 71 report signed by CFO and screenshot as proof of submission | 3 | 0 | Signed Quality Certificate and proof of submission | 3 | 0 | Signed Quality Certificate and proof of submission |  | Signed Quality Certificate and proof of submission
4.1. | Finacial Viability and Management | Preparation and submission of Section 52 (d) quarterly reports | The municipality complies with section 52 (d) of the MFMA. 4 quarterly reports submitted | 4.1.4. Number of S52 (d) reports submitted to the Mayor and Treasury within 30 days after the end of the quarter | 4 | 1 | 0 | Section 52 (d) report signed by CFO and screenshot as proof of submission | 1 | 0 | Section 52 (d) report signed by CFO and screenshot as proof of submission | 1 | 0 | Signed Quality Certificate and proof of submission | 1 | 0 | Signed Quality Certificate and proof of submission | 0 | Signed Quality Certificate and proof of submission
4.1. | Finacial Viability and Management | Preparation and submission of section 72 (mid-term) report | The municipality complies with section 72 of the MFMA. 1 mid-term report submitted annually | 4.1.5. Number of S72 reports submitted to Mayor and Treasury by 25 January 2023 | 1 | N/A | N/A | N/A | N/A | 0 | N/A | 1 | 0 | Signed Quality Certificate and proof of submission | N/A | 0 | N/A | 0 | Signed Quality Certificate and proof of submission
4.1. | Finacial Viability and Management | Preparations and submission of the AFS for 2021/22 by 31 August 2022 | AFS for 2020/21 were submitted on 30 September 2021 | 4.1.6. Number times the annual financial statements are submitted to Auditor General, National Treasury and Provincial Treasury by 31 August | 1 | N/A | 0 | N/A | N/A | 0 | N/A | N/A | 0 | N/A | 1 | 2500000 | Acknowledgement letter from AG | 2500000 | Acknowledgement letter from AG
4.1. | Finacial Viability and Management | Preparaion of bank reconcilaitions on a Monthly basis by 2022/23. | Bank and grants reconciliations were prepared and submitted monthly for 2020/21 Financial year | 4.1.7. Number of bank reconcilaitions prepared and approved | 12 | 3 | 0 | Monthly bank reconciliations signed by the CFO | 3 | 0 | Monthly bank reconciliations signed by the CFO | 3 | 0 | Approved Bank Reconciliation | 3 | 0 | Approved Bank Reconciliation |  | Approved Bank Reconciliation
4.2. | Finacial Viability and Management | Payment of creditors within 30 days after reciept and confirmation of invoices on a monthly basis by 2022/23 | All invoices that were received and confirmed were paid within 30 days in 2020/21 | 4.2.1. Percentage of invoices paid within 30 days after receipt and confirmation | 100% | 100% | 0 | Invoice register and proof of payment | 100% | 0 | Invoice register and proof of payment | 100% | 0 | Creditors Age Analysis | 100% | 0 | Creditors Age Analysis |  | Creditors Age Analysis
4.2. | Finacial Viability and Management | Preparation and submission of Creditors reconciliations on a Monthly basis by 2022/23 | Creditors reconciliations were prepared and submitted monthly in 2020/21 | 4.2.2. Number of creditors reconciliations prepared | 12 | 3 | 0 | Monthly Creditors reconciliations signed by the CFO | 3 | 0 | Monthly Creditors reconciliations signed by the CFO | 3 | 0 | Approved Creditors Reconciliation | 3 | 0 | Approved Creditors Reconciliation |  | Approved Creditors Reconciliation
4.2. | Finacial Viability and Management | Preparation and submission of Payroll reconciliation on a monthly basis for 2022/23 | Payroll reconciliations were prepared and submitted monthly in 2020/22 | 4.2.3. Number of payroll reconciliation prepared | 12 | 3 | 0 | Monthly Payroll reconciliations signed by the CFO | 3 | 0 | Monthly Payroll reconciliations signed by the CFO | 3 | 0 | Approved Payroll Reconciliation | 3 | 0 | Approved Payroll Reconciliation |  | Approved Payroll Reconciliation
4.2. | Finacial Viability and Management | Preparation and submission of VAT reconciliation on a monthly basis in 2022/23 financial year. | VAT reconciliations were prepared and submitted monthly in 2020/23 | 4.2.4. Number of VAT reconciliations prepared | 12 | 3 | 0 | Monthly VAT reconciliations signed by the CFO | 3 | 0 | Monthly VAT reconciliations signed by the CFO | 3 | 0 | Approved Vat Reconciliation | 3 | 0 | Approved Vat Reconciliation |  | Approved Vat Reconciliation
4.3. | Finacial Viability and Management | Review of Revenue Enhancement Strategy by 30 June 23 | Revenue enhancement strategy has been reviewed in 2021/22 Financial year | 4.3.1. Number of Reports on Review and adoption of Revenue enhancement Strategy | 1 | N/A | 0 | N/A | 1 | 0 | Report on review of revenue enhancement strategy and council resolution | 1 | N/A | Report on review of revenue enhancement strategy and council resolution | N/A | N/A | N/A | 0 | Report on review of revenue enhancement strategy and council resolution
4.3. | Finacial Viability and Management | Preparation of report on the implementation of Revenue Enhancement Strategy | Report on Revenue Enhancement Strategy was prepared in the 2020/21 FY | 4.3.2. Number of Reports on Improved revenue Collection | 12 | 3 | 0 | Monthly reports on the implementation of Revenue Enhancement Strategy signed by the CFO | 3 | 0 | Monthly reports on the implementation of Revenue Enhancement Strategy signed by the CFO | 3 | 0 | Revenue Collection report against billing. | 3 | 0 | Revenue Collection report against billing. |  | Revenue Collection report against billing.
4.3. | Finacial Viability and Management | Sitting of Municipal Revenue Committee meetings | Revenue committee meetings were held on a quarterly basis in 2020/21 FY | 4.3.3. Number of revenue committee meetings to be held | 4 | 1 | 25000 | Attendance register, munites and report | 1 | 25000 | Attendance register, munites and report | 1 | 25000 | Attendance register, munites and report | 1 | 25000 | Attendance register, munites and report | 100000 | Attendance register, munites and report
4.3. | Finacial Viability and Management | Review of Free Basic Services Strategy by 30 June 2023 | Free Basic Services Strategy was reviewed in 2020/21 | 4.3.4. Number of Review for Free Basic Service Policy | 1 | N/A | 0 | N/A | 1 | 200000 | Report on review on Free Basic Services Strategy and council resolution | N/A | 0 | N/A | 1 | 0 | Council Resolution | 200000 | Council Resolution
4.3. | Finacial Viability and Management | Provision of Free Basic Services to indigent households | Report on the implementation of Free basic Services Strategy was prepared in 2020/21 | 4.3.5. Percentage expenditure on free basic services allocation | 100% | 25% | 1307502 | Monthly reports on the implementation of Free Basic Services signed by the CFO | 25% | 1307502 | Monthly reports on the implementation of Free Basic Services signed by the CFO | 25% | 1307502 | Monthly reports on the implementation of Free Basic Services | 25% | 1307502 | Monthly reports on the implementation of Free Basic Services | 5230008 | Monthly reports on the implementation of Free Basic Services
4.4. | Finacial Viability and Management | Procurement of Fleet Management System in 2022/23 financial year. | Fleet Management Policy in place and No Fleet Management System | 4.4.1. Number of Fleet Management system procured | 1 | 1 | 0 | Appointment letter | 1 | 0 | Proof of System Installation | 1 | 0 | Installation certificate | N/A | 0 | N/A |  | Installation certificate
4.4. | Finacial Viability and Management | Preparation of report on the implementation of the Fleet Management system | Fleet Management Policy in place and No Fleet Management System | 4.4.2. Number of reports on implementation of the Fleet Management system. | 6 | N/A | 750000 | N/A | N/A | 750000 | N/A | 3 | 750000 | monthly reports on implementation of fleet management system | 3 | 750000 | monthly reports on implementation of fleet management system | 3000000 | monthly reports on implementation of fleet management system
4.5. | Finacial Viability and Management | Updating and submission of GRAP compliant Fixed Asset Register | Fixed Asset Register is updated monthly and submitted with the AFS to AG | 4.5.1. Number of Monthly reconciliation of Fixed Asset and TB/GL | 6 | N/A | 0 | N/A | N/A | 0 | N/A | 3 | 0 | Monthly Reconciliation of FAR with TB/GL | 3 | 2000000 | Monthly Reconciliation of FAR with TB/GL | 2000000 | Monthly Reconciliation of FAR with TB/GL
4.5. | Finacial Viability and Management | Preparation of monthly reports on insurance of all municipal assets | All Municipal assets were insured by 2020/21 financial year. Assets are insured as they are procured | 4.5.2. Number of Confirmation of Insurance for Municipal Assets | 12 | 3 | 0 | Insurance report signed by CFO and confirmation of insurance | 3 | 2500000 | Insurance report signed by CFO and confirmation of insurance | 3 | 0 | Confirmation of insurance for all Municipal Assets | 3 | 0 | Confirmation of insurance for all Municipal Assets | 2500000 | Confirmation of insurance for all Municipal Assets
4.6. | Finacial Viability and Management | Implementation of activities in the procuremnet plan | Procurement plan was implemented on a monthly basis in 2020/21 financial year | 4.6.2. Percentage implementation of activities in the procurement plan | 100% | 100% | 0 | quarterly progress report on the implementation of the PP and PP | 100% | 0 | quarterly progress report on the implementation of the PP and PP | 100% | 0 | quarterly progress report on the implementation of the PP and PP | 100% | 0 | quarterly progress report on the implementation of the PP and PP | 0 | quarterly progress report on the implementation of the PP and PP
4.6. | Finacial Viability and Management | Preparation and submission of a report on the assessment of contractor performance | Contractor performance assessment report was prepared in 2020/21 financial year | 4.6.3. Number of reports on the assessment of contractor performance prepared | 12 | 3 | 0 | Monthly report on the assessment of contractor performance signed by CFO | 3 | 0 | Monthly report on the assessment of contractor performance signed by CFO | 3 | 0 | Monthly report on the assessment of contractor performance | 3 | 0 | Monthly report on the assessment of contractor performance | 0 | Monthly report on the assessment of contractor performance
4.6. | Finacial Viability and Management | Preparation and submission of report on updating of contract management register | Contract register is in place and has beed updated for 2020/21 financial year | 4.6.4. Number of reports on updating of contract management register to be prepared | 12 | 3 | 0 | Monthly report on contract management signed by the CFO | 3 | 0 | Monthly report on contract management signed by the CFO | 3 | 0 | Monthly report on contract management | 3 | 0 | Monthly report on contract management |  | Monthly report on contract management
4.7. | Good governance and Public Participation | Implementation of the Audit Action Plan to improve audit outcome | The Municipality attained Qualified audit opinion | 4.7.1. Percentage implementation of the Audit Action Plan. Number of Improved Audit Status | 100% | 25% | 0 | Progress report on the implementation of the Audit Action Plan | 25% | 0 | Progress report on the implementation of the Audit Action Plan | 25% | 0 | Monthly Progress report on adressing Audit Finding | 25% | 0 | Monthly Progress report on adressing Audit Finding |  | Monthly Progress report on adressing Audit Finding
Note on K24: Sinazo S. Gono: these figures should not be here as there is no target on the respective quarters

## Milestones BTO
Objective: To promote Finacial Viability and Management
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation of Municipal Budget
INSTITUTION: |  |  | Ingquza Hill Local Municipality
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | 0
SOURCE OF FUNDING |  |  | Nil
Project Objectives |  |  | Project Key Performance Indicators
To promote Finacial Viability and Management |  |  | Number of adopted annual budgets prepared and submitted in compliance with budget circular
Time Frames
Key Milestones |  |  | Responsible
|  |  | Official | [8 empty] | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of annual budget in compliance with budget circular |  |  | Mr. Ndabeni | [22 empty] | 1
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [23 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 |  |  | 3
[16 empty] | 1 XCouncil resolution |  |  | Nil | [5 empty] | Nil
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation of Budget adjustment
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
To promote Finacial Viability and Management | [8 empty] | Number of adopted adjustment budgets by 28 February 2023
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of adjustment budget by 28 February 2023 | [8 empty] | Mr. Ndabeni
O. Mbele
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Equitable share
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [12 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation and submission of section 71 financial monthly reports
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparation and submission of section 71 financial monthly reports | [8 empty] | Number of S71 reports submitted to the Mayor and Treasury with 10 working days
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official | [5 empty] | 1st Quarter |  |  |  | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[15 empty] | 1 | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3
Preparation and submission of section 71 financial monthly reports | [8 empty] | Mr. Ndabeni
O.Mbele
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [27 empty] | Source of Finance
| 1st Quarter |  |  |  | 2rd Quarter |  |  | 3th Quarter |  |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
Preparation and submission of section 71 financial monthly reports | [28 empty] | Equitable Share
Equitable Share
DEPARTMENT | Budget and Treasury Office | [11 empty] | PROJECT MANAGER | [12 empty] | Mr. Mhlifili
PROJECT NAME: | Preparation and submission of Section 52 (d) quarterly reports
INSTITUTION: | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING | Equitable share
Project Objectives | [10 empty] | Project Key Performance Indicators
To comply with the MFMA section 52 d | [10 empty] | Number of S52 (d) reports submitted to the Mayor and Treasury within 30 days after the end of the quarter
Time Frames
Key Milestones | [10 empty] | Responsible
[11 empty] | Official |  |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter | [7 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[16 empty] | 1 |  |  | 2 | 3 | 1 |  | 2 |  | 3 |  |  | 1 |  | 2 | 3 |  |  | 1 |  | 2 | 3
Preparation and submission of Section 52 (d) quarterly reports | [10 empty] | Mr. Ndabeni
O.Mbele
Projections Per Milestone |  | Budget Projections in multiples of R1000 (xR1000) | [29 empty] | Source of Finance
|  | 1st Quarter |  |  |  | 2nd Quarter |  | 3rd Quarter | [6 empty] | 4th Quarter | [8 empty] | Total
|  | 1 | 2 | 3 | 1 |  | 2 |  | 3 | 1 |  | 2 |  | 3 |  |  | 1 | 2 |  |  |  | 3
Preparation and submission of Section 52 (d) quarterly reports | [34 empty] | Equitable share
Equitable share
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation and submission of section 72 (mid-term) report
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET: |  |  | Nil
SOURCE OF FUNDING |  |  | Nil
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparation and submission of section 72 (mid-term) report | [8 empty] | Number of S72 reports submitted to Mayor and Treasury by 25 January 2023
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of section 72 (mid-term) report | [8 empty] | Mr. Ndabeni
O. Mbele
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Nil | [26 empty] | Nil
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparations and submission of the AFS for 2021/22 by 31 August 2022
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparations and submission of the AFS for 2021/22 by 31 August 2022 | [8 empty] | Number times the annual financial statements are submitted to Auditor General, National Treasury and Provincial Treasury by 31 August
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparations and submission of the AFS for 2021/22 by 31 August 2022 | [8 empty] | Mr. Ndabeni
O. Mbele
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Preparations and submission of the AFS for 2021/22 by 31 August 2022 | [26 empty] | Equitable shares
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparaion of bank reconcilaitions on a Monthly basis by 2022/23.
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparaion of bank reconcilaitions on a Monthly basis by 2022/23. | [8 empty] | Number of bank reconcilaitions prepared and approved by the CFO
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparaion of bank reconcilaitions on a Monthly basis by 2022/23. | [8 empty] | Mr. Ndabeni |  |  |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report |  | 1 Report
N. Hlonti
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Preparaion of bank reconcilaitions on a Monthly basis by 2022/23. | [26 empty] | Equitable shares
Equitable shares.
DEPARTMENT |  |  | Budget and Treasury Office | [6 empty] | PROJECT MANAGER | [10 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Payment of creditors within 30 days after reciept and confirmation of invoices on a monthly basis by 2022/23
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Payment of creditors within 30 days after reciept and confirmation of invoices on a monthly basis by 2022/23 | [8 empty] | Percentage of invoices paid within 30 days after receipt and confirmation
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Payment of creditors within 30 days after reciept and confirmation of invoices on a monthly basis by 2022/23 | [8 empty] | S. Mzana
N. Mgilane
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 | 1 |  | 2 |  |  | 3
Payment of creditors within 30 days after reciept and confirmation of invoices on a monthly basis by 2022/23 | [26 empty] | Equitable shares
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation and submission of Creditors reconciliations on a Monthly basis by 2022/23
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparation and submission of Creditors reconciliations on a Monthly basis by 2022/23 | [8 empty] | Number of creditors reconciliations prepared and approved by the CFO
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
nd submission of Creditors reconciliations on a Monthly basis by 2022/23 | [8 empty] | S. Mzana
N. Mgilane
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Preparation and submission of Creditors reconciliations on a Monthly basis by 2022/23 | [26 empty] | Equitable shares
DEPARTMENT | Budget and Treasury Office |  | PROJECT MANAGER | [5 empty] | Mr. Mhlifili
PROJECT NAME: | Preparation and submission of Payroll reconciliation on a monthly basis for 2022/23
INSTITUTION: | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING | Equitable share
Project Objectives |  | Project Key Performance Indicators
Preparation and submission of Payroll reconciliation on a monthly basis for 2022/23 |  | Number of payroll reconciliation prepared and approved by the CFO
Time Frames
Key Milestones |  | Responsible
|  | Official |  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter | [6 empty] | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 |  |  | 1 |  | 2 |  | 3 |  | 1 |  | 2 |  | 3
Preparation and submission of Payroll reconciliation on a monthly basis for 2022/23 |  | S. Mzana
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [12 empty] | Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
| 0 | 0 | 0 | 0 | [9 empty] | General Revenue
DEPARTMENT | Budget and Treasury Office |  | PROJECT MANAGER | [5 empty] | Mr. Mhlifili
PROJECT NAME: | Preparation and submission of VAT reconciliation on a monthly basis in 2022/23 financial year.
INSTITUTION: | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING | General Revenue
Project Objectives |  | Project Key Performance Indicators
Preparation and submission of VAT reconciliation on a monthly basis in 2022/23 financial year. |  | Number of VAT reconciliations prepared and approved by the CFO
Time Frames
Key Milestones |  | Responsible
|  | Official |  | 1st Quarter |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter | [6 empty] | 4th Quarter
|  |  |  | 1 | 2 | 3 | 1 | 2 |  | 3 |  |  | 1 |  | 2 |  | 3 |  | 1 |  | 2 |  | 3
Preparation and submission of VAT reconciliation on a monthly basis in 2022/23 financial year. |  | Mr. Ndabeni
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [12 empty] | Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter |  |  | Total
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Preparation and submission of VAT reconciliation on a monthly basis in 2022/23 financial year. | [13 empty] | General Revenue
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Review of Revenue Enhancement Strategy by 30 June 23
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2001-07-22
PROJECT COMPLETION DATE: |  |  | 1930-06-22
TOTAL APPROVED BUDGET: |  |  | R0.00
SOURCE OF FUNDING
Project Objectives | [8 empty] | Project Key Performance Indicators
Review of Revenue Enhancement Strategy by 30 June 23 | [8 empty] | Review of Revenue Enhancement Strategy annually in 2022/23 fiancial year.
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Review of Revenue Enhancement Strategy by 30 June 23 | [8 empty] | Mr. Ndabeni
Review of Revenue Enhancement Strategy by 30 June 23 | [8 empty] | N. Nodlabi
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Preparation of report on the implementation of Revenue Enhancement Strategy
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 01-07-2021
PROJECT COMPLETION DATE: |  |  | 30-06-2023
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparation of report on the implementation of Revenue Enhancement Strategy | [8 empty] | Number of reports on the implementation of the Revenue Enhancement Strategy
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation of report on the implementation of Revenue Enhancement Strategy | [8 empty] | Mr. Ndabeni
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Equitable share
DEPARTMENT |  |  | Budget and Treasury Office | [8 empty] | PROJECT MANAGER | [10 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Sitting of Municipal Revenue Committee meetings
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-01-07
PROJECT COMPLETION DATE: |  |  | 2019-06-30
TOTAL APPROVED BUDGET: |  |  | R0.00
SOURCE OF FUNDING
Project Objectives | [9 empty] | Project Key Performance Indicators
Sitting of Municipal Revenue Committee meetings | [9 empty] | Number of revenue committee meetings to be held
Time Frames
Key Milestones | [9 empty] | Responsible
[10 empty] | Official |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 |  |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 |  | 2 | 3 |  |  | 1 | 2 | 3
Sitting of Municipal Revenue Committee meetings | [9 empty] | Mr. Ndabeni
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [28 empty] | Source of Finance
| 1st Quarter |  |  |  | 3rd Quarter |  |  |  | 4th Quarter | [6 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  | 1 |  | 2 |  |  |  | 3
DEPARTMENT |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  | Review of Free Basic Services Strategy by 30 June 2023
INSTITUTION: |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  | 2022-06-21
PROJECT COMPLETION DATE: |  |  | 2023-07-22
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Review of Free Basic Services Strategy by 30 June 2023 | [8 empty] | Review of Free Basic Services Strategy
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Review of Free Basic Services Strategy by 30 June 2023 | [8 empty] | Mr. Ndabeni | [8 empty] | 684850 | [5 empty] | 684850 |  |  |  | 684850
Review of Free Basic Services Strategy by 30 June 2023 | [8 empty] | N. Nodlabi | [8 empty] | 684850 | [5 empty] | 684850 |  |  |  | 684850
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
DEPARTMENT |  | Budget and Treasury Office | [9 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  | Provision of Free Basic Services to indigent households
WARD: |  | All
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2021-01-06
PROJECT COMPLETION DATE: |  | 2022-07-22
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING: |  | Equitable Share
| Project Objectives | [7 empty] | Project Key Performance Indicators
Provision of Free Basic Services to indigent households | Percentage expenditure on free basic services allocation
Key Milestones | [13 empty] | Time Frames
Responsible
[9 empty] | Official |  |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 |  | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
Provision of Free Basic Services to indigent households | [8 empty] | Mr. Ndabeni
N. Nodlabi
Projections Per Milestone | Budget Projections | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  |  | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  | 1 |  |  | 2 |  | 3
Equitable share
DEPARTMENT |  | Budget and Treasury Office | [9 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  | Development of Fleet Management Plan in 2022/23 financial year.
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2001-06-21
PROJECT COMPLETION DATE: |  | 2001-07-22
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING: |  | Equitable Share
| Project Objectives | [7 empty] | Project Key Performance Indicators
| Development of Fleet Management Plan in 2022/23 financial year. | [7 empty] | Number of Fleet Management Plans to be developed
Time Frames
| Key Milestones | [7 empty] | Responsible
[9 empty] | Official |  |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 |  | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
| Development of Fleet Management Plan in 2022/23 financial year. | [7 empty] | S. Mzana
F.J. Mafukula
Projections Per Milestone | Budget Projections | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  |  | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  | 1 |  |  | 2 |  | 3
|  |  |  | 493500 |  | 493500 |  |  |  | 493500 | [5 empty] | 493500 |  |  |  |  | 1974000 | [5 empty] | Equitable share
DEPARTMENT |  | Budget and Treasury Office | [9 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  | Preparation of report on the implementation of the Fleet Management Plan
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-06-21
PROJECT COMPLETION DATE: |  | 2023-07-22
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING: |  | Equitable Share
| Project Objectives | [7 empty] | Project Key Performance Indicators
| Preparation of report on the implementation of the Fleet Management Plan | [7 empty] | Number of reports on implementation of the Fleet Management Plan
Time Frames
| Key Milestones | [7 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter | [5 empty] | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 |  |  | 3 | 1 |  | 2 |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
| Preparation of report on the implementation of the Fleet Management Plan | [7 empty] | S. Mzana
F.J. Mafukula
Projections Per Milestone | Budget Projections | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter | [5 empty] | 4th Quarter | [5 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 |  | 2 | 3
[20 empty] | 525000 | [6 empty] | Equitable share
DEPARTMENT |  | Budget and Treasury Office | [9 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  | Updating and submission of GRAP compliant Fixed Asset Register
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  | 2022-06-21
PROJECT COMPLETION DATE: |  | 2023-07-22
TOTAL APPROVED BUDGET:
| Project Objectives | [7 empty] | Project Key Performance Indicators
| Updating and submission of GRAP compliant Fixed Asset Register | [7 empty] | Number of GRAP compliant Fixed Asset Register prepared and submitted to National Treasury and Auditor General by 31 August 2022
Time Frames
| Key Milestones | [7 empty] | Responsible
[9 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 | 2 |  | 3 |  | 1 | 2 |  | 3 |  | 1 | 2 |  | 3 | 1 | 2 | 3
| Updating and submission of GRAP compliant Fixed Asset Register | [7 empty] | S. Mzana
O. Nomdlembu
Projections Per Milestone | Budget Projections | [23 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 |  | 2 | 3 | 1 | 2 | 3 | 1 |  | 2 | 3 | 1 |  |  | 2 |  | 3
[20 empty] | 1050000 |  |  |  |  | Equitable share
DEPARTMENT |  |  |  | Budget and Treasury Office | [6 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Preparation of monthly reports on insurance of all municipal assets
INSTITUTION: |  |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2001-06-21
PROJECT COMPLETION DATE: |  |  |  | 2001-07-22
TOTAL APPROVED BUDGET: |  |  |  | 1050000
SOURCE OF FUNDING |  |  |  | Equitable Share
Project Objectives | [8 empty] | Project Key Performance Indicators
Preparation of monthly reports on insurance of all municipal assets | [8 empty] | Number of reports prepared on the insurance of municipal assets
Time Frames
Key Milestones | [8 empty] | Responsible
[9 empty] | Official |  |  |  |  | 1st Quarter |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 |  | 3 | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation of monthly reports on insurance of all municipal assets | [8 empty] | S. Mzana
O Nomdlembu
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 | 2 |  |  | 3
Equitable Share
DEPARTMENT |  |  |  | Budget and Treasury Office | [6 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Preparation and submission of oversight report on SCM processes
INSTITUTION: |  |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2001-06-21
PROJECT COMPLETION DATE: |  |  |  | 2001-07-22
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  |  | Equitable Share
Project Objectives |  |  |  |  | 3rd Quarter 2: Project Key Performance Indicators
Preparation and submission of oversight report on SCM processes |  |  |  |  | 3rd Quarter 2: Number of oversight reports submitted to the Mayor and Treasury
Time Frames
Key Milestones |  |  |  |  | 3rd Quarter 2: Responsible
[5 empty] | 3rd Quarter 2: Official |  |  |  | 1st Quarter |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 |  | 3 | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of oversight report on SCM processes |  |  |  |  | 3rd Quarter 2: P. Dlomo
S. Ntanjana
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 | 2 |  |  | 3
Equitable Share
DEPARTMENT |  |  |  | Budget and Treasury Office | [6 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Preparation and submission of the progress report on the implementation of procuremnet plan
INSTITUTION: |  |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2001-06-21
PROJECT COMPLETION DATE:
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  |  | Equitable Share
Project Objectives |  |  |  |  | 3rd Quarter 2: Project Key Performance Indicators
Preparation and submission of the progress report on the implementation of procuremnet plan |  |  |  |  | 3rd Quarter 2: Number of reports prepared and approved by the CFO on implementation of procurement plan
Time Frames
Key Milestones |  |  |  |  | 3rd Quarter 2: Responsible
[5 empty] | 3rd Quarter 2: Official |  |  |  | 1st Quarter |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of the progress report on the implementation of procuremnet plan |  |  |  |  | 3rd Quarter 2: P. Dlomo
S. Ntanjana
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 | 2 |  |  |  | 3
Equitable Share
DEPARTMENT |  |  |  | Budget and Treasury Office | [6 empty] | PROJECT MANAGER | [9 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Preparation and submission of a report on the assessment of contractor performance
INSTITUTION: |  |  |  | INGQUZA HILL LOCAL MUNICIPALITY
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2022-01-07
PROJECT COMPLETION DATE: |  |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING |  |  |  | Equitable Share
Project Objectives |  |  |  |  | 3rd Quarter 2: Project Key Performance Indicators
Preparation and submission of a report on the assessment of contractor performance |  |  |  |  | 3rd Quarter 2: Number of reports on the assessment of contractor performance prepared
Time Frames
Key Milestones |  |  |  |  | 3rd Quarter 2: Responsible
[5 empty] | 3rd Quarter 2: Official |  |  |  | 1st Quarter |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter |  |  |  |  | 4th Quarter
[14 empty] | 1 | 2 | 3 |  | 1 | 2 |  |  | 3 |  | 1 | 2 | 3 |  | 1 | 2 | 3
Preparation and submission of a report on the assessment of contractor performance |  |  |  |  | 3rd Quarter 2: P. Dlomo
Projections Per Milestone | Budget Projections in multiples of R1000 (xR1000) | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 | 2 |  |  |  | 3
Equitable Share
DEPARTMENT |  |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [10 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Preparation and submission of report on updating of contract management register
WARD: |  |  |  | All
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2022-01-06
PROJECT COMPLETION DATE: |  |  |  | 30-06-2023
TOTAL APPROVED BUDGET:
| Project Objectives |  |  |  | 3rd Quarter 2: Project Key Performance Indicators
Preparation and submission of report on updating of contract management register |  |  |  |  | 3rd Quarter 2: Number of reports on updating of contract management register to be prepared
Time Frames
| Key Milestones |  |  |  | 3rd Quarter 2: Responsible
[5 empty] | 3rd Quarter 2: Official |  |  | 1st Quarter |  |  |  | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  |  | 1 | 2 |  | 3 |  | 1 | 2 | 3
| Preparation and submission of report on updating of contract management register |  |  |  | 3rd Quarter 2: P. Dlomo
S. Ntanjana
Projections Per Milestone | Budget Projections | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 | 2 |  |  |  | 3
DEPARTMENT |  |  |  | Budget and Treasury Office | [7 empty] | PROJECT MANAGER | [10 empty] | Mr. Mhlifili
PROJECT NAME: |  |  |  | Implementation of the Audit Action Plan to improve audit outcome
WARD:
VOTE NUMBER:
PROJECT STARTING DATE: |  |  |  | 2022-07-01
PROJECT COMPLETION DATE: |  |  |  | 2023-06-30
TOTAL APPROVED BUDGET:
| Project Objectives |  |  |  | 3rd Quarter 2: Project Key Performance Indicators
| Implementation of the Audit Action Plan to improve audit outcome |  |  |  | 3rd Quarter 2: Percentage implementation of the Audit Action Plan
Time Frames
| Key Milestones |  |  |  | 3rd Quarter 2: Responsible
[5 empty] | 3rd Quarter 2: Official |  |  | 1st Quarter |  |  |  | 2nd Quarter | [6 empty] | 3rd Quarter |  |  |  |  | 4th Quarter
[13 empty] | 1 |  | 2 | 3 |  | 1 |  | 2 | 3 |  |  |  | 1 | 2 |  | 3 |  | 1 | 2 | 3
| Implementation of the Audit Action Plan to improve audit outcome |  |  |  | 3rd Quarter 2: Mr. Ndabeni
| Implementation of the Audit Action Plan to improve audit outcome |  |  |  | 3rd Quarter 2: S. Mzana
Projections Per Milestone | Budget Projections | [25 empty] | Source of Finance
| 1st Quarter |  |  |  | 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 1 | 2 | 3 |  | 1 | 2 | 3 | 1 |  | 2 | 3 |  |  | 1 | 2 |  |  |  | 3
Equitable share

## MM's office
IDP NO. | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY PERFORMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGET | [11 empty] | TOTAL BUDGET | MEANS OF VERIFICATION
[6 empty] | Quarter |  | Means of verification | Quarter 2 |  | Means of verification | Quarter 3 |  | Means of verification | Quarter |  | Means of verification
[6 empty] | 1 | [8 empty] | 4
[6 empty] | tar | bud |  | tar | bud |  | tar | bud |  | tar | bud
Ojective: To promote good governance and public participation
5.1 | Good Governance and Public Participation | Quarterly performance monitoring | PMS Policy adopted by council and reports submitted quarterly | 5.1.1. Number of quarterlry reports to be reviewed by management | 4 | 1 |  | Attendance register and minutes | 1 |  | Attendance register and minutes | 1 |  | Attendance register and minutes | 1 |  | Attendance register and minutes |  | Attendance register and minutes
5.1 | Good Governance and Public Participation | Monthly performance monitoring | PMS policy available and reporting timelines set | 5.1.2. Number of monthly reports to be reviewed by management | 12 | 3 |  | Attendance register and minutes | 3 |  | Attendance register and minutes | 3 |  | Attendance register and minutes | 3 |  | Attendance register and minutes |  | Attendance register and minutes
5.1 | Good Governance and Public Participation | Presentation of reports to council | PMS policy available and reporting timelines set | 5.1.3. Number of reports to be tabled to council | 7 | 1 |  | Attendance register and minutes | 2 |  | Attendance register and minutes | 3 |  | Attendance register and minutes | 1 |  | Attendance register and minutes |  | Attendance register and minutes
5.2 | Good Governance and Public Participation | IDP Planning and revision - Sitting of IDP meetings | IDP Process Plan has been adopted by council | 5.2.1. Number of IDP meetings to be held | 9 | 4 | 112498 | Attendance Register and Minutes | 2 | 112498 | Attendance Register and Minutes | 2 | R 112 498 | Attendance Register and Minutes | 1 | 112498 | Attendance Register and Minutes | R 449992 | Attendance Register and Minutes
5.2 | Good Governance and Public Participation | IDP Planning and revision - Collection of ward information | IDP Process Plan has been adopted by council | 5.2.2. Number of Ward Needs Analysis to be conducted | 1 | 1 | 0 | N/A | 0 | 0 | N/A | 1 | 0 | Report and attendance register | 0 | 0 | N/A |  | Ward Based Needs Analysis
5.2 | Good Governance and Public Participation | IDP Planning and revision- Sitting of departmental strategic planning sessions | IDP Process Plan has been adopted by council | 5.2.3. Number of Departmental Strategic Planning Sessions to be held | 6 | 0 | 0 | Report and attendance register | 6 | R 150 000 | Consolidated Strategic Report and Attendance Register | 6 | 0 | Consolidated Strategic Report and Attendance Register | 0 | 0 | N/A | R 150000 | Consolidated Strategic Report and Attendance Register
5.2 | Good Governance and Public Participation | IDP Planning and revision- Sitting of institutional strategic planning session | IDP Process Plan has been adopted by council | 5.2.4. Number of Institutional Strategic Planning Sessions to be held | 1 strat plan and 1 Exco Lekgotla | 0 | 0 | N/A | 0 | 0 | N/A | 1 Strat Plan and 1 Exco Lekgotla | R 1 927 800 | Attendance Register and Report | 0 | 0 | N/A | R 1927800 | Attendance Register and Report
5.3 | Good governance and public participation | Implementation of the Internal Audit Plan | 2022-23 Internal Audit Plan approved by MM | 5.3.1.1. % implementation of Internal Audit Plan measured per quarter. | 100% | 20% | 0 | Monthly Internal Audit Unit Performance Report | 40% | 0 | Monthly Internal Audit Unit Performance Report | 60% | 0 | Monthly Internal Audit Unit Performance Report | 100% | 0 | Monthly Internal Audit Unit Performance Report | 0 | Monthly Internal Audit Unit Performance Report
5.3 | Good governance and public participation | Preparation of 2022/23 Internal Audit Plan | 2022/2023 Annual Risk Assessment Report endorsed by Management on 17/05/2022 | 5.3.1.2. Number ot Internal Audit Plans prepared and approved by the MM | 1 | 0 | 0 | Signed Internal Audit Plan | 0 | 0 | Signed Internal Audit Plan | 0 | 0 | Signed Internal Audit Plan | 1 | 0 | Signed Internal Audit Plan | 0 | Signed Internal Audit Plan
5.3 | Good governance and public participation | Sitting of Audit Committee meetings | Audit Committee Annual Meeting Diary endorsed by the Audit Committee by 31 August 2022. | 5.3.1.3. Number of audit committee meetings to be held | 4 | 1 | R125 000.00 | Minutes of meeting | 1 | R125 000,00 | Minutes of meeting | 1 | R125 000,00 | Minutes of meeting | 1 | R125 000,00 | Minutes of meeting | R500,000,00 | Minutes of meeting
5.3 | Good governance and public participation | Re-Establishment of Municipal Disciplinary Board | Council Resolution on Re-Establishment of MDB obtained on 28 April 2022 | 5.3.1.4 Number of Municipal Disciplinary Board established | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | R150,000.00 | Appointment letters and council resolution on MDB successful appointees | R150,000.00 | Appointment letters and council resolution on MDB successful appointees
5.3 | Good governance and public participation | Sitting of Monthly Risk Monitoring Meetings by management. | 2022-2023 Risk Registers Endorsed by management on 17/05/2022 | 5.3.2.1. Number of Risk Monitoring Meetings to be held monthly | 12 | 3 | 0 | Attendance registers and minutes of monthly management meeting | 3 | 0 | Attendance registers and minutes of monthly management meeting | 3 |  | Attendance registers and minutes of monthly management meeting | 3 |  | Attendance registers and minutes of monthly management meeting | 0 | Attendance registers and minutes of monthly management meeting
5.3 | Good governance and public participation | Sitting of Risk Management Committee meetings | Risk Management Committee Annual Meeting Diary endorsed by the Risk Management Committee by 31 August 2022. | 5.3.2.2. Number of Risk Management Committee meetings to be held quarterly | 4 | 1 | R65,000.00 | List of attendees signed by HOD and Minutes of meeting | 1 | R65,000.00 | List of attendees signed by HOD and Minutes of meeting | 1 | R65,000.00 | Minutes of meeting | 1 | R65000 | Minutes of meeting | R260,000.00 | Minutes of meeting
5.4. | Good Governance and Public Participation | Case Management | The municipality has 26 cases as at end of previous FY | 5.4.1. Percentage of cases managed by the institution | 100% | 100% | 803108 | Attendance register, instruction letters and litigation registers | 100% | 803108 | Attendance register, instruction letters and litigation registers | 100% | 803108 | Attendance register, instruction letters and litigation registers | 100% | 803108 | Attendance register, instruction letters and litigation registers | 3212432 | Attendance register, instruction letters and litigation registers
5.4. | Good Governance and Public Participation | Provision of legal advice on legal documents and matters | Legal Office provides legal guidance to the municipality | 5.4.3 Percentage of legal advice on legal documents and matters provided | 100% | 100% | 0 | Copy of contracts reviewed and consultation | 100% | 0 | Copy of contracts reviewed and consultation | 100% | 0 | Copy of contracts reviewed and consultation | 100% | 0 | Copy of contracts reviewed and consultation | 100% | Copy of contracts reviewed and consultation
5.5 | Good Gvernance and Public Participation | Sitting of council meetings | Adopted Rules and Standing Orders. | 5.5.1. Number of Council meetings to be held | 12 | 2 | 48000 | Attendance Register and Minutes | 3 | R 202 595 82 | Attendance Register and Minutes | 3 | 72000 | Attendance Register and Minutes | 4 | 406556.36 | Attendance Register and Minutes | 729152.18 | Attendance Register and Minutes
5.5 | Good Governance & Public Participation | Sitting of Council Committees | Adopted Rules and Standing Orders | 5.5.2.Number of Committee meetings to be held | 20 | 4 | 12000 | Attendance Register and Minutes | 4 | 12000 | Attendance Register and Minutes | 6 | 18000 | Attendance Register and Minutes | 6 | 18000 | Attendance Register and Minutes | 60000 | Attendance Register and Minutes
5.6 | Good Governance & Public Participation | Translation of Documents and reports | Received and translated 30 reports and documents | 5.6.1. Percentage of documents to be translated | 100% | 100% | 0 | Signed translation register | 100% | 0 | Signed translation register | 100% | 0 | Signed translation register | 100% | 0 | Signed translation register | R0.00 | Signed translation register
5.6 | Good Governance & Public Participation | Sitting of Internal Communicators Forum | Adopted Communications Strategy and Policy in place | 5.6.2. Number of Internal Communicators Forums to be held | 4 | 1 |  | Signed attendance register and minutes | 1 | 0 | Signed attendance register and minutes | 1 | 0 | Signed attendance register and minutes | 1 | 0 | Signed attendance register and minutes | NIL | Signed attendance register and minutes
5.6 | Good Governance & Public Participation | Sitting of Local Communicators forum | Adopted Communications Strategy and Policy in place | 5.6.3. Number of Local Communicators Forums to be held | 4 | 1 | 7200 | Signed attendance register and minutes | 1 | 7200 | Signed attendance register and minutes | 1 | 7200 | Signed attendance register and minutes | 1 | 7200 | Signed attendance register and minutes | 28800 | Signed attendance register and minutes
5.6 | Good Governance & Public Participation | Media Engagements, Print Media and Media Briefings on important events | Adopted Communications Strategy and Policy in place | 5.6.4. Percentage media engagements for municipal programmes and Events | 100% | 100% | 0 | Photographs, media statement and report | 100% | 0 | Photographs, media statement and report | 100% | 0 | Photographs, media statement and report | 100% | 0 | Photographs, media statement and report | 0 | Photographs, media statement and report
5.6 | Good Governance & Public Participation | Live Broadcast of events through Radio and TV Transmission | Adopted Communications Strategy and Policy in place | 5.6.6. Number of Media Partnership, Radio Slots and Live Broadcasts for important events to be held | 4 | 1 | 117000 | Purchase Order | 1 | 96000 | Purchase Order | 1 | 150000 | Purchase Order | 1 | 100000 | Purchase Order | 463000 | Purchase Order
5.6 | Good Governance & Public Participation | Production of the municipal newsletter | Communication Strategy and Policy in place | 5.6.7. Number of municipal newsletters to be produced | 1 | 0% | 0 | N/A | 1 | N/A | Delivery note | Nil | N/A | N/A | 1 | 100000 | Delivery note | 200000 | Delivery note
5.6 | Good Governance & Public Participation | Procurement of branding and Marketing material | Communication Strategy and Policy in place | 5.6.8. Number of Municipal branding material to be procured | 1 | 1 | 136900 | Delivery note | 0% | 0 | N/A | 0% | N/A | N/A | 0% | N/A | N/A | 136900 | Delivery note
5.6 | Good Governance & Public Participation | Procurement of Photographic equipment | Communication Strategy and Policy in place | 5.6.9. Number of times photographic equipment is procured | 1 | 0 | 0 | N/A | 1 | 144900 | Delivery note | 0% | 0 | N/A | 0% | 0 | N/A | 0 | Delivery note
5.6 | Good Governance & Public Participation | Annual review of Communication Strategy and the policy | Communication Strategy and Policy in place | 5.6.11. Number of times communication strategy and policy are reviewd | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 |  | 1 | 0 | Copy of reviewed Communication Strategy | 0 | Copy of reviewed Communication Strategy
5.6. | Good Governance & Public Participation | Procurement of Audio Visuals | Communication Strategy and Policy in place | 5.6.14. Number of Audio Visuals to be procured | 1 | 0 | 0 | N/A | 1 | 100000 | Delivery note |  | 0 | N/A | 1 | 100000 | Delivery note | 100000 | Delivery note
5.6. | Good Governance and Public Participation | Sitting of IGR meetings | IGR Policy | 5.6.16. Number of IGR meetings to be held | 4 | 1 | 17499 | Report and attendance register | 1 | 17499 | Report and attendance register | 1 | 17499 | Report and attendance register | 1 | 17499 | Report and attendance register | 69996 | Report and attendance register
5.7. | Good Governance and Public Participation | Support to Traditional Leaders | Municipality has 13 Traditional Councils. The leaders normally request assistance with transportation | 5.7.1 Percentage of support provided to traditional leaders | 100% | 100% | 35 714, 30 | Copy of requests | 100% | 35714.3 | Copy of requests | 100% | 35714.3 | Copy of requests | 100% | 35714.3 | Copy of requests | 142857.4 | Copy of requests
5.7. | Good Governance and Public Participation | Facilitation of payment of Ward Committee Stipend | Ward Committee stipend is paid monthly | 5.7.2. Number of times ward committee stipend is paid | 12 | 3 | 2 496 000 | Proof of payment | 3 | 2 496 000 | Proof of payment | 3 | 2 496 000 | Proof of payment | 3 | 2 496 000 | Proof of payment | 9984000 | Proof of payment
5.7. | Good Governance and Public Participation | Mobilization of stakeholders for all governmental programs | Public Participation policy guides the involvement of the public in municipal events and activities. | 5.7.3 Number of municipal programs to be mobilised for | 10 | 1 | 0 | Report and Attendance register | 2 | 0 | Report and Attendance register | 4 | 0 | Report and Attendance register | 3 | 0 | Report and Attendance register | 0 | Report and Attendance register
5.7. | Good Governance and Public Participation | Public Participation Awareness Campaign | Communities are educated on the municiplity's Public Participation processes. Public Particpation Policy is adopted by council | 5.7.4. Number of public participation awareness campaigns conducted | 4 | 1 | 83559.55 | Attendance register and report | 1 | 83 559 , 55 | Attendance register and report | 1 | 83 559, 55 | Attendance register and report | 1 | 83,559,55 | Attendance register and report | 334238.23 | Attendance register and report
5.7.. | Good Governance and Public Participation | Mayoral Campaigns - Public consultation through EXCO Outreach and IDP Roadshows | Municipal Systems Act mandates municipalites to encourage public participation. Public Participation policy guides the involvement of the public in municipal events and activities. | 5.7.5. Number of Mayoral campaigns - Public consultations through EXCO Outreach, MPAC Oversight and IDP Roadshows | 2 | 0 | 0 | N/A | 0 | 0 | N/A | 1 exco outreach and MPAC Oversight | 880000 | Attendance registers and report | 1 IDP & Budget roadshows | 880000 | Attendance register and report | 1600000 | Attendance register and report
5.7. | Good Governance and Public Participation | Sitting and functionality of Ward Committee Meetings | Two wards were not sitting for the meetings due to a standoff between the ward and ward committee members. New Ward Committees elected for the new term. Standard Ward Committee Procedure Manual on establishment of ward committees, Code of Coduct for Ward Committee Members | 5.7.6. Number of ward committee meetings to be held | 12 | 3 | 0 | Attendance register, Minutes and report | 3 | 0 | Attendance register, Minutes and report | 3 | 0 | Attendance register, Minutes and report | 3 | 0 | Attendance register, Minutes and report | 0 | Attendance register, Minutes and report
5.7. | Good Governance and Public Participation | Publication of municipal events | Public participation policy is adopted by council. Municipal Systems Act mandates public participation. | 5.7.7. Number of Municipal events advertised | 13 | 2 | 11666.67 | Advert | 3 | 23.333,34 | Advert | 3 | 23333.34 | Advert | 5 | 11666.67 | Advert | 70000 | Advert
5.7. | Good Governance and Public Participation | Management of Petitions | Public Participation Policy adopted by council | 5.7.8. Percentage of Municipal Petition received and attended | 100% | 100% | 0 | Copy of petitions received, attendance register and petitions report | 100% | 0 | Copy of petitions received, attendance register and petitions report | 100% | 0 | Copy of petitions received, attendance register and petitions report | 100% | 0 | Copy of petitions received, attendance register and petitions report | 0 | Copy of petitions received, attendance register and petitions report
5.7. | Good Governance and Public Participation | Commemoeration of Mpondo Revolt | Historical event to commemorate Mpondo Revolt | 5.7.9. Number of times Mpondo Revolt is commemorated | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 257000 | Report and attendance register | 257000 | Report and attendance register
5.7. | Good Governance and Public Participation | Conducting Public and voter education | Public Participation Policy adopted by council. Creating awarenes on the importance of voting | 5.7.10. Number of Public and voter education campaigns to be held | 3 | 0 |  | N/A | 0 | 0 | N/A | 1 | 89335.82 | Attendance register and report | 2 | 89335.82 | Attendance register and report | R178 671 ,64 | Attendance register and report
5.7. | Good Governance and Public Participation | Promotion of moral regeneration through events | Moral regeneration movement guidelines from The Presidency serve as a guide. | 5.7.11. Number of moral regeneration movement events to be held | 4 | 1 | 92500 | Report and Attendance Register | 1 | 92500 | Report and Attendance Register | 1 | 92500 | Reports and Attendance Register | 1 | 92500 | Report and Attendance Register | 370000 | Report and Attendance Register
5.8. | Good Governance and Public Participation | Support to destitute children | National Childrens' Rights Charter | 5.8.1. Number of child programs to be supported | 2 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 139599.18 | Delivery note and receiving register | 1 | 0 | Delivery note and receiving register | R 279 198 .36 | Delivery note and receiving register
5.8 | Good Governance and Public Participation | Youth Development through Mayoral Week | Youth Development strategy and policy adopted by the council | 5.8.2 . Number of Mayoral week programs to be held | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 |  | Attendance Register and report | 2720000 | Attendance Register and report
5.8. | Good Governance and Public Participation | Youth Development through Miss Ingquza | The program is requested by the youth for confidence and self-esteem development | 5.8.3. Number of beauty pageants to be held | 1 | 1 |  | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 0 | Report and Attendance Register | 410000 | Report and Attendance Register
5.8. | Good Governance and Public Participation | Gender Development | Guided by National Gender Commission and Women's Caucus | 5.8.4. Number of women's events to be held | 1 | 1 | R214.817.00 | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | 1 | R214.817.00 | Attendance Register and report | R 214 817 .00 | Attendance Register and report
5.8. | Good Governance and Public Participation | Support to the elderly and veterans | National Policy on Elderly and Veterans | 5.8.5. Number of times support to the elderly and veterans is provided | 1 | 1 | R367 696 .00 | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | 1 | R367 696 .00 | Attendance Register and report | R367. 696.00 | Attendance Register and report
5.8 | Good Governance and Public Participation | Community Development - Provision of Burial Support | Development of Burial Support policy | 5.8.6. Percentage of burial support provided to the impoverished | 100% | 100% | R 101 148. 95 | Copy of request | 100% | R101 148.95 | Copy of request | 100% | R101 148. 95 | Service of request | 100% | R 101 148/95 | Copy of request | 404595.82 | Copy of request
5.8. | Good Governance and Public Participation | Community Initiative - Sitting of O.R. Tambo memorial lecture | Promotion of social cohesion | 5.8.7. Number of times O.R. Tambo Memorial Lectures is held | 1 | 0 | 0 | N/A | 1 | R 264 590.00 | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | R 264 590.00 | Attendance Register and report
5.8. | Good Governance and Public Participation | Community Initiative - Creation of awareness against the abuse of women and children during the 16 days of activism | Guided by National Gender Commission and Women's Caucus | 5.8.8. Number of events held in line with 16 days of Activism | 1 | 0 | 0 | N/A | 1 | 300000 | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | 300000 | Attendance Register and report
5.8. | Good Governance and Public Participation | Support to people living with disability | National Forum on Disability launched | 5.8.9. Number of times support is provided to people living with disability | 1 | 0 | 0 | N/A | 1 | R186 938 .18 | Attendance Register and report | 0 | 0 | N/A | 0 | 0 | N/A | R 186 938.18 | Attendance Register and report
5.8 | Good Governance and Public Participation | Youth Development through support to the Youth Council | Adopted Youth Development Strategy and Policy | 5.8.10. Number of youth council programmes to be held | 4 | 1 | 25000 | Attendance Register and report | 1 | 25000 | Attendance Register and report | 1 | 25000 | Attendance Register and report | 1 | 25000 | Attendance Register and report | 100000 | Attendance Register and report
5.6 | Good Governance and Public Participation | Celebration of Mandela Day | Event is on National Calendar and is celebrated annually | 5.8.11. Number of times Mandela Day is celebrated | 1 | 1 | 121000 | attendance register and report | Nil | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 0 | Attendance Register and report

## Milestones MM (hidden)
| PROJECT NO. | PROJECT 01
| PROJECT NAME: |  | Performance management system
| INSTITUTION: |  | Ingquza Hill Local Municipality
| PROJECT START DATE: |  | 2018-07-01
| PROJECT COMPLETION DATE: |  | 2019-06-30
| TOTAL APPROVED BUDGET: |  | 0
| SOURCE OF FUNDING: |  | None
| Project Objectives | [6 empty] | Project Key Performance Indicators
| To promote good governance and public participation | [6 empty] | Number of performance agreement and accountability contratcs signed
Number of reports reviewed
Number of reports tabled to the Council
| Key Milestones | [6 empty] | Responsible Official | Time Frames
[9 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
One on one meetings with the Directors to align performance agreements
Submission of signed performance agreements 2018/19 to CoGTA
Monthly review of reports by management
Submision of reports to Council | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Qaurterly report presentation to employees | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
Project Expenditure
PROJECT NO.2
| PROJECT NAME: | 1st Quarter 2: Intergrated Development Plan
| INSTITUTION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: 2611250
| SOURCE OF FUNDING: | 1st Quarter 2: Equitable Share
| Project Objectives | 3rd Quarter 1: Project Key Performance Indicators
| To promote good governance and public participation | 3rd Quarter 1: Number of IDP meeting held
Number of departmemental strategic plans held
Number of Council strategic planning held
| Key Milestones | 3rd Quarter 1: Responsible Official; 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
| Preparation and presentation of the IDP process plan 2019/2020 | [6 empty] | S. Rubuluza | bar: 1st Quarter 1
| Process plan and situational analysis | [6 empty] | S. Rubuluza
| Strategies and objectives | [6 empty] | S. Rubuluza | bar: 1st Quarter 1 to 1st Quarter 2
| Project identification | [6 empty] | S. Rubuluza | bar: 1st Quarter 3 to 2nd Quarter 1
| Intergration | [6 empty] | S. Rubuluza | bar: 2nd Quarter 3 to 3rd Quarter 1
| Departmental strategic planning | [6 empty] | S. Rubuluza | bar: 2nd Quarter 2; 4th Quarter 2 to 4th Quarter 3
| Council strategic planning | [6 empty] | S. Rubuluza | bar: 3rd Quarter 2
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| IDP Rep forums and technical committee | 600000 | 45500 | 60000 | 20000 | 39000 |  | 20000 | 39000 | [5 empty] | 40000 |  |  |  | 328000
| Departmental strategic planning | 2nd Quarter 2: 220000
| Council strategic planning | [8 empty] | 2,3 m
PROJECT NO 3
| PROJECT NAME: | 1st Quarter 2: Intergovernmental Relations
| INSTITUTION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: 93000
| SOURCE OF FUNDING: | 1st Quarter 2: Equitable Share
| Project Objectives | 3rd Quarter 1: Project Key Performance Indicators
| To promote good governance and public participation | 3rd Quarter 1: Number of meetings held with functional IGR structures
Number of war rooms held
| Key Milestones | 3rd Quarter 1: Responsible Official; 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Development of IGR terms of reference and policy | bar: 1st Quarter 1
IGR quarterly meetings | bar: 1st Quarter 2; 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 1
Social and economic cluster meetings | bar: 2nd Quarter 2; 3rd Quarter 1; 4th Quarter 2
Number of local war rooms held | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| Project Expenditure | 600000 | 45500 | 60000 | 20000 | 39000 |  | 20000 | 39000 | [5 empty] | 40000 |  |  |  | 328000
PROJECT NO 4
| PROJECT NAME: | 1st Quarter 2: Legal Services
| INSTITUTION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: 2369600
| SOURCE OF FUNDING: | 1st Quarter 2: Equitable Share
| Project Objectives | 3rd Quarter 1: Project Key Performance Indicators
| To promote good governance and public participation | 3rd Quarter 1: Number of meetings held with functional IGR structures
Number of war rooms held
| Key Milestones | 3rd Quarter 1: Responsible Official; 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Monitor preparedness of the lawyers and ensure that most cases have court dates | bar: 1st Quarter 1
Monthly meeting IHLM lawyers to ensure monitoring of cases | bar: 1st Quarter 2; 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 1
Social and economic cluster meetings | bar: 2nd Quarter 2; 3rd Quarter 1; 4th Quarter 2
Number of local war rooms held | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| Project Expenditure | 600000 | 45500 | 60000 | 20000 | 39000 |  | 20000 | 39000 | [5 empty] | 40000 |  |  |  | 328000
PROJECT NO 5
| PROJECT NAME: | 1st Quarter 2: Risk Management
| INSTITUTION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: NIL
| SOURCE OF FUNDING: | 1st Quarter 2: None
\] |  | 3rd Quarter 1: Project Key Performance Indicators
\ | To promote good governance and public participation | 3rd Quarter 1: Number of activities implmented as per risk management imolementation plan
Number of risk jmanagement committeemeetings held
Number of risk management workshops held
| Key Milestones | 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
annul review of the risk manaementimplementation plan | bar: 1st Quarter 1 to 1st Quarter 2
identification of emerging | bar: 1st Quarter 1 to 1st Quarter 2
review reports y managemenent committee | bar: 1st Quarter 2; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
conduct risk management and review risk register | bar: 4th Quarter 1 to 4th Quarter 3
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
Project Expenditure
PROJECT NO 6
| PROJECT NAME: | 1st Quarter 2: Internal Audit Unit
| INSTITUION: | 1st Quarter 2: Ingquza Hill Local Municipality
\ | PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: 105640
| SOURCE OF FUNDING: | 1st Quarter 2: Equitable Share
| Project Objectives | 3rd Quarter 1: Project Key Performance Indicators
| · To promote good governance and public participation | 3rd Quarter 1: . Number of activities implemented as per risk management implementation plan
. Number of Risk Management Committee meeting held
. Number of risk management workshops held
| Key Milestones | 3rd Quarter 1: Responsible Official; 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
| · Annual review of the risk management implementation plan | [6 empty] | N. Jiki/ S. Magenu | bar: 1st Quarter 1 to 1st Quarter 3
| · Identification of emerging risks | [6 empty] | N. Jiki/ S. Magenu | bar: 1st Quarter 1 to 1st Quarter 3
| · Review of the institutional risk register | [6 empty] | N. Jiki/ S. Magenu | bar: 1st Quarter 1 to 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| · Review reports by Risk Management Committee | [6 empty] | N. Jiki/ S. Magenu | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| · Conduct risk assessment and review risk register | [6 empty] | N. Jiki/ S. Magenu | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| Project Expenditure | [17 empty] | 0 | Equitable Share
| · Annual review of the risk management implementation plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| · Identification of emerging risks | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| · Review of the institutional risk register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
| · Review reports by Risk Management Committee | 0 | 0 | 26400 | 0 | 0 | 26400 | 0 | 0 |  | 26400 |  | 0 |  | 0 |  | 26400 |  | 105600
| · Conduct risk assessment and review risk register | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
PROJECT NO 7
| PROJECT NAME: | 1st Quarter 2: Council Support
| INSTITUION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: 2741210
| SOURCE OF FUNDING: | 1st Quarter 2: Equitale Share
Project Key Performance Indicators
| To promote good governance and public participation | 3rd Quarter 1: Number of council calendar adopted
Number of council minutes prepared
Number of reports adopted
Number of council resolution registers compiled
| Key Milestones | 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
sitting of council and its committes | bar: 1st Quarter 1
sitting of council meetings | bar: 1st Quarter 1; 2nd Quarter 1 to 4th Quarter 3
sitting of executive committee
municipal oublic accounts committee (MPAC) | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 1; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 1
rules of committee | bar: 1st Quarter 2; 3rd Quarter 1
ethics and membeships interest | bar: 1st Quarter 2; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
multi-party womens caucus | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 3
public participation and pettions committee | bar: 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
sitting section 80 committee | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 2
taking council to the people | bar: 2nd Quarter 2
state of the municipal address | bar: 4th Quarter 2
junior council | bar: 1st Quarter 3; 3rd Quarter 2
translation of quarterly reports and publiations
mpondo revolt | bar: 4th Quarter 3
IDP&budget roadshows | bar: 4th Quarter 1
exco outreach programme | bar: 3rd Quarter 2
awareness campaign | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 1; 4th Quarter 3
stakeholder engegements | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| sitting of council meetings | 41400 |  |  | 41400 | 41400 | 41400 | 41400 | 41400 |  | 41400 |  | 41400 |  | 41400 |  | 41400 |  | 41400000 | Equitable share
| sitting of executive committee | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 | 3750 |  | 3750 |  | 3750 |  | 3750 |  | 3750 |  | 3750 | Equitable share
| sitting of municipal public accounts committee (MPAC) | 8800 | 8800 |  | 8800 |  |  | 8800 | 8800 |  | 8800 |  | 8800 | [5 empty] | 52800 | Equitable share
| sitting of members interest and ethics committee | 1st Quarter 2: 2200; 2nd Quarter 3: 2200 |  | 2200 | [5 empty] | 2200 |  | 8800 | Equitable share
| sitting of rules committee | 1st Quarter 2: 2200; 3rd Quarter 2: 2200 | [9 empty] | 4400 | Equitable share
| sitting of public participation and petitions committee | 1st Quarter 3: 2200; 2nd Quarter 2: 2200; 3rd Quarter 2: 2200 | [5 empty] | 2200 |  |  |  | 8800 | equitable share
| womens caucus | 1st Quarter 2: 5400; 2nd Quarter 2: 5400; 3rd Quarter 2: 5400 | [7 empty] | 54000 |  | 21600 | equitable share
| sitting of 80 committee | 1st Quarter 1: 22500; 2nd Quarter 1: 22500; 3rd Quarter 1: 22500 |  | 22500 |  | 22500 |  | 22500 |  |  |  | 135000 | equitable share
| taking counccil to the people | 2nd Quarter 2: 351400 | [9 empty] | 351400 | equitable share
| state of the municipal address | [13 empty] | 193900 |  |  |  | 193900 | equitable share
| junior council | 1st Quarter 3: 55480 | [9 empty] | 110960 | equitable share
| mpondo revolt | [15 empty] | 476000 |  | 476000 | equitable share
| exco outreach programme | [8 empty] | 1200000 | [8 empty] | 1200000 | equitable share
| IDP&budget roadshows | [14 empty] | 1200000 |  |  | 1200000 | equitable share
| awareness campaign | 1st Quarter 2: 560000; 2nd Quarter 2: 250000; 3rd Quarter 2: 250000 | [6 empty] | 540000 |  |  | 1560000 | equitable share
| stakeholder engegements | 1st Quarter 2: 38750; 2nd Quarter 2: 38750 |  |  |  | 38750 |  |  |  | 38750 |  | 155000 | equitable share
PROJECT NO 8
| INSTITUTION: | 1st Quarter 2: Ingquza Hill Local Municipality
| PROJECT NAME | 1st Quarter 2: Communications
| PROJECT START DATE: | 1st Quarter 2: 2018-07-01
| PROJECT COMPLETION DATE: | 1st Quarter 2: 2019-06-30
| TOTAL APPROVED BUDGET: | 1st Quarter 2: NIL
| SOURCE OF FUNDING: | 1st Quarter 2: None
Project Key Performance Indicators
| To promote good governance and public participation | 3rd Quarter 1: Number of projects completed as per audit plan
Number of audit committee meetings held
Numer of audit committee strategic planning held
| Key Milestones | 3rd Quarter 2: Time Frames
|  | 3rd Quarter 2: 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[9 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Sitting of Local Communicators Forum
Sitting of Internal Communicators Forum
Media Engagements, Radio slots, Print media and Media Briefings on important events | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 1; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 3
Radio and TV transmission | bar: 1st Quarter 1
TV Licensing | bar: 1st Quarter 1
Production of the Municipal Newsletter
Procurement of Flag poles | bar: 1st Quarter 1
Procurement of Flag and Pull-Up Banners | bar: 2nd Quarter 1
Procurement of Branded Laptop Stickers+B230:R230 | bar: 1st Quarter 2
Procurement of Flyers and Posters | bar: 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Purchase of Digital Camera and Video Camera | bar: 1st Quarter 1
Branding and Marketing of Municipal and Government Events | bar: 1st Quarter 2 to 3rd Quarter 1; 4th Quarter 1 to 4th Quarter 3
Review and update Website and Social Network
Develop Communication Plan | bar: 1st Quarter 1
Review Communication Strategy | bar: 3rd Quarter 2
Adoption of Communication Strategy by Council | bar: 4th Quarter 1
Capacity Buiding of Communications Officials | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
| Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
|  | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
|  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 |  | 3 |  | 1 |  | 2 |  | 3
| Sitting of Local Communicators Forum | 1st Quarter 2: 8000; 2nd Quarter 2: 8000; 3rd Quarter 2: 8000 | [5 empty] | 8000 |  |  |  | 32000
| Radio and TV transmission | 1st Quarter 1: 100000 | [9 empty] | 100000
| TV Licensing | 1st Quarter 1: 10000 | [9 empty] | 10000
| Production of the Municipal Newsletter | 2nd Quarter 3: 80000 | [6 empty] | 80000 |  |  | 160000
| Procurement of Flag poles | 1st Quarter 1: 32000 | [9 empty] | 32000
| Procurement of Flag and Pull-Up Banners | 2nd Quarter 1: 25000 | [9 empty] | 25000
| Procurement of Branded Laptop Stickers | 1st Quarter 2: 5000 | [9 empty] | 5000
| Procurement of Flyers and Posters | 2nd Quarter 2: 1000 | 1000 | [5 empty] | 1000 |  | 1000 | 4000
| Purchase of Digital Camera and Video Camera | 1st Quarter 1: 62000 | [9 empty] | 62000
430000
PROJECT 09

## Social Services Milestones (hidden)
PROJECT NO. | 6.1
PROJECT NAME: | CRIME PREVENTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 273032
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  |  | Project Key Performance Indicators
• To create platform for stakeholders involvement in crime prevention initiatives |  |  |  | • Number of CSF Meetings convened
• To create awareness about crime trends and patterns |  |  |  | • Number of awareness campaigns conducted
• To safeguard municipal property and employees |  |  |  | • Number of access points guarded
• To provide effective close protection operation to principals |  |  |  | • Number of personnel deployed
To provide support to Community Policing Forums/ Village committees |  |  |  | Number of CPFs Equipment supported
Key Milestones |  |  |  | Responsible Official | Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of CSF Meetings to be convened • Securing the venue • Sending invitation letters • Arranging the logistics |  |  |  | L. Joji | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of awareness campaigns to be conducted • Securing the venue • Sending of invitation letters • Arranging the logistics |  |  |  | M. Njisane | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of access points guarded • Drafting duty roosters • Signing of duty roosters • Monitoring of attendance and work performance |  |  |  | M. Njisane | 6 | 6 | 6 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Number of personnel deployed • Deployment of personnel to specific principal • Conducting of close protection operations |  |  |  | M. Njisane | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Number of CPFs Equipment procured • Drafting and submission of specification • Submission of pre-requisition • Sitting of Specification Committee • Sitting of Bid Evaluation Committee • Siting of Bid Adjudication Committee • Appointment of Service Provider • Delivery of goods |  |  |  | L. Joji | bar: 3rd Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
CSF Meetings
Crime Prevention Awareness Campaigns |  |  | 1st Quarter 2: 50000; 2nd Quarter 2: 50000; 3rd Quarter 2: 50000; 4th Quarter 2: 50000 | 200000 | Own Rev
Safeguarding of municipal premises
VIP Protection
CPF Support |  |  | 3rd Quarter 2: 20000 | 200000 | Own Rev
PROJECT NO. | 6.2
PROJECT NAME: | BEACH SAFETY MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To prevent drownings in all three beaches during peak seasons |  |  | 1st Quarter 2: • Number of deployment times for lifeguards
To prevent drowings in all three beaches during peak seasons |  |  | 1st Quarter 2: Number of times uniform or protective clothing is procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Depoloyment of lifeguards during peak seasons |  |  |  | Joji | bar: 2nd Quarter 3; 3rd Quarter 3
Provision of lifeguards equipment |  |  |  | Joji | bar: 2nd Quarter 3; 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of deployment times for lifeguards |  |  | 2nd Quarter 3: 300000 | 300000 | Equitable Share
Number of times lifeguards provided with equipment Drafting and submission of specification Submission of Pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjutication Committee Appointment of Service Provider Delivery of Goods |  |  | 2nd Quarter 3: 200000 | 200000 | Equitable Share
PROJECT NO. | 6.3
PROJECT NAME: | TRAFFIC LAW ENFORCEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 618000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
•To enforce compliance with road traffic regulations |  |  | 1st Quarter 2: • Number of traffic fines issued
• To comply with speed enforcement regulations |  |  | 1st Quarter 2: • Number of speed machine calibrations conducted
To equip the traffic personnel with tools of trade for work readiness |  |  | 1st Quarter 2: Number of traffic personnel provided with tools of trade
• To enhance municipal revenue through traffic fines |  |  | 1st Quarter 2: • Amount collected from traffic fines
To enhance municipal revenue through traffic fines |  |  | 1st Quarter 2: Number of Books and printing publications
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of traffic fines issued |  |  |  | Vato (CTO) | 200 | 250 | 250 | 210 | 300 | 340 | 280 | 250 | 220 | 250 | 240 | 190
Number of Speed machine calibrations conducted |  |  |  | Joji (PSM) | bar: 1st Quarter 3; 3rd Quarter 2
Provision of tools of trade to traffic personnel |  |  |  | Vato (CTO) | bar: 1st Quarter 3; 3rd Quarter 2
Amount collected from traffic fines |  |  |  | Vato (CTO)
Number of time books are procured |  |  |  | Vato (CTO) | bar: 2nd Quarter 1; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of traffic fines issued Setting of Duty Rosters Traffic Safety Patrols Issuing of traffic fines |  |  | 1st Quarter 3: 22,433.37; 3rd Quarter 1: 17,566.63 | 40,000 | Traffic Fines
Number of Speed machine calibrations conducted Submission of pre-requisition Issuing of an order Conducting calibration by the manufacturer Fcilitation of payment |  |  | 1st Quarter 3: 9000; 3rd Quarter 3: 9000 | 18,000 | Traffic Fines
Number of traffic personnel provided with working tools Drafting and Submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Adjudication Committee Appointment of service provider Delivery of goods |  |  | 1st Quarter 3: 180000 | 180000 | Traffic Fines
Amount collected from traffic fines Setting of duty rosters Traffic satey patrols Issuing of traffic fines |  |  | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | 300000 | Traffic Fines
Number of time books are procured |  |  | 2nd Quarter 1: 40000; 4th Quarter 1: 40000 | 80000
PROJECT NO. | 6.4
PROJECT NAME: | REGISTRATION & LICENSING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 630934
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To provide effective traffic support service for motor vehicle licensing |  |  | 1st Quarter 2: Number of motor vehicles to be licensed
To comply with requirements for operating of VTS |  |  | 1st Quarter 2: VTS Registration Certificate
To minimise unroadworthy vehicles |  |  | 1st Quarter 2: Number of vehicles examined
To Comply with SABS standards of examination of vehicles |  |  | 1st Quarter 2: Number of VTS equipment calibrarations
To provide unlicenced people with oppoturnity to possess leaners licence |  |  | 1st Quarter 2: Number of learners licence application administered
To comply with requirements for operating a DLTC |  |  | 1st Quarter 2: Upgraded DLTC Registration Certificate
To comply with requirements for operating a DLTC |  | ing of DLTC | 1st Quarter 2: Number of driving licences applications administered
Payment of driving licence cads orderd from DLCA |  |  | 1st Quarter 2: Number of invoices for driving cards paid
To enhance municipal revenue generation through agency fees |  |  | 1st Quarter 2: Amount generated from ENaTIS Agency fees
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of motor vehicles to be licensed Provision of application forms Distribution of face value documents Conducting of licensing transations |  |  |  | VATO(CTO) | 750 | 750 | 750 | 800 | 800 | 1100 | 800 | 750 | 750 | 750 | 750 | 750
Number of vehicles to be examined Provision of application forms Distribution of face value documents Conducting of vehicles examination and testing |  |  |  | VATO (CTO)&VTS Management Rep | 100 | 140 | 160 | 180 | 200 | 220 | 240 | 210 | 200 | 200 | 240 | 210
VTS equipment calibrations Submission of pre-requisition Issuing of an order Conducting of calibration by manufacturer Facilitation of payment |  |  |  | JOJI (PSM) | bar: 3rd Quarter 1
Number of Learners licence applications |  |  |  | VATO(CTO) | 331 | 333 | 336 | 480 | 480 | 540 | 540 | 480 | 337 | 330 | 334 | 336
Number of Driving Licence applications |  |  |  | VATO(CTO) | 150 | 160 | 190 | 220 | 2400 | 340 | 300 | 335 | 365 | 350 | 380 | 370
Number of invoices for driving licences paid |  |  |  | VATO | bar: 1st Quarter 1 to 4th Quarter 3
Amount generated from ENaTIS Agency fees |  |  |  | JOJI (PSM)
VTS 3% levy paid to SABS |  |  |  | JOJI (PSM) | bar: 2nd Quarter 3; 4th Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of vehicles to licensed |  |  | 1st Quarter 3: 30,000; 3rd Quarter 2: 30,000 | 60,000 | eNatis Agency Fees
Number of vehicles examined
Number of VTS equipment calibrations |  |  | 3rd Quarter 3: 150000 | 150000 | Enatis Agency fees
Number of learners licence examined
Number of driving licences administered
Number of invoices for driving licences paid |  |  | 26000 | 26000 | 28000 | 28000 | 28000 | 34000 | 35000 | 35000 | 40000 | 38000 | 39000 | 43000 | 400,000 | eNatis Agency Fees
Amount generated from ENaTIS Agency fees |  |  | 4000 | 430000 | 500000 | 480000 | 482000 | 483000 | 500000 | 524000 | 560000 | 53000 | 534000 | 536000 | 5,934,080
VTS 3% levy paid to SABS |  |  | 2nd Quarter 3: 15000 | 15,000 | eNatis Agency Fees
PROJECT NO. | 6.5
PROJECT NAME: | DISASTER RISK MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide relief to disaster victims |  |  | 1st Quarter 2: • Number of times for acquisition of disaster relief items
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Procurement of disaster relief tools |  |  |  | Joji | bar: 2nd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
To provide relief Drafting and submission of specification Submission of pre-requisition Sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjutication Committee Appointment of service provider Delivery of Goods Issuing of relief |  |  | 2nd Quarter 1: 300000 | 300000 | Equitable Share
PROJECT NO. | 6.6
PROJECT NAME: | SOCIAL FACILITATION (HEALTH)
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 84800
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To prevent spread of non-communicable diseases |  |  | 1st Quarter 2: • Number of LAC meetings convened
• To promote healthy lifestyle |  |  | 1st Quarter 2: • Number of awareness campaigns to be conducted
• To improve nutrition for infetced parties |  |  | 1st Quarter 2: • Number of clinic gardens supported
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of meetings to be convened • Securing the venue • Writing and sending of invitation letters • Arrange the logistics |  |  |  | Tukani | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of awareness campaigns to be conducted • Securing the venue • Writing and sending of invitation letters • Arrange the logistics |  |  |  | Tukani | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of OVCs supported • Submission of pre-requisition • Issuing of an order • Delivery of goods by the service provider Distribution of goods to the beneficiaries Facilitation of payment |  |  |  | Tukani | 2nd Quarter 2: 24; 4th Quarter 3: 12
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of meetings to be convened • Securing the venue • Writing and sending of invitation letters • Arrange the logistics | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of awareness campaigns to be conducted • Securing the venue • Writing and sending of invitation letters • Arrange the logistics |  |  | 1st Quarter 2: 15; 2nd Quarter 2: 15; 3rd Quarter 2: 15; 4th Quarter 2: 15 | 60,000 | Own Revenue
Number of OVCs supported • Submission of pre-requisition • Issuing of an order • Delivery of goods by the service provider Distribution of goods to the beneficiaries Facilitation of payment |  |  | 1st Quarter 2: 24,800 | 24,800 | Equitable Share
PROJECT NO. | 6.7
PROJECT NAME: | LIBRARY SERVICES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 228000
SOURCE OF FUNDING: | LIBRARY SERVICES CONDITIONAL GRANT
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To create awareness on library usage |  |  | 1st Quarter 2: • Number of outreach programmes to be conducted
• To promote participation on national events |  |  | 1st Quarter 2: • Number of LIASA calender events to be celebrated
• To provide effective library service delivery |  |  | 1st Quarter 2: • Number of patrons visiting libraries
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of outreach programmes to be conducted |  |  |  | Nqalo | 2 | 2 |  | 2 | 2 |  |  | 2 | 2 | 2 | 2
Number of LIASA calender events to be conducted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  |  | Nqalo | bar: 1st Quarter 2; 3rd Quarter 2; 4th Quarter 2
Transportation of local winners |  |  |  | Nqalo | bar: 1st Quarter 2; 3rd Quarter 2; 4th Quarter 2
No of patrons vising libraries |  |  |  | Nqalo | 1100 | 1100 | 800 | 1000 | 1300 | 700 | 600 | 1200 | 1200 | 1150 | 1150 | 700
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of outreach programmes to be conducted | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
Number of LIASA calender events to be conducted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  | 1st Quarter 2: 50000; 3rd Quarter 2: 50000; 4th Quarter 2: 50000 | 150000 | Own Revenue
Number of times of transportation local winners Submission of pre-requisition Issuing of an order Arrange the logistics |  |  | 1st Quarter 2: 23333; 3rd Quarter 2: 23333; 4th Quarter 2: 23333 | 70000 | Own Revenue
PROJECT NO. | 6.8
PROJECT NAME: | SPORT PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 335000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To create promote stakeholders participation in sport decision making |  |  | 1st Quarter 2: • Number of sport council meetings to be convened
• To promote sport participation |  |  | 1st Quarter 2: • Number of sport events to be hosted
• To improve sport management |  |  | 1st Quarter 2: • Number of federations , clubs and players to be assisted
To promote promotion |  |  | 1st Quarter 2: Number of sport equipment procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport council meetings to be convened • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Makhobongwana | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of sport events to be hosted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  |  | Makhobongwana | bar: 2nd Quarter 1; 4th Quarter 1
Number of federations, clubs and players to be assisted |  |  |  | Makhobongwana | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
Number of times sport equipment is provided |  |  |  | Makhobongwana | bar: 1st Quarter 3; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport council meetings to be convened • Securing the venue • Writing and sending invitation letters • Arranging the logistics | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of sport events to be hosted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  | 2nd Quarter 2: 117500; 4th Quarter 2: 117500 | 235000 | Equitable Share
Number of federations, clubs and players to be assisted |  |  | 1st Quarter 3: 28750; 2nd Quarter 3: 28750; 3rd Quarter 3: 28750; 4th Quarter 3: 28750 | 115000
Number of sport equipment procured |  |  | 1st Quarter 1: 50000; 4th Quarter 1: 50000 | 100000 | Equitable Share
PROJECT NO. | 6.9
PROJECT NAME: | EARLY CHILDHOOD DEVELOPMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 123279
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To promote early childhood development |  |  | 1st Quarter 2: • Number of pre-schools to be support
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of pre-schools to be supported |  |  |  | Makhobongwana | 3rd Quarter 2: 6
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of pre-schools to be supported Drafting and submission of specification Submission of pre-requisition sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of service provider Delivery of goods Handing over of goods |  |  | 3rd Quarter 2: 80000 | 80000 | Equitable Share
PROJECT NO. | 6.1
PROJECT NAME: | ARTS & CULTURE PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 180000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To promote arts and culture participation |  |  | 1st Quarter 2: • Number of arts and culture activities or events to be supported
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of arts and culture activities or events to be supported • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Makhobongwana | bar: 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 3; 4th Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of arts and culture activities or events to be supported • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  | 1st Quarter 3: 40000; 2nd Quarter 2: 50000; 3rd Quarter 3: 50000; 4th Quarter 3: 40000 | 180000 | Own Revenue
PROJECT NO. | 6.11
PROJECT NAME: | FREE BASIC SERVICES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 8600000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To ensure proper leadership and management on provision of indigent support |  |  | 1st Quarter 2: • Number of steering committee meetings to be conducted
• To ensure that all house households are evaluated |  |  | 1st Quarter 2: • Number of households registered and forms captured
• To ensure that deserving poor people receive the indigent support |  |  | 1st Quarter 2: • Number of indigents benefiting
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of steering committee meetings to be conducted • Securing the venue •Writing and sending invitation letters • Arranging the logistics |  |  |  | Tukani/Nodlabi | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of households registered and forms captured |  |  |  | Nodlabi | 2nd Quarter 2: 17000; 2nd Quarter 3: 17000; 3rd Quarter 1: 17000
Number of indigents benefiting |  |  |  | Nodlabi | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385 | 9385
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of steering committee meetings to be conducted • Securing the venue •Writing and sending invitation letters • Arranging the logistics |  |  | 1st Quarter 1: 15000; 2nd Quarter 1: 15000; 3rd Quarter 1: 15000; 4th Quarter 1: 15000 | 60000 | Equitable Share
Number of households registered and forms captured |  |  | 1st Quarter 3: 10000; 3rd Quarter 1: 15000 | 25,000 | Equitable Share
Number of indigents benefiting Drafting and submission of specification Submission of pre-requisition Sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of Service Provider Delivery of Goods |  |  | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 716, 666 | 8600000 | Equitable Share
PROJECT NO. | 6.12
PROJECT NAME: | EXPANDED PUBLIC WORKS PROGRAMME
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 2000000
SOURCE OF FUNDING: | EPWP GRANT
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• Poverty alleviation |  |  | 1st Quarter 2: • Number of times for employment of casuals
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times for employment of casual workers |  |  |  | Dakwa | bar: 2nd Quarter 1; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times for employment of casual workers Recruitment and selection Signing of employment contracts |  |  | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 166666 | 2000000 | EPWP Grant
PROJECT NO. | 6.13
PROJECT NAME: | PROTECTIVE CLOTHING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 2000000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To equip the personnel with working tools for work readiness |  |  | 1st Quarter 2: • Number of employees provided with protective clothing
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of employees provided with protective clothing |  |  |  | Dakwa/Pani | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of employees provided with protective clothing Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation committee Sitting of Bid Adjudication committee Appointment of Service Provider Issuance of Uniform to the employees |  |  | 3rd Quarter 1: 2000000 | 2000000 | Own Revenue
PROJECT NO. | 6.14
PROJECT NAME: | MULTI PURPOSE DOWZER
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 7000000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To improve the capacity of landfill sites |  |  | 1st Quarter 2: • Number of multi-purpose dowsers purchased
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of multi-purpose dowsers and TLB purchased |  |  |  | Dakwa | bar: 1st Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of multi-purpose dowsers purchased Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 1st Quarter 3: 7000000 | 7000000 | Own Revenue
PROJECT NO. | 6.15
PROJECT NAME: | ESTABLISHMENT OF NEW LANDFILL SITE
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 5000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide sufficient landfill space |  |  | 1st Quarter 2: Number of new landfill site established
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of new landfill site established |  |  |  | dakwa | bar: 1st Quarter 2; 2nd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of new landfill site established Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 4th Quarter 2: 5000000 | 5000000 | Own Revenue
PROJECT NO. | 6.16
PROJECT NAME: | PURCHASE OF REFUSE BAGS
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 1900000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To educate the employees and community about waste management and environmental sustainability |  |  | 1st Quarter 2: Number of workshops to be conducted
To ensure that there is constant supply of refuse bags |  |  | 1st Quarter 2: Number of refuse bags to be procured
To provide waste littering bins in towns and bus stops |  |  | 1st Quarter 2: Number of street litter bins to be procured
To monitor medical waste management practises from medical centres |  |  | 1st Quarter 2: Number of monitoring visits to general practitioners, hospitals
To measure waste disposal in our landfill sites for future planning |  |  | 1st Quarter 2: Number of loads to be disposed
To eradicate illegal dumping by providing lasting solutions |  |  | 1st Quarter 2: Number of illegal dumping site to be removed
To eradicate illegal dumping by providing lasting solutions |  |  | 1st Quarter 2: Number of times waste pickers are supported
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of workshops to be conducted • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Dakwa | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of refuse bags procured |  |  |  | Dakwa | 2nd Quarter 1: 225000; 4th Quarter 1: 225000
Number of skip bins procured |  |  |  | Dakwa | 3rd Quarter 2: 10
Number of monitoring visits to general practitioners, hospitals |  |  |  | Dakwa | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Number of loads to be disposed |  |  |  | Dakwa/Mdiya | 116 | 117 | 117 | 133 | 133 | 134 | 134 | 133 | 133 | 117 | 117 | 116
Number of illegal dumping site to be removed |  |  |  | Dakwa/Mdiya | 1 | 1 | 2 | 1 | 1 | 2 | 1 | 2 | 2 | 2 | 2 | 1
Number of times waste pickers are supported |  |  |  | Dakwa/Mdiya | bar: 2nd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of workshops to be conducted • Securing the venue • Writing and sending invitation letters • Arranging the logistics | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of refuse bags procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider |  |  | 2nd Quarter 1: 700000; 4th Quarter 1: 700000 | 1400000 | Equitable share
Number of skip bins and street litter bins to be procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider |  |  | 2nd Quarter 3: 500000 | 500000 | Equitable share
Number of monitoring visits to general practitioners, hospitals
Number of loads to be disposed |  |  | 2nd Quarter 1: 500000 | 500000 | Equitable share
Number of illegal dumping site to be removed
Number of times waste pickers are supported
PROJECT NO. | 6.17
PROJECT NAME: | CLEANING & GREENING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 1055000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide essential tools of trade |  |  | 1st Quarter 2: • Number of working tools to be procured
• To remove excess vegetation |  |  | 1st Quarter 2: • Number of bush and grass cutting activities per annum
Servicing of essential tools |  |  | 1st Quarter 2: Number of working tools serviced
To remove excess vegetation |  |  | 1st Quarter 2: Tree felling
To beautify both towns |  |  | 1st Quarter 2: Beuatification of Towns
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of working tools to be procured |  |  |  | Pani | bar: 2nd Quarter 1
Number of grass cutters to be procured |  |  |  | Pani/Kasana | bar: 1st Quarter 1
Number of machines to be serviced |  |  |  | Pani/Kasana | bar: 2nd Quarter 1; 3rd Quarter 3
Tree felling |  |  |  | Pani/Kasana | bar: 2nd Quarter 2
Beautification of towns |  |  |  | Pani/Kasana | bar: 1st Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of working tools to be procured |  |  | 2nd Quarter 1: 200000 | 200000 | Equitable Share
Number of grass cutters to be procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider |  |  | 1st Quarter 1: 65000 | 65000 | Equitable Share
Number of machines to be serviced |  |  | 2nd Quarter 3: 20000; 4th Quarter 2: 20000 | 40000 | Equitable Share
Tree felling |  |  | 2nd Quarter 2: 1200000 | 12000000 | Equitable Share
The beautification of towns |  |  | 1st Quarter 2: 300000 | 300000 | Equitable Share
PROJECT NO. | 6.18
PROJECT NAME: | PARKS, POUNDS & CEMETERIES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 79585
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To remove stray animals causing nuisance and damage on the public places |  |  | 1st Quarter 2: • Number of animals to be impounded
• To provide decent burial space |  |  | 1st Quarter 2: • Number of graves to be issued
To provide decent burial space |  |  | 1st Quarter 2: Cemetry layout
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of animal to be impounded |  |  |  | Pani/Kasana | 8 | 6 | 6 | 7 | 6 | 7 | 7 | 7 | 6 | 6 | 6 | 8
Number of graves to be issued |  |  |  | Pani/Kasana | 2 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | 2
Cemetry Layout |  |  |  | Pani/Kasana | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times of cutting grass and bushes Identification of area of operation Deployment of teams to specific area Grass cutting and buck clearing |  |  | 1st Quarter 1: 10; 2nd Quarter 1: 10; 3rd Quarter 1: 9,585 | 29,585 | Own Revenue
Number of animals to be impounded Street patrols by rangers Impoundment of stray animal Safe guarding of animals Release of animals paid for Auctiocation of burial space |  |  | 1st Quarter 2: 4000; 2nd Quarter 2: 2000; 3rd Quarter 2: 8000; 4th Quarter 2: 12000 | 26000 | Own Revenue
Number of graves to be issued Proccessing of grave acquisition Identification of burial space
Cemetry Layout |  |  | 3rd Quarter 1: 1000000 | 1000000 | Own Revenue
PROJECT NO. | 6.19
PROJECT NAME: | FENCING OF EXISITING MUNICIPAL CEMETERIES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2019-07-01
PROJECT COMPLETION DATE: | 2020-06-30
TOTAL APPROVED BUDGET: | 5000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To safeguard the municipal cemeteries |  |  | 1st Quarter 2: • Number of cemeteries fenced
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
• Drafting and submission of specification • Submission of pre-requisition • Sitting of Specification Committee • Sitting of Bid Evaluation Committee • Siting of Bid Adjudication Committee • Appointment of Service Provider • Fencing • Project hand over. |  |  |  | S. Dakwa | bar: 3rd Quarter 3 to 4th Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Fencing of cemeteries |  |  | 4th Quarter 2: 5000000 | 5000000 | Own Rev

## Milestones MM's Office
PRO+A2:T141JECT NAME: |  | Performance management system
INSTITUTION: |  | Ingquza Hill Local Municipality
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | 0
SOURCE OF FUNDING: |  | None
Project Objectives | [6 empty] | Project Key Performance Indicators
To promote good governance and public participation | [6 empty] | Number of reports reviewed
Number of reports tabled to the Council
[7 empty] | Responsible Official | Time Frames
Key Milestones | [7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Monthly review of reports by management
Submision of reports to Council | bar: 1st Quarter 1; 2nd Quarter 1; 2nd Quarter 3 to 3rd Quarter 1; 3rd Quarter 3 to 4th Quarter 1
Review of quarterly reports | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Projections per milestone | Budget Projections in multiples of R1000 (xR1000)
| 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1 | 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure
PROJECT NO.2
PROJECT NAME: |  | Intergrated Development Plan
INSTITUTION: |  | Ingquza Hill Local Municipality
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | Friday, June 30, 2023
TOTAL APPROVED BUDGET: |  | R 2 597, 788
SOURCE OF FUNDING: |  | Equitable Share |  |  |  |  | Project Key Performance Indicators
Project Objectives | [6 empty] | Number of IDP meeting held
To promote good governance and public participation | [6 empty] | Number of departmemental strategic plans held
Number of Council strategic planning held
[7 empty] | Responsible Official | 1st Quarter 1: Time Frames
Key Milestones | [7 empty] | 1st Quarter 1: 1st Quarter; 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
T. Dlungwana | bar: 1st Quarter 1 to 1st Quarter 2
Preparation and presentation of the IDP process plan 2021-2022 for Council notification and adoption | [6 empty] | T. Dlungwana | bar: 1st Quarter 3 to 2nd Quarter 1
Sitting of technical committiee and rep forum for Situational analysis | [6 empty] | T. Dlungwana | bar: 2nd Quarter 2 to 3rd Quarter 1
Sitting of technical committee and rep forum for Strategies and objectives | [6 empty] | T. Dlungwana | bar: 3rd Quarter 2
Sitting of technical committee and rep forum for Project identification | [6 empty] | T. Dlungwana | bar: 3rd Quarter 3
Presentation of draft IDP & Budget for Council notification and adoption | [6 empty] | T. Dlungwana | bar: 4th Quarter 1 to 4th Quarter 2
Sitting of technical committee & Rep Forum for Intergration & Budget | [6 empty] | T. Dlungwana | bar: 4th Quarter 2
Approval of IDP & Budget | [6 empty] | T. Dlungwana | bar: 2nd Quarter 2 to 2nd Quarter 3
Departmental strategic planning (in prep for main strat plan) | [6 empty] | T. Dlungwana | bar: 3rd Quarter 1 to 3rd Quarter 2
Council strategic planning (Vision, Mission, Strategic goals)
Projections per milestone | Budget Projections in multiples of R1000 (xR1000) | [5 empty] | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
| 1 | 2 | 3 | 1 | 2 | 3 |  | 1st Quarter 3: R 112 498; 3rd Quarter 1: R 112 498; 4th Quarter 2: R 449992
IDP Rep forums and technical committee |  |  | R 112 498 |  |  | R 112 498 |  | 4th Quarter 2: R 150 ,000
Departmental strategic planning |  |  |  |  | 150000 |  |  | 1st Quarter 2: R 1 927, 800; 4th Quarter 2: R 1 927,800
Council strategic planning
PROJECT NO 3
PROJECT NAME: |  | Intergovernmental Relations
INSTITUTION: |  | Ingquza Hill Local Municipality
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | R 69 996
SOURCE OF FUNDING: |  | Equitable Share |  |  |  |  | Project Key Performance Indicators
Project Objectives | [6 empty] | Number of meetings held with functional IGR structures
To promote good governance and public participation | [6 empty] | Number of war rooms held
[7 empty] | Responsible Official | 1st Quarter 1: Time Frames
Key Milestones | [7 empty] | 1st Quarter 1: 1st Quarter; 2nd Quarter 1: 2nd Quarter; 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
T. Dlungwana | bar: 1st Quarter 1
Development of IGR terms of reference and policy | [6 empty] | T. Dlungwana | bar: 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
IGR quarterly meetings | [6 empty] | T. Dlungwana | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
Social and economic cluster meetings | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Number of local war rooms held
Projections per milestone | Budget Projections in multiples of R1000 (xR1000) | [5 empty] | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 1st Quarter |  |  | 2nd Quarter |  |  | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
| 1 | 2 | 3 | 1 | 2 | 3 |  | 1st Quarter 3: 17499; 3rd Quarter 3: 17499; 4th Quarter 2: R69 996
PROJECT NAME: |  | Council Support
INSTITUION: |  | Ingquza Hill Local Municipality
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING: |  | Levies
Project Key Performance Indicators
To promote good governance and public participation | [6 empty] | Number of council calendar adopted
Number of council minutes prepared
Number of reports adopted
Number of council resolution registers compiled
Key Milestones | [6 empty] | Responsible Person | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Sitting of Council | [6 empty] | N. Mdiya
Sitting of Executive Committee | [6 empty] | L. Tshingana
Municipal Public Accounts Committee (MPAC) | [6 empty] | N. Mdiya | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Rules of Committee | [6 empty] | N. Mdiya | bar: 2nd Quarter 2; 4th Quarter 1
Ethics and Membeships Interest | [6 empty] | N. Mdiya | bar: 2nd Quarter 3; 4th Quarter 3
Multi-Party Womens Caucus | [6 empty] | N. Mdiya | bar: 1st Quarter 1; 3rd Quarter 1
Public Participation and Pettions Committee | [6 empty] | N. Mdiya | bar: 1st Quarter 1; 3rd Quarter 2
Sitting Section 80 Committee | [6 empty] | L. Tshingana | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Support to Traditional Leaders | [6 empty] | N.Mdiya
Taking Council to the People | [6 empty] | N. Mdiya | bar: 2nd Quarter 2
State of the Municipal Address | [6 empty] | N. Mdiya | bar: 4th Quarter 2
Translation of Quarterly Reports | [6 empty] | N.Mdiya | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Mpondo Revolt | [6 empty] | N. Mdiya | bar: 4th Quarter 3
IDP & Budget Roadshows | [6 empty] | N. Mdiya | bar: 4th Quarter 1
Exco Outreach Programme | [6 empty] | N. Mdiya | bar: 3rd Quarter 2
Awareness Campaign | [6 empty] | N. Mdiya | bar: 1st Quarter 2; 2nd Quarter 1; 3rd Quarter 2; 4th Quarter 2
Voter Education | [6 empty] | N. Mdiya | bar: 3rd Quarter 3; 4th Quarter 3
Moral Regeneration | [6 empty] | N. Mdiya | bar: 1st Quarter 2; 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: |  | SPECIAL PROGRAMMES
INSTITUTION: |  | Ingquza Hill Local Municipality
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET:
SOURCE OF FUNDING: |  | Levies
Project Objectives | [6 empty] | Project Key Performance Indicators
To promote integrated of designated groups (Children, Youth, Women, Disabled and older persons | [6 empty] | Quartely Targets
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Child Programmes (support to Destitute) | [6 empty] | Ms N Siphungela | bar: 3rd Quarter 1
Youth Programme : Mayoral Week | [6 empty] | Mr X.Vusiwe | bar: 4th Quarter 3
Youth Development: Miss Ingquza | [6 empty] | Ms N Siphungela | bar: 1st Quarter 3
Gender Development (Women's Month) | [6 empty] | Ms N Siphungela | bar: 1st Quarter 2
Elderly/ Veterans | [6 empty] | Ms N Siphungela | bar: 1st Quarter 2
Community Development/ Burial Support | [6 empty] | Ms N Siphungela
Community Initiative : OR Tambo Memorial Lecture | [6 empty] | Ms N Siphungela | bar: 2nd Quarter 1
Community Initiative : 16 Days of Activism | [6 empty] | Ms N Siphungela | bar: 2nd Quarter 2
Disability | [6 empty] | Ms N Siphungela | bar: 2nd Quarter 3
Youth Development: Support to Youth Council | [6 empty] | Mr. X. Vusiwe | bar: 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 1; 4th Quarter 3
Mandela Day | [6 empty] | Ms N Siphungela | bar: 1st Quarter 1
PROJECT NO. |  | 6.8
PROJECT NAME: |  | SPORT PROMOTION
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | 1420000
SOURCE OF FUNDING: |  | EQUITABLE SHARE
Project Objectives | [6 empty] | Project Key Performance Indicators
• To create promote stakeholders participation in sport decision making | [6 empty] | • Number of sport council meetings to be convened
• To promote sport participation | [6 empty] | • Number of sport events to be hosted
• To improve sport management | [6 empty] | • Number of federations , clubs and players to be assisted
To promote promotion | [6 empty] | Number of sport equipment procured
Key Milestones | [6 empty] | Responsible Official | 1st Quarter 1: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport council meetings to be convened • Securing the venue • Writing and sending invitation letters • Arranging the logistics | [6 empty] | Makhobongwana | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of sport events to be hosted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics | [6 empty] | Makhobongwana | bar: 2nd Quarter 1; 4th Quarter 1
Number of federations, clubs and players to be assisted | [6 empty] | Makhobongwana | bar: 1st Quarter 3; 2nd Quarter 3; 3rd Quarter 3; 4th Quarter 3
Number of times sport equipment is provided | [6 empty] | Makhobongwana | bar: 1st Quarter 3; 4th Quarter 1
Projections per milestone | [5 empty] | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
[6 empty] | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
[6 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport council meetings to be convened • Securing the venue • Writing and sending invitation letters • Arranging the logistics | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Number of sport events to be hosted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics | [5 empty] | 1st Quarter 3: 600000; 4th Quarter 2: 150000 | 750000 | Equitable Share
Number of federations, clubs and players to be assisted | [5 empty] | 1st Quarter 3: 142500; 2nd Quarter 3: 142500; 3rd Quarter 3: 142500; 4th Quarter 3: 142500 | 570000
Number of sport equipment procured | [5 empty] | 4th Quarter 1: 100000 | 100000 | Equitable Share
PROJECT NO. |  | 6.9
PROJECT NAME: |  | EARLY CHILDHOOD DEVELOPMENT
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | 200000
SOURCE OF FUNDING: |  | OWN REVENUE
Project Objectives | [5 empty] | 1st Quarter 2: Project Key Performance Indicators
• To promote early childhood development | [5 empty] | 1st Quarter 2: Number of times pre-school learning material procured
Key Milestones | [5 empty] | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times pre-school learning material procured | [6 empty] | Makhobongwana | bar: 3rd Quarter 2
Projections per milestone | [5 empty] | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
[6 empty] | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
[6 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times pre-school learning material to be procured Drafting and submission of specification Submission of pre-requisition sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of service provider Delivery of goods Handing over of goods | [5 empty] | 3rd Quarter 3: 200000 | 200000 | Equitable Share
PROJECT NO. |  | 6.1
PROJECT NAME: |  | ARTS & CULTURE PROMOTION
INSTITUION: |  | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: |  | 2022-07-01
PROJECT COMPLETION DATE: |  | 2023-06-30
TOTAL APPROVED BUDGET: |  | 690000
SOURCE OF FUNDING: |  | OWN REVENUE
Project Objectives | [5 empty] | 1st Quarter 2: Project Key Performance Indicators
• To promote arts and culture participation | [5 empty] | 1st Quarter 2: • Number of arts and culture activities or events to be supported
Key Milestones | [5 empty] | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[8 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[8 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of arts and culture activities or events to be supported • Securing the venue • Writing and sending invitation letters • Arranging the logistics | [6 empty] | Makhobongwana | 1st Quarter 3: 1; 2nd Quarter 2: 1; 3rd Quarter 3: 2; 4th Quarter 3: 1
Projections per milestone | [5 empty] | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
[6 empty] | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
[6 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of arts and culture activities or events to be supported • Securing the venue • Writing and sending invitation letters • Arranging the logistics | [5 empty] | 1st Quarter 3: 172500; 2nd Quarter 2: 172500; 3rd Quarter 3: 172500; 4th Quarter 3: 172500 | 690000 | Own Revenue

## Social Services
IDP NO. | KEY PERFORMANCE AREA | PROJECT | BASELINE | KEY PERFROMANCE INDICATOR | ANNUAL TARGET | QUARTERLY TARGETS | [11 empty] | TOTAL BUDGET
[6 empty] | Quarter |  | Means of Verification | Quarter 2 |  | Means of Verification | Quarter 3 |  | Means of Verification | Quarter |  | Means of Verification
[6 empty] | 1 | [8 empty] | 4
[6 empty] | tar | bud |  | tar | bud |  | tar | bud |  | tar | bud
OBJECTIVE: To provide an effective, efficient and sustainable community support service
6.1 | Social Services | Traffic control, law enforcement and support | The National Road Traffic Act 93 of 1996 requires that law transgressors should be fined accordingly. A total number of traffic fines was issued in 2021-22FY | 6.1.1. Number of traffic fines issued | 1600 | 500 | 0 | Traffic Fines Registers | 500 | 0 | Traffic Fines Registers | 300 | 0 | Traffic Fines Registers | 300 | 0 | Traffic Fines Registers | 0 | Traffic Fines Registers
6.1 | Social Services | Vehicle Registration & Licensing | The National Road Traffic Act 93 of 1996 requires that motor vehicle licences are renewed annually. A total of licences were issued in 2021-22 | 6.1.2. Number of motor vehicles licensed | 9500 | 2250 | 30000 | RD 329 Reports | 2700 | 0 | RD 329 Reports | 2300 | 30000 | RD 329 Reports | 2250 | 0 | RD 329 Reports | 60000 | RD 329 Reports
6.1 | Social Services | Learners licence examined | The National Road Traffic Act 93 of 1996 requires that motor vehicle licences are renewed annually. A total of learners licences were issued in 2021-22FY | 6.1.3. Number of learners licences examined | 3100 | 1000 | 0 | RD 329 Reports | 1500 | 0 | RD 329 Reports | 300 | 0 | RD 329 Reports | 300 | 0 | RD 329 Reports | 0 | RD 329 Reports
6.1 | Social Services | Vehicle Testing station | The National Road Traffic Act 93 of 1996 requires that VTS must have motorcycle kit. | 6.1.4. Number of motorcycle test kit procured. | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 30000 | Delivery note | 0 | 0 | N/A | 30000 | Delivery note
6.1 | Social Services | Procurement of Disaster material | Satellite office for OR Tambo is available in Lusikisiki and services both towns | 6.1.6. Number of times disaster relief items is procured | 1 | 0 | 0 | N/A | 1 | 0 | N/A | 1 | 400000 | Delivery note | 0 | 0 | N/A | 4000000 | Delivery note
6.1 | Social Services | Safeguarding of municipal assets | Security personnel posted at 6 access points (Lusikisiki municipal offices, DLTC, Two gates at Flagstaff new municipal offices, Two gates at Old municipal offices) | 6.1.7. Number of access points guarded | 6 | 6 | 0 | Duty rosters and Attendance Registres | 6 | 0 | Duty rosters and Attendance Registres | 6 | 0 | Duty rosters and Attendance Registres | 6 | 0 | Duty rosters and Attendance Registres | 0 | Duty rosters and Attendance Registres
6.1 | Social Services | Safeguarding of municipal assets | 6 access points in need of gun safes | 6.1.8. Number of gun safes procured | 4 | 0 | 0 | N/A | 0 | 0 | N/A | 0 |  | N/A | 4 | 40000 | Delivery note | 40000 | Delivery note
6.2. | Social Services | Support Community Police Forums (CPF) through CPF equipment and trainings | Two community polising forums supported | 6.2.2. Number of times CPF equipment is procured and distributed to CPFs | 2 | 0 | 0 | N/A | 1 | 50000 | Distribution register | 0 | 0 | N/A | 1 | 50000 | Distribution register | 100000 | Distribution register
6.2. | Social Services | Crime prevention awareness campaigns | High crime rate in the municipality. No synergy on the implementation of crime prevention initiatives by stakeholders | 6.2.4. Number of crime prevention awareness campaigns conducted | 4 | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 150000 | Attendance registers and report
6.2. | Social Services | Provision of stationery for public safety personnel | Public Safety and Traffic Officers require specific stationery items | 6.2.5. Number of times Public Safety personnel is provided with stationery | 2 | 0 | 0 | N/A | 1 | 150000 | Delivery note | 0 | 0 | N/A | 1 | 150000 | Delivery note | 300000 | Delivery note
6.2. | Social Services | Participation in LIASA events | High illiteracy rate in the municipality | 6.2.8. Number of LIASA events celebrated | 3 | 1 | 50000 | Attendance registers and report | 0 | 0 | N/A | 1 | 50000 | Attendance registers and report | 1 | 50000 | Attendance registers and report | 150000 | Attendance registers and report
6.2. | Social Services | Waste management education | There is one operating landfill site, and there is a waste management unit | 6.2.8. Number of waste management workshops conducted | 4 | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 1 | 37500 | Attendance registers and report | 150000 | Attendance registers and report
6.2. | Social Services | Provision of uniform & protective clothing | The nature of duty requires annual replacement of protective clothing and working tools | 6.2.9. Number of times employees provided with working tools and protective clothing | 1 | 0 | 0 | N/A | 0 | R0.00 | N/A | 0 | 0 | N/A | 1 | 2500000 | Delivery note and distribution register | 2500000 | Delivery note and distribution register
6.2. | Social Services | Access to library services | There are three libraries in the municipality that are servicing the community | 6.2.10. Number of patrons serviced at libraries | 7500 | 750 | 0 | Library registers | 750 | 0 | Library registers | 3000 | 0 | Library registers | 3000 | 0 | Library registers | R0.00 | Library registers
6.3 | Social Services | Contracting of 17 lifegaurds and 10 patrollers | Mbotyi, Msikaba and Mkhambathi beaches require the employment of lifeguards on a seasonal | 6.3.1. Number of times lifeguards are deployed | 1 | 0 | 0 | N/A | 1 | 1000000 | Employment Contracts | 0 | 0 | N/A | 0 | 0 | N/A | 1000000 | Employment contracts
6.3 | Social Services | Employment of EPWP casuals | The unemployment rate in the area is high | 6.3.2. Number of times Casual workers employed | 2 | 1 | 1000000 | Employment contracts | 0 | 0 | N/A | 1 | 1000000 | Employment contracts | 0 | 0 | N/A | 2000000 | Employment contracts
6.4 | Social Services | Payment of Driving Licence Cards | DLTC is operational. Monthly payments are made to DLCA.12 payments made in 2021-22 | 6.4.4. Number of payments done to DLCA | 12 | 3 | 95000 | Proof of payments/ invoice | 3 | 95000 | Proof of payments/ invoice | 3 | 95000 | Proof of payments/ invoice | 3 | 95000 | Proof of payments/ invoice | 380000 | Proof of payments/ invoice
6.5 | Social Services | CSF meetings | Community Safety Forum is a structure in place | 6.5.1. Number of CSF Meetings convened | 4 | 1 | 0 | Attendance Registers & minutes | 1 | 0 | Attendance Registers & minutes | 1 | 0 | Attendance Registers & minutes | 1 | 0 | Attendance Registers & minutes | 0 | Attendance Registers & minutes
6.4 | Social Services | Participation in district level LIASA events | District LIASA event occurs and requires participation of succeeded learners | 6.5.5 . Number of times local winners are transported to the District LIASA event | 3 | 1 | 50000 | Name list of transported winners | 0 | 0 | N/A | 1 | 50000 | Name list of transportated winners | 1 | 50000 | Name list of transported winners | 150000 | Name list of transported winners
6.6 | Basic Service Delivery | Procurement of grass cutting machines | Municipality has five working grass cutting machines and three non-working machines | 6.6.1.3. Number of grass cutting machines procured | 10 | 0 | 0 | N/A | 0 | 0 | N/A | 10 | 200000 | Delivery note | 0 | 0 | N/A | 200000 | Delivery note
6.6 | Basic Service Delivery | Procurement of refuse bags | 550 000 refuse bags procured in the previous FY | 6.6.3. Number of refuse bags procured | 1050000 | 400000 | 500000 | Delivery note | 0 | 0 | N/A | 0 | 0 | N/A | 650000 | 721673.18 | Delivery note | 122167318 | Delivery note
6.6 | Basic Service Delivery | Waste disposal | There is one operating landfill site, and there is a waste management unit | 6.6.6.Number of loads disposed | 1500 | 350 | 0 | Landfill register | 400 | 0 | Landfill register | 400 | 0 | Landfill register | 350 | 0 | Landfill register | 0 | Landfill register
6.6 | Basic Service Delivery | Removal of illegal dumping sites | High rate of illegal dumping site | 6.6.7. Number of illegal dumping sites to be removed | 18 | 4 | 0 | Pictures (before & after) | 4 | 0 | Pictures (before & after) | 5 | 0 | Pictures (before & after) | 5 | 0 | Pictures (before & after) | 0 | Pictures (before & after)
6.6 | Basic Service Delivery | Waste recycling | Two buy back centres are operating in Flagstaff and in Lusikisiki | 6.6.8. Number of tons of waste recycled | 400 | 100 | 0 | Analysis Report | 100 | 0 | Analysis Report | 100 | 0 | Analysis Report | 100 | 0 | Analysis Report | 0 | Analysis Report
6.6 | Basic Service Delivery | Reporting to SAWIS for waste generation by the Municipality | There is one operating landfill site, and there is a waste management unit | 6.6.9. Number of times tons of waste is reported to SAWIS | 4 | 1 | 0 | SAWIS submission screen | 1 | 0 | SAWIS submission screen | 1 | 0 | SAWIS submission screen | 1 | 0 | SAWIS submission screen | 0 | SAWIS submission screen
6.6 | Social Services | Overgrown vegetation clearing | Overgrown vegetation is removed quarterly to keep both towns clean and presentable | 6.6.10. Number of times of overgrown vegetation is removed | 30 | 6 | 10000 | Pictures (before & after) | 9 | 15000 | Pictures (before & after) | 9 | 15000 | Pictures (before & after) | 6 | 10000 | Pictures (before & after) | 50000 | Pictures (before & after)
6.6 | Social Services | Provision of Tree felling services for IHLM | Tree felling is done to remove aged, invasive and overgrown trees | 6.6.11 Number of times invasive trees are removed | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 750000 | Completion report | 0 | 0 | N/A | 750000 | Completion report
6.6 | Social Services | Impounding of stray animals | Stary animals in town and along the roads pose a danger and nuisance to the public | 6.6.12. Number of animals impounded | 80 | 20 | 18866 | Pounds Register | 20 | 18866 | Pounds Register | 20 | 18866 | Pounds Register | 20 | 18866 | Pounds Register | 75465 | Pounds Register
6.6 | Basic Service Delivery | Assistance of Waste Pickers through the provision of equipment and tools of trade | 52 waste pickers supported with wheely bins and identification clothing | 6.6.17. Number of times waste pickers are supported | 1 | 0 | 0 | N/A | 1 | 150000 | Delivery note | 0 | 0 | N/A | 0 | 0 | N/A | 150000 | Delivery note
6.6 | Social Services | Beautification of municipal premises through horticultural activities | There is a need to facelift the municipal premises | 6.6.18. Number of times flowers and plants are procured for beautification of towns | 2 | 0 | 0 | N/A | 1 | 250000 | Delivery note and photos | 0 | 0 | N/A | 1 | 250000 | Delivery note and photos | 500000 | Delivery note and photos
6.6 | Social Services | Procurement of chairs for 32 community halls | A number of the previously procured chairs have broken. There is a need for more chairs | 6.6.21. Number of chairs to be procured | 1800 | 0 | 0 | N/A | 800 | 800000 | Delivery Note | 1000 | 1000000 | Delivery Note | 0 | 0 | N/A | 1000000 | Delivery Note
6.6 | Basic Service Delivery | Procurement of wheely bins | Currently residents are supplied with refuse bags. The bins will replace the refuse bags. This proct will be piloted 100h/h in Lusikisiki ward 15 | 6.6.23. Number of wheely bins procured | 100 | 0 | 0 | N/A | 100 | 1000000 | Delivery Note | 100 | 1000000 | Delivery Note | 0 | 0 | N/A | 1000000 | Delivery Note
6.6 | Social Services | Traffic control, law enforcement and support | Poor signage and road markings, which makes it dificult to perform law enforcement duties | 6.6.24. Number of times road signs and paints are procured | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 750000 | Delivery note | 750000 | Delivery note
6.6 | Social Services | Renovation of two guardrooms (Flagstaff and Lusikisiki) | Security personnel require safe gaurdrooms | 6.6.25. Number of guardrooms to be renovated | 2 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 2 | 100000 | Completion certificate | 100000 | Completion certificate
6.6 | Social Services | Renovation of solid waste office | The current space used as the office for Solid Waste is dilapidated | 6.6.25. Number of times solid waste office is renovated | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 200000 | Completion certificate | 200000 | Completion certificate
6.6 | Social Services | Development of Integrated Community Safety Plan | High crime rate in the municipality. No synergy on the implementation of crime prevention initiatives by stakeholders | 6.6.26. Number of Integrated Community Safety Plan to be developed | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 400000 | Developed Community Safety Plan | 400000 | Developed Community Safety Plan
6.6 | Basic Service Delivery | Procurement of street litter bins and skip bins | There is one operating landfill site, and there is a waste management unit | 6.6.27. Number of times street litter and skip bins to be procured | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 500000 | Delivery note | 0 | 0 | N/A | 500000 | Delivery note
6.6 | Social Services | Provision of protective gear for employees | Solid Waste, Traffic Officers and Security Officers in need of protective gear to perform duties | 6.6.30. Number of times protective gear is procured | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 65000 | Delivery note | 0 | 0 | N/A | 65000 | Delivery note
6.6 | Social Services | Construction of guardrooms in the Flagstaff and Lusikisiki Pound | There is no gaurdroom at the pounds | 6.6.31. Number of guardrooms to be constructed for the pounds | 2 | 0 | 0 | N/A | 0 | 0 | N/A | 2 | 600000 | Completion certificates | 0 | 0 | N/A | 600000 | Completion certificates
6.6 | Basic Service Delivery | Provision of grass cutting machines | Limited resources for grass cutting. | 6.6.32. Number of lawn mowers procured | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 30000 | Delivery note | 30000 | Delivery note
6.6 | Social Services | Promotion of sports through sports events | There is a sports council in the municipality | 6.7.1. Number of sports events hosted | 2 | 1 | 600000 | Attendance register and report | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 150000 | Attendance register and report | 750000 | Attendance register and report
6.6 | Social Services | Assistance of federations and players | There is a sports council in the municipality | 6.7.2. Number of federations assisted | 5 | 1 | 142500 | Register for the list of federations assisted and request letter for assistance | 1 | 142500 | Register for the list of federations assisted and request letter for assistance | 1 | 142500 | Register for the list of federations assisted and request letter for assistance | 2 | 142500 | Register for the list of federations assisted and request letter for assistance | 570000 | Register for the list of federations assisted and request letter for assistance
6.6 | Social Services | Support of Arts and Culture groups and events | There is an Arts Council and an Initiation Forum | 6.7.3. Number of arts and culture groups and events supported | 4 | 1 | 172500 | Attendance register and report and request letter for assistance | 1 | 172500 | Attendance register and report and request letter for assistance | 1 | 172500 | Attendance register and report and request letter for assistance | 1 | 172500 | Attendance register and report and request letter for assistance | 690000 | Attendance register and report and request letter for assistance
6.2. | Social Services | Provision of Early Childhood Development learning material | Five Early Childhood Development centres supported in previous FY | 6.7.5. Number of Early Childhood Development centres supported with learning material | 6 | 0 | 0 | N/A | 0 | 0 | N/A | 6 | 200000 | Distribution register | 0 | 0 | N/A | 109150 | Distribution register
6.2. | Social Services | Provision of security services for land invasion cases | High level of land invasion | 6.7.6. Number of times service provider for security services for land invasion cases are appointed | 1 | 0 | 0 | N/A | 0 | 0 | N/A | 1 | 500000 | Appointment letter | 0 | 0 | Appointment letter | 500000 | Appointment letter
6.2. | Social Services | Fencing of Pounds in Flagstaff and Lusikisiki | Debilitated fencing at the pounds | 6.7.7. Number of pounds to be fenced | 2 | 0 | R0.00 | N/A | 0 | R0.00 | N/A | 0 | 0 | N/A | 2 | 1750000 | Completion certificate | R1 750 000.00 | Completion certificate

## Milestones Social Services
PROJECT NO. | 6.1
PROJECT NAME: | TRAFFIC LAW ENFORCEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Traffic fines
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  |  | Project Key Performance Indicators
•To enforce compliance with road traffic regulations |  |  |  | • Number of traffic fines issued
Key Milestones |  |  |  | Responsible Official | Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of traffic fines issued |  |  |  | Vato (CTO) | 200 | 250 | 250 | 210 | 300 | 340 | 280 | 250 | 220 | 250 | 240 | 190
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of traffic fines issued Setting of Duty Rosters Traffic Safety Patrols Issuing of traffic fines |  |  | 1st Quarter 3: 750; 2nd Quarter 3: 750; 3rd Quarter 3: 750; 4th Quarter 3: 750 | 3000 | Own revenue
PROJECT NAME: | REGISTRATION & LICENSING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Licensing of Motor Vehicles
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 60000
SOURCE OF FUNDING: | eNatis Agency Fees
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To provide effective traffic support service for motor vehicle licensing |  |  | 1st Quarter 2: Number of motor vehicles to be licensed
To comply with requirements for operating a DLTC |  | ing of DLTC | 1st Quarter 2: Number of driving licences applications administered
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of motor vehicles to be licensed Provision of application forms Distribution of face value documents Conducting of licensing transations |  |  |  | Mbola | 1st Quarter 3: 2250; 2nd Quarter 3: 2700; 3rd Quarter 3: 2300; 4th Quarter 3: 2250
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of vehicles to licensed |  |  | 1st Quarter 3: 30,000; 3rd Quarter 2: 30,000 | 60,000 | eNatis Agency Fees
PROJECT NAME: | REGISTRATION & LICENSING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Learners Licenses
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To provide unlicenced people with oppoturnity to possess leaners licence |  |  | 1st Quarter 2: Number of learners licence application administered
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Learners licence applications |  |  |  | Mbola | 1st Quarter 3: 1000; 2nd Quarter 3: 1500; 3rd Quarter 3: 1000; 4th Quarter 3: 1000
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of learners licence examined
PROJECT NAME: | DISASTER RISK MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of Disaster Relief Material
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 4000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide relief to disaster victims |  |  | 1st Quarter 2: • Number of times for acquisition of disaster relief items
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Procurement of disaster relief tools |  |  |  | Macanikwa | bar: 2nd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
To provide relief Drafting and submission of specification Submission of pre-requisition Sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjutication Committee Appointment of service provider Delivery of Goods Issuing of relief |  |  | 2nd Quarter 1: 4000000 | 4000000 | Own Revenue
PROJECT NO. | 6.6
PROJECT NAME: | CRIME PREVENTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To safeguard municipal property and employees |  |  | 1st Quarter 2: • Number of access points guarded
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of access points guarded • Drafting duty roosters • Signing of duty roosters • Monitoring of attendance and work performance |  |  |  | M. Njisane | 6 | 6 | 6 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Safeguarding of municipal premises | [15 empty] | Own revenue
PROJECT NAME: | CRIME PREVENTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 100000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To provide support to Community Policing Forums/ Village committees |  |  | 1st Quarter 2: Number of CPFs Equipment supported
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of CPFs Equipment procured • Drafting and submission of specification • Submission of pre-requisition • Sitting of Specification Committee • Sitting of Bid Evaluation Committee • Siting of Bid Adjudication Committee • Appointment of Service Provider • Delivery of goods |  |  |  | M. Njisane | bar: 2nd Quarter 2; 4th Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
CPF Support |  |  | 2nd Quarter 2: 50000; 4th Quarter 2: 50000 | 100000 | Own revenue
PROJECT NAME: | CRIME PREVENTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 150000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To create awareness about crime trends and patterns |  |  | 1st Quarter 2: • Number of awareness campaigns conducted
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of awareness campaigns to be conducted • Securing the venue • Sending of invitation letters • Arranging the logistics |  |  |  | M. Njisane | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Crime Prevention Awareness Campaigns |  |  | 1st Quarter 2: 37500; 2nd Quarter 2: 37500; 3rd Quarter 2: 37500; 4th Quarter 2: 37500 | 150000 | Own revenue
PROJECT NAME: | PUBLIC SAFETY STATIONERY
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of stationery
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To enhance municipal revenue through traffic fines |  |  | 1st Quarter 2: Number of Books and printing publications
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of time books are procured |  |  |  | Vato (CTO) | bar: 2nd Quarter 1; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times stationery is procured |  |  | 2nd Quarter 1: 150000; 4th Quarter 1: 150000 | 300000 | Own revenue
PROJECT NAME: | LIBRARY SERVICES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | LIASA calender events
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-07-30
TOTAL APPROVED BUDGET: | 150000
SOURCE OF FUNDING: | LIBRARY SERVICES CONDITIONAL GRANT
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To promote participation on national events |  |  | 1st Quarter 2: • Number of LIASA calender events to be celebrated
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of LIASA calender events to be conducted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  |  | Nqalo | bar: 1st Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of LIASA calender events to be conducted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  | 1st Quarter 2: 50000; 3rd Quarter 2: 50000; 4th Quarter 2: 50000 | 150000 | Condtional grant
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Waste Management Workshop
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 150000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To educate the employees and community about waste management and environmental sustainability |  |  | 1st Quarter 2: Number of workshops to be conducted
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of workshops to be conducted • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Dakwa | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of workshops to be conducted • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  | 1st Quarter 1: 37500; 2nd Quarter 1: 37500; 3rd Quarter 1: 37500; 4th Quarter 1: 37500 | 150000 | Own revenue
PROJECT NAME: | PROTECTIVE CLOTHING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM:
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 2500000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To equip the personnel with working uniform for work readiness |  |  | 1st Quarter 2: • Number of employees provided with protective clothing
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of employees provided with protective clothing |  |  |  | Dakwa/Pani | bar: 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of employees provided with protective clothing Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation committee Sitting of Bid Adjudication committee Appointment of Service Provider Issuance of Uniform to the employees |  |  | 4th Quarter 1: 2500000 | 2500000 | Equitable share
PROJECT NAME: | LIBRARY SERVICES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Patrons Serviced
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-07-30
TOTAL APPROVED BUDGET: | 140000
SOURCE OF FUNDING: | LIBRARY SERVICES CONDITIONAL GRANT
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide effective library service delivery |  |  | 1st Quarter 2: • Number of patrons visiting libraries
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of patrons visiting libraries |  |  |  | Nqalo | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250 | 250
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of patrons visiting libraries | [15 empty] | Conditional Grant
PROJECT NAME: | Beach Management
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Employment of Lifeguards and Coastal Patrollers
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide safe beach environment for all |  |  | 1st Quarter 2: • Number of times Lifeguards and Coastal Patrollers employed
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times beach patrollers and lifeguards employed |  |  |  | Macanikwa | bar: 2nd Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times beach patrollers and lifeguards employed Arrange logistics |  |  | 2nd Quarter 1: 1000000 | 1000000 | Equitable Share
PROJECT NAME: | EPWP EMPLOYMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Employment of casual workers
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 2000000
SOURCE OF FUNDING: | EPWP Grant
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide employment on a casual basis |  |  | 1st Quarter 2: • Number of times casual workers employed
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times casual workers employed |  |  |  | Pani | bar: 1st Quarter 1; 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times casual workers employed |  |  | 1st Quarter 1: 1000000; 3rd Quarter 1: 1000000 | 2000000 | EPWP Grant
PROJECT NAME: | REGISTRATION & LICENSING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Driving license cards
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 6559080
SOURCE OF FUNDING: | eNatis Agency Fees
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
Payment of driving licence cads orderd from DLCA |  |  | 1st Quarter 2: Number of invoices for driving cards paid
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Learners licence applications |  |  |  | Mbola | 331 | 333 | 336 | 480 | 480 | 540 | 540 | 480 | 337 | 330 | 334 | 336
Number of Driving Licence applications |  |  |  | Mbola | 150 | 160 | 190 | 220 | 2400 | 340 | 300 | 335 | 365 | 350 | 380 | 370
Number of invoices for driving licences paid |  |  |  | Mbola | bar: 1st Quarter 1 to 4th Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of invoices for driving licences paid |  |  | 1st Quarter 3: 95000; 2nd Quarter 3: 95000; 3rd Quarter 3: 95000; 4th Quarter 3: 95000 | 380000 | eNatis Agency Fees
PROJECT NAME: | LIBRARY SERVICES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Transportation of local winners
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-07-30
TOTAL APPROVED BUDGET: | 150000
SOURCE OF FUNDING: | LIBRARY SERVICES CONDITIONAL GRANT
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To create awareness on library usage |  |  | 1st Quarter 2: • Number of outreach programmes to be conducted
• To promote participation on national events |  |  | 1st Quarter 2: • Number of LIASA calender events to be celebrated
• To provide effective library service delivery |  |  | 1st Quarter 2: • Number of patrons visiting libraries
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Transportation of local winners |  |  |  | Nqalo | bar: 1st Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times of transportation local winners Submission of pre-requisition Issuing of an order Arrange the logistics |  |  | 1st Quarter 2: 50000; 3rd Quarter 2: 50000; 4th Quarter 2: 50000 | 150000 | Own Revenue
PROJECT NAME: | CCTV Cameras
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of CCT V Cameras
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To improve vigilance in our structures |  |  | 1st Quarter 2: • Number of CCTV Cameras procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of CCTV procured |  |  |  | Dakwa | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of installation of CCTV cameras are procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 3rd Quarter 1: 300000 | 300000 | Equitable share
PROJECT NAME: | EXCAVATOR
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of Excavator
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 4000000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To improve the capacity of landfill sites |  |  | 1st Quarter 2: • Number of excavators procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Excavators procured |  |  |  | Dakwa | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Excavators to be procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 3rd Quarter 1: 4000000 | 4000000 | Equitable share
PROJECT NAME: | Grass Cutting Machines
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of grass cutting machines
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 200000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To improve the removal of grass within CBDs |  |  | 1st Quarter 2: • Number of grass cutting machines procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Grass Cutting Machines procured |  |  |  | Dakwa | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Grass Cutting Machines procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 3rd Quarter 1: 200000 | 200000 | Equitable share
PROJECT NAME: | PURCHASE OF REFUSE BAGS
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of refuse bags
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 580000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To ensure that there is constant supply of refuse bags |  |  | 1st Quarter 2: Number of refuse bags to be procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of refuse bags procured |  |  |  | Dakwa | 2nd Quarter 1: 500000; 4th Quarter 1: 500000
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of refuse bags procured Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider |  |  | 2nd Quarter 1: 500000; 4th Quarter 1: 500000 | 1000000 | Own revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Monitoring to practitioners and hospitals
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To monitor medical waste management practises from medical centres |  |  | 1st Quarter 2: Number of monitoring visits to general practitioners, hospitals
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of monitoring visits to general practitioners, hospitals |  |  |  | Dakwa | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of monitoring visits to general practitioners, hospitals
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Disposing of loads
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To eradicate illegal dumping by providing lasting solutions |  |  | 1st Quarter 2: Number of illegal dumping site to be removed
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of loads to be disposed |  |  |  | Dakwa/Mdiya | 1st Quarter 1: 350; 2nd Quarter 1: 400; 3rd Quarter 1: 400; 4th Quarter 1: 350
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of loads to be disposed
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Removal of illegal dumoing sites
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To eradicate illegal dumping by providing lasting solutions |  |  | 1st Quarter 2: Number of illegal dumping site to be removed
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of illegal dumping site to be removed |  |  |  | Dakwa | 1st Quarter 1: 4; 2nd Quarter 1: 4; 3rd Quarter 1: 4; 4th Quarter 1: 4
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of illegal dumping site to be removed
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Tons of waste recycled
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To minimise waste into tons |  |  | 1st Quarter 2: Number of tons of waste recycled
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of tons of waste recycled |  |  |  | Dakwa | 1st Quarter 1: 100; 2nd Quarter 1: 100; 3rd Quarter 1: 100; 4th Quarter 1: 100
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of tons of waste recycled
PROJECT NAME: | CLEANING & GREENING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Removal of excess vegetation
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 50000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To remove excess vegetation |  |  | 1st Quarter 2: • Number of bush and grass cutting activities per annum
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of bush and grass cutting activities per annum |  |  |  | Pani | 1st Quarter 1: 6; 2nd Quarter 1: 9; 3rd Quarter 1: 9; 4th Quarter 1: 6
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of bush and grass cutting activities per annum |  |  | 1st Quarter 1: 10000; 2nd Quarter 1: 15000; 3rd Quarter 1: 15000; 4th Quarter 1: 10000 | 50000 | Own revenue
PROJECT NAME: | CLEANING & GREENING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Tree felling services
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 750000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
To provide tree felling services |  |  | 1st Quarter 2: Number of times invasive trees are removed
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times invasive trees are removed |  |  |  | Pani/Kasana | bar: 3rd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Tree felling |  |  | 3rd Quarter 1: 750000 | 750000 | Own revenue
PROJECT NAME: | POUNDS & CEMETERIES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Animals impounded
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 75465
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To remove stray animals causing nuisance and damage on the public places |  |  | 1st Quarter 2: • Number of animals to be impounded
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of animal to be impounded |  |  |  | Pani | 1st Quarter 1: 20; 2nd Quarter 1: 20; 3rd Quarter 1: 20; 4th Quarter 1: 20
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of animals to be impounded Street patrols by rangers Impoundment of stray animal Safe guarding of animals Release of animals paid for Auctiocation of burial space |  |  | 1st Quarter 1: 18866; 2nd Quarter 1: 18866; 3rd Quarter 1: 18866; 4th Quarter 1: 18866 | 75465 | Own Revenue
PROJECT NAME: | CLEANING & GREENING
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Beautification
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To beautify towns |  |  | 1st Quarter 2: • Number of times tree felling is procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times tree felling is procured |  |  |  | Pani/Kasana | bar: 2nd Quarter 1; 4th Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times tree felling is procured |  |  | 2nd Quarter 1: 250000; 4th Quarter 1: 250000 | 500000 | Own revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Support for waste pickers
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 250000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide support for waste pickers |  |  | 1st Quarter 2: • Number of times waste pickers are supported
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times waste pickers are supported |  |  |  | Pani | bar: 2nd Quarter 1
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times waste pickers are supported |  |  | 2nd Quarter 1: 250000 | 250000 | Own revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Environmental Impact Assessment
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide safe landfill sites |  |  | 1st Quarter 2: • Number of Environmental Impact Assessment conducted
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Environmental Impact Assessment conducted |  |  |  | Pani/Kasana | bar: 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of Environmental Impact Assessment conducted |  |  | 3rd Quarter 3: 1000000 | 1000000 | Own revenue
PROJECT NAME: | COMMUNITY SERVICES CHAIRS
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of chairs for community halls
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide chairs for Community Halls |  |  | 1st Quarter 2: • Number of chairs to be procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of chairs to be procured |  |  |  | Pani | 2nd Quarter 3: 800
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of chairs to be procured |  |  | 3rd Quarter 3: 1000000 | 1000000 | Equitable Share
PROJECT NAME: | POUNDS & CEMETERIES
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of Cemetery layout
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1500000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide decent burial space |  |  | 1st Quarter 2: • Number of cemetery layout procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of cemetery layouts procured |  |  |  | Pani | bar: 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of cemetery layouts procured |  |  | 3rd Quarter 3: 1500000 | 1500000 | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of wheelie bins
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1000000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To create a cleanliness environment |  |  | 1st Quarter 2: • Number of wheelie bins procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of wheelie bins procured |  |  |  | Pani | 2nd Quarter 3: 100
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of wheelie bins procured |  |  | 3rd Quarter 3: 1000000 | 1000000 | Own Revenue
PROJECT NAME: | Traffic services
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Road signs and markings
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 750000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide road signs and markings |  |  | 1st Quarter 2: • Number of times road signs and markings procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times road signs and markings procured |  |  |  | Pani | bar: 4th Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times road signs and markings procured | [14 empty] | 750000 | Own Revenue | bar: 4th Quarter 3
PROJECT NAME: | CRIME PREVENTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of guardrooms
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 100000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide conducive environment for security officers |  |  | 1st Quarter 2: • Number of guardrooms renovated
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times guardroms are renovated |  |  |  | Pani | 3rd Quarter 3: 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times guardroms are renovated |  |  | 3rd Quarter 3: 100000 | 100000 | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of solid waste office
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 1662624
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To remove stray animals causing nuisance and damage on the public places |  |  | 1st Quarter 2: • Number of animals to be impounded
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of animal to be impounded |  |  |  | Pani/Kasana
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times of times wet fuel is procured Identification of area of operation Deployment of teams to specific area Grass cutting and buck clearing | [15 empty] | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Skip bins and street litter bins
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide cleanliness in both towns |  |  | 1st Quarter 2: Number of skip bins and street litter bins to be procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of new landfill site established |  |  |  | dakwa | bar: 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of skip bins and street litter bins procured |  |  | 3rd Quarter 3: 500000 | 500000 | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Buy back centres
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide cleanliness in both towns |  |  | 1st Quarter 2: Percentage completion of the storage facility at Flagstaff buy back centre
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Percentange completion of the stoarage facility at Flagstaff buy back centre |  |  |  | dakwa | 3rd Quarter 2: 75%; 4th Quarter 3: 100%
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Percentange completion of the stoarage facility at Flagstaff buy back centre |  |  | 3rd Quarter 3: 250000; 4th Quarter 3: 250000 | 500000 | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of one backie for solid waste management unit
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide cleanliness for both towns |  |  | 1st Quarter 2: number of vehicles to be procured for waste management unit
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of vehicles to be procured for waste management unit |  |  |  | dakwa | bar: 2nd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of vehicles to be procured for waste management unit |  |  | 2nd Quarter 3: 600000 | 600000 | Own Revenue
PROJECT NAME: | SOLID WASTE MANAGEMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Protective gear procurement
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 65000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To provide cleanliness to both towns |  |  | 1st Quarter 2: Number of times protective gear is procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times protective gear is procured |  |  |  | dakwa | bar: 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times protective gear is procured |  |  | 3rd Quarter 3: 65000 | 65000 | Own Revenue
PROJECT NAME: | Pound and Cemeteries
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Number of guardrooms to be constructed for pounds
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To keep stray animals away from the CBDs |  |  | 1st Quarter 2: Number of times guardrooms to be procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times guardroom to be procured |  |  |  | dakwa | 3rd Quarter 3: 2
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times guardroom to be procured |  |  | 3rd Quarter 3: 600000 | 600000 | Own Revenue
PROJECT NAME: | Cleaning and Greening
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of lawn mower
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 30000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To promote cleanliness for both towns |  |  | 1st Quarter 2: Number of lawn mower to be procured
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of lawn mower to be procured |  |  |  | dakwa | bar: 3rd Quarter 3
Projections per milestone |  |  | Budget Projections in multiples of R1000 (xR1000) |  | 4th Quarter 3: Source of Finance
|  |  | 1st Quarter |  | 1st Quarter 2: 2nd Quarter; 2nd Quarter 2: 3rd Quarter; 3rd Quarter 2: 4th Quarter; 4th Quarter 2: Total
|  |  | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of new landfill site established Drafting and submission of specification Submission of pre-requisition Sitting of specification committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of sevice provider Delivery of goods by the service provider Facilitation of payment |  |  | 3rd Quarter 3: 30000 | 30000 | Own Revenue
PROJECT NAME: | SPORT PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Sport Council meetings convened
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 0
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  | 1st Quarter 2: Project Key Performance Indicators
• To promote stakeholders participation in sport decision making |  |  | 1st Quarter 2: • Number of sport council meetings to be convened
Key Milestones |  |  | 1st Quarter 2: Responsible Official; 1st Quarter 3: Time Frames/Budget
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport council meetings to be convened • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Makhobongwana | bar: 1st Quarter 1; 2nd Quarter 1; 3rd Quarter 1; 4th Quarter 1
PROJECT NAME: | SPORT PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Sport events to be hosted
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 750000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  |  | Project Key Performance Indicators
• To promote sport participation |  |  |  | • Number of sport events to be hosted
Key Milestones |  |  |  | Responsible Official | 1st Quarter 1: Time Frames/Budget
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of sport events to be hosted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  |  | Makhobongwana | 2nd Quarter 1: 600000; 4th Quarter 1: 150000
PROJECT NAME: | SPORT PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Federations to be assisted
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 570000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  |  | Project Key Performance Indicators
To improve sport management |  |  |  | • Number of federations to be assisted
Key Milestones |  |  |  | Responsible Official | 1st Quarter 1: Time Frames/Budget
[5 empty] | b |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of federations to be assisted • Securing the venue • Writing and sending of invitation letters • Arranging the logistics |  |  |  | Makhobongwana | b 3: 142500; 2nd Quarter 3: 142500; 3rd Quarter 3: 142500; 4th Quarter 3: 142500
PROJECT NAME: | SPORT PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of sport equipment
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 100000
SOURCE OF FUNDING: | EQUITABLE SHARE
Project Objectives |  |  |  | Project Key Performance Indicators
To improve sport management |  |  |  | • Number of federations to be assisted
Key Milestones |  |  |  | Responsible Official | b 1: Time Frames/ Budget
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times sport equipment is procured Draft and submission of pre-requisition Draft and submission of specification Sitting of specificaion committee |  |  |  | Makhobongwana | 4th Quarter 1: 100000
PROJECT NO. | 6.9
PROJECT NAME: | EARLY CHILDHOOD DEVELOPMENT
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Procurement of pre-school material
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 102300
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  |  | Project Key Performance Indicators
• To promote early childhood development |  |  |  | Number of times pre-school learning material is procured
Key Milestones |  |  |  | Responsible Official | 1st Quarter 1: Time Frames/ Budget
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of times pre-school learning material is procured Drafting and submission of specification Submission of pre-requisition sitting of specification Committee Sitting of Bid Evaluation Committee Sitting of Bid Adjudication Committee Appointment of service provider Delivery of goods Handing over of goods |  |  |  | Makhobongwana | 3rd Quarter 1: 102300
PROJECT NO. | 6.1
PROJECT NAME: | ARTS & CULTURE PROMOTION
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Arts and culture activities or events supported
PROJECT START DATE: | 2022-07-01
PROJECT COMPLETION DATE: | 2023-06-30
TOTAL APPROVED BUDGET: | 690000
SOURCE OF FUNDING: | OWN REVENUE
Project Objectives |  |  |  | Project Key Performance Indicators
• To promote arts and culture participation |  |  |  | • Number of arts and culture activities or events to be supported
Key Milestones |  |  |  | Responsible Official | 1st Quarter 1: Time Frames/ Budget
[5 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[5 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
Number of arts and culture activities or events to be supported • Securing the venue • Writing and sending invitation letters • Arranging the logistics |  |  |  | Makhobongwana | 1st Quarter 3: 172500; 2nd Quarter 3: 172500; 3rd Quarter 3: 172500; 4th Quarter 3: 172500

## Quarterly Projections
Quarter | OPEX | CAPEX | TOTAL (OPEX & CAPEX) | REVENUE
Technical Services
1
2
3
4
SUB TOTAL
Corporate Services
1
2
3
4
SUB TOTAL
Planning & Development
1
2
3
4
SUB TOTAL
Budget & Treasury
1
2
3
4
SUB TOTAL
MM's Office
1
2
3
4
SUB TOTAL
Community Services
1 | 1695000 | 0 | 1695000 | 48866
2 | 4468866 | 1750000 | 6218866 | 18866
3 | 2445000 | 8780000 | 17225000 | 48866
4 | 6695000 | 850000 | 7545000 | 18866
SUB TOTAL | 15303866 | 11380000 | 32683866 | 135464
TOTAL

## Tech milestones (hidden)
MILESTONES
1.1.1.1
PROJECT NAME: | Construction of Lower Luqumbini Access Roas at Ward 3
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Lower Luqumbini Access Roas at Ward 3
PROJECT START DATE: | 2018-12-01
PROJECT COMPLETION DATE: | 2019-09-06
TOTAL APPROVED BUDGET: | 1045876.98
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Lower Luqumbini | [7 empty] | · Operational Road
· To create short term job opportunities | [7 empty] | · EPWP report
Key Milestones | [5 empty] | Responsible Official | Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Wearing Course Testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Practical Completion Walkover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close - out | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 400000 | 400000 | 0 | 0 | 0 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 0; 2nd Quarter 2: 245876.98; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 1045876.98; 4th Quarter 3: MIG
1.1.1.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Mcwabantsasa Access Roas at Ward 14
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Mcwabantsasa Access Roas at Ward 14
PROJECT START DATE: | 2018-12-01
PROJECT COMPLETION DATE: | 2019-09-06
TOTAL APPROVED BUDGET: | 1045876.98
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mcwabantsasa | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Wearing Course Testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Practical Completion Walkover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close - out | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 400000 | 0 | 0 | 0 | 0 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 324371.98; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 724371.98; 4th Quarter 3: MIG
1.1.1.3 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Tyhuphu Access Roas at Ward 22
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Tyhupu Access Roas at Ward 22
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-09-30
TOTAL APPROVED BUDGET: | 7700000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Tyhupu | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 150000 | 0 | 740000 | 1000000 | 210000 | 1st Quarter 1: 900000; 1st Quarter 3: 1000000; 2nd Quarter 2: 700000; 3rd Quarter 1: 1500000; 3rd Quarter 3: 1500000; 4th Quarter 2: 7700000; 4th Quarter 3: MIG
1.1.1.4 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Ntsimbini Access Roas at Ward 6
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Ntsimbini Access Roas at Ward 6
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-06-26
TOTAL APPROVED BUDGET: | 6116677.32
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Ntsimbini | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Wearing Course Testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
· Practical Completion Walkover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 150000 | 0 | 591457 | 1000000 | 868543 | 1st Quarter 1: 500000; 1st Quarter 3: 500000; 2nd Quarter 2: 1000000; 3rd Quarter 1: 506677.32; 3rd Quarter 3: 1000000; 4th Quarter 2: 6116677.32; 4th Quarter 3: MIG
1.1.1.5 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Jaca to Qojana Access Roas at Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Jaca to Qojana Access Roas at Ward 30
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-09-30
TOTAL APPROVED BUDGET: | 6142207
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Jaca and Qojana | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 190000 | 0 | 0 | 500000 | 385452 | 1st Quarter 1: 1000000; 1st Quarter 3: 1000000; 2nd Quarter 2: 1000000; 3rd Quarter 1: 1066755; 3rd Quarter 3: 1000000; 4th Quarter 2: 6142207; 4th Quarter 3: MIG
1.1.1.6 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Mbudu Access Roas at Ward 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Mbudu Access Roas at Ward 19
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-09-30
TOTAL APPROVED BUDGET: | 6287641.81
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mbudu | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Installation of pipe culverts | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 190000 | 0 | 432789 | 0 | 1000000 | 1st Quarter 1: 498379.25; 1st Quarter 3: 1000000; 2nd Quarter 2: 1000000; 3rd Quarter 1: 1166473.56; 3rd Quarter 3: 1000000; 4th Quarter 2: 6287641.81; 4th Quarter 3: MIG
1.1.1.7 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Emafusi Access Roas at Ward 26
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Emafusini Access Roas at Ward 26
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-06-26
TOTAL APPROVED BUDGET: | 5909495.5
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Emafusini | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Wearing Course Testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
· Practical Completion Walkover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 150000 | 500000 | 836080.45 | 500000 | 1000000 | 1st Quarter 1: 900000; 1st Quarter 3: 307363.5; 2nd Quarter 2: 1000000; 3rd Quarter 1: 0; 3rd Quarter 3: 716051.55; 4th Quarter 2: 5909495.5; 4th Quarter 3: MIG
1.1.1.8 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Kugqweza Access Roas at Ward 29
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Kugqweza Access Roas at Ward 29
PROJECT START DATE: | 2019-11-01
PROJECT COMPLETION DATE: | 2020-09-30
TOTAL APPROVED BUDGET: | 6650000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Kugqweza | [6 empty] | 1st Quarter 2: · Operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Roadbed Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Testing of roadbed | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Installation of pipe culverts | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Hauling and Tipping | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Processing of gravel material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 150000 | 0 | 1000000 | 1027426.68 | 1000000 | 1st Quarter 1: 180755.25; 1st Quarter 3: 1000000; 2nd Quarter 2: 500000; 3rd Quarter 1: 791818.07; 3rd Quarter 3: 1000000; 4th Quarter 2: 6650000; 4th Quarter 3: MIG
1.1.1.9 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Malola Access Roas at Ward 25
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Malola Access Roas at Ward 25
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Malola | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.1.10 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Mdiya Access Roas at Ward 16
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Mdiya Access Roas at Ward 16
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mdiya | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.1.11 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Mevana Access Roas at Ward 21
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Mevana Access Roas at Ward 21
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mevana | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.1.12 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Dimfi Access Roas at Ward 23
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Dimfi Access Roas at Ward 23
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mevana | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.1.13 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Bukazi Access Roas at Ward 12
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Bukazi Access Roas at Ward 12
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Mevana | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.1.14 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of Singembeni Access Roas at Ward 32
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of Singembeni Access Roas at Ward 32
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 300000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of access road to Singembeni | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.2.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Landfill Site in Ward 7
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Landfill Site in Ward 7
PROJECT START DATE: | 2018-02-08
PROJECT COMPLETION DATE: | 2019-12-06
TOTAL APPROVED BUDGET: | 650000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of landfill site in Flagstaff Town | [6 empty] | 1st Quarter 2: · Operating landfill site
· To create short term joj opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Construction of cells | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of road signs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Practical completion walkover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 400000 | 100000 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 150000; 4th Quarter 2: 650000; 4th Quarter 3: Equitable Share
1.1.2.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre - engineering of Landfill Site in Ward 15
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre - engineering of Landfill Site in Ward 15
PROJECT START DATE: | 2020-01-10
PROJECT COMPLETION DATE: | 2020-01-29
TOTAL APPROVED BUDGET: | 2000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of landfill site in Lusikisiki Town | [6 empty] | 1st Quarter 2: · Operating landfill site
· To create short term joj opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Preparation and approval of specification | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Tender Stage | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 0 | 0 | 1st Quarter 1: 1000000; 1st Quarter 3: 0; 2nd Quarter 2: 1000000; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 2000000; 4th Quarter 3: Equitable Share
1.1.3.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of surfaced road at ward 6
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of surfaced road at ward 6
PROJECT START DATE: | 2018-04-06
PROJECT COMPLETION DATE: | 2019-12-06
TOTAL APPROVED BUDGET: | 6000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of surfaced road to Ward 6 community | [6 empty] | 1st Quarter 2: · Operational road
· To create job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Construction of kerbs | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Sub-base testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Tipping of selected material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Subgrade preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Practical completion walkover | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close - out | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 1000000 | 1000000 | 750000 | 1000000 | 1000000 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 500000; 4th Quarter 2: 5250000; 4th Quarter 3: MIG
1.1.3.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of surfaced road phase 2 at ward 15
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of surfaced road phase 2 at ward 15
PROJECT START DATE: | 2019-08-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 12000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of surfaced road to Ward 15 community | [6 empty] | 1st Quarter 2: · Operational road
· To create job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Base Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Testing of Base | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Hauling and Tipping of Sub-base material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Processing of Sub-base material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 3rd Quarter 2; 4th Quarter 2
· Construction of kerbs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Sub-base testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Tipping of selected material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Subgrade preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Construction of headwalls | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 2
· Installation road signs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
· General Cleaning | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
· Practical completion walkover | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1000000 | 1st Quarter 1: 1000000; 1st Quarter 3: 1000000; 2nd Quarter 2: 1000000; 3rd Quarter 1: 1000000; 3rd Quarter 3: 1000000; 4th Quarter 2: 11000000; 4th Quarter 3: MIG
1.1.3.3 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of surfaced road phase at ward 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of surfaced road phase at ward 19
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-09-29
TOTAL APPROVED BUDGET: | 9000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of surfaced road to Ward 19 community | [6 empty] | 1st Quarter 2: · Operational road
· To create job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site Establishment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Clearing and Grubbing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Base Preparation | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 3rd Quarter 2; 4th Quarter 2
· Testing of Base | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Installation of stormwater pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Hauling and Tipping of Sub-base material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
· Processing of Sub-base material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Construction of kerbs | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Sub-base testing | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Tipping of selected material | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 1000000 | 1000000 | 1000000 | 1000000 | 1st Quarter 1: 1000000; 1st Quarter 3: 1000000; 2nd Quarter 2: 1000000; 3rd Quarter 1: 1000000; 3rd Quarter 3: 1000000; 4th Quarter 2: 9000000; 4th Quarter 3: MIG
1.1.3.4 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of 2.5km R61 road , Ward 6
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of 2.5km R61 road , Ward 6
PROJECT START DATE: | 2019-07-15
PROJECT COMPLETION DATE: | 30/01/2021
TOTAL APPROVED BUDGET: | 10130000
SOURCE OF FUNDING: | Office of the Premier
Project Objectives | [5 empty] | Project Key Performance Indicators
· Tender Advert, Adjudication and Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Tender Advert | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Tender Breifing | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Tender Adjudication and Appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Site Handover | [5 empty] | A.Vuza | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Site Establishment and Clear and Grubbing | [5 empty] | A.Vuza | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Earthworks | [5 empty] | A.Vuza | bar: 1st Quarter 2; 2nd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
. Layer works | [5 empty] | A.Vuza | bar: 1st Quarter 2; 2nd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
. Stormwater Drainage | [5 empty] | A.Vuza | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 3; 4th Quarter 2
. Practical handover | [5 empty] | A.Vuza | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 350000 | 900000 | 1200000 | 1000000 | 1400000 | 1500000 | 1st Quarter 1: 1650000; 1st Quarter 3: 1830000; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 10130000; 4th Quarter 3: OTP
1.1.3.5 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Designs of flagstaff bypass , Ward 6&9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Designs of flagstaff bypass , Ward 6&9
PROJECT START DATE: | 2019-01-07
PROJECT COMPLETION DATE: | N/A
TOTAL APPROVED BUDGET: | 1500000
SOURCE OF FUNDING: | Office of the Premier
Project Objectives | [5 empty] | Project Key Performance Indicators
· Feasibility Study Report | [5 empty] | . Monthly reports
· Feasibility Study Report | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
. Advert for the Consultant | [5 empty] | B. Tshitshi | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Feasibilty Study Report | [5 empty] | A. Vuza | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Preliminary Design Report | [5 empty] | A. Vuza | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final Design Report | [5 empty] | A. Vuza | bar: 1st Quarter 2; 2nd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 150000 | 150000 | 150000 | 150000 | 200000 | 200000 | 1st Quarter 1: 200000; 1st Quarter 3: 200000; 4th Quarter 2: 1500000; 4th Quarter 3: OTP
1.1.4.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of taxi rank,ward 6
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of taxi rank,ward 6
PROJECT START DATE: | 15/07/2019
PROJECT COMPLETION DATE: | TBA
TOTAL APPROVED BUDGET: | 3000000
SOURCE OF FUNDING: | Office of the Premier
Project Objectives | [5 empty] | Project Key Performance Indicators
· Feasibility Study | [5 empty] | . Monthly reports
· Feasibility Study | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Feasibilty Study Report | [5 empty] | A. Vuza | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Preliminary Design Report | [5 empty] | A. Vuza | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final Design Report | [5 empty] | A. Vuza | bar: 1st Quarter 2; 2nd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 300000 | 300000 | 300000 | 400000 | 400000 | 400000 | 1st Quarter 1: 400000; 1st Quarter 3: 400000; 4th Quarter 2: 3000000; 4th Quarter 3: OTP
1.1.5.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT |  |  |  |  | 2nd Quarter 1: PROJECT MANAGER |  | Director Technical Services: L.S Tshangela
PROJECT NAME: |  | MAINTANANCE OF GRAVEL ROADS
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | EARTHWORKS:ROAD MAINTANANCE ROADS
PROJECT STARTING DATE: |  | 2019-10-01
PROJECT COMPLETION DATE: |  | 2019-06-26
TOTAL APPROVED BUDGET: |  | R15,725,000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [6 empty] | 1st Quarter 2: Project Key Performance Indicators
· To ensure maintance of access roads to all 32 wards | [6 empty] | 1st Quarter 2: · Maintained operational Road
· To create short term job opportunities | [6 empty] | 1st Quarter 2: · EPWP report
Time Frames
Key Milestones | [6 empty] | 1st Quarter 2: Responsible
[7 empty] | 1st Quarter 2: Official; 2nd Quarter 3: 1st Quarter; 4th Quarter 2: 2nd Quarter |  |  |  | 3rd Quarter |  |  | 4th Quarter
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Preparation and approval of specification | [7 empty] | B. Tshitshi
· Tender Stage | [7 empty] | B. Tshitshi
· Contractor Appointment | [7 empty] | B.Tshitshi
· Site Establishment | [7 empty] | B.Tshitshi
· Blading/Grading | [7 empty] | OP.Zide | bar: 3rd Quarter 1
· Hauling and Tipping | [7 empty] | OP.Zide | bar: 3rd Quarter 1
· Processing of gravel material | [7 empty] | OP.Zide | bar: 3rd Quarter 1 to 4th Quarter 1
· Cleaning of stormwater pipes | [7 empty] | OP.Zide | bar: 3rd Quarter 2 to 4th Quarter 2
· General Cleaning | [7 empty] | OP.Zide | bar: 3rd Quarter 2 to 4th Quarter 2
· Final Completion walkover | [7 empty] | B Tshitshi | bar: 4th Quarter 3
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  | 0 | 1572500 | 1572500 | 1572500 | 1834583.33 | 1834583.33 | 1834583.33 |  | 1834584.33 |  | 1834583.33 |  |  | 1834583.33 |  |  | R15,725,000.00
1.1.5.2
DEPARTMENT |  | TECHNICAL SERVICES DEPARTMENT | [7 empty] | PROJECT MANAGER | [9 empty] | Director Technical Services: L.S Tshangela
PROJECT NAME: |  | SURFACED ROAD MAINTENANCE
INSTITUTION: |  | INGQUZA HILL LOCAL MUNICIPALITY
PROJECT: |  | ROAD SURFACING
PROJECT STARTING DATE: |  | 2019-07-22
PROJECT COMPLETION DATE: |  | 2020-06-28
TOTAL APPROVED BUDGET: |  | R2,532,000.00
SOURCE OF FUNDING |  | EQUITABLE SHARE
Project Objectives | [7 empty] | Project Key Performance Indicators
· To ensure maintance of surfaced roads | [7 empty] | · Maintained operational Road
· To create short term job opportunities | [7 empty] | · EPWP report
Time Frames
Key Milestones | [7 empty] | Responsible
[8 empty] | Official |  |  |  | 1st Quarter |  |  |  |  | 2nd Quarter |  |  |  |  | 3rd Quarter 1: 3rd Quarter; 4th Quarter 1: 4th Quarter
[12 empty] | 1 |  | 2 | 3 |  | 1 | 2 |  |  | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Preparation and approval of specification | [7 empty] | B. Tshitshi
· Tender Stage | [7 empty] | B. Tshitshi
· Contractor Appointment | [7 empty] | B.Tshitshi
· Site Establishment | [7 empty] | B.Tshitshi
· Preparation of the road | [7 empty] | OP.Zide | bar: 3rd Quarter 1 to 4th Quarter 1
· Filling of base course | [7 empty] | OP.Zide | bar: 3rd Quarter 1 to 4th Quarter 1
· Pouring of asphalt | [7 empty] | OP.Zide | bar: 3rd Quarter 1 to 4th Quarter 1
· Road Markings and installation of road signs and general cleaning | [7 empty] | OP.Zide | bar: 4th Quarter 2 to 4th Quarter 3
· Asphalt tests | [7 empty] | B. Tshitshi | bar: 4th Quarter 1 to 4th Quarter 2
· Final Completion walkover | [7 empty] | B Tshitshi | bar: 4th Quarter 3
Projections Per Milestone
|  |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  |  | 4th Quarter | [7 empty] | Total
| 2 |  | 3 | 1 | 2 | 3 | 1 | 2 | 3 |  | 1 |  | 2 |  |  | 3
Project expenditure | R0 |  | 0 | R253,200.00 | R253,200.00 | R253,200 | R333,333.33 | R333,333.33 | R333,333.33 |  | R257,466.67 |  | 257466.67 |  |  | 257466.67 |  |  | R2,532,000.00
1.1.6.1
PROJECT NAME: | Construction of Ward 2 Multi-purpose Sports Field
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Ward 2 Munlti-purpose Sports Field
PROJECT START DATE: | 2018-12-01
PROJECT COMPLETION DATE: | 2019-12-02
TOTAL APPROVED BUDGET: | 2458402.28
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· To ensure provision of sports field in ward 2 | [5 empty] | . Operationg sports field
· To create job opportunities | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Import top soil for soccer field | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Import Sabhunga for other sports codes | [5 empty] | A.Hlehliso | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Installation of sub-soil drainage pipes | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Building of main ablution block guard house | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Building of changing rooms | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Fencing of main field and combi courts | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Construction of Combi courts | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Construction of Soccer Field | [5 empty] | A.Hlehliso | bar: 1st Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Practical Completion Walkover | [5 empty] | A.Hlehliso | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 871477.83 | 0 | 0 | 936924.45 | 0 | 1st Quarter 1: 0; 1st Quarter 3: 0; 3rd Quarter 3: 650000; 4th Quarter 2: 2458402.28; 4th Quarter 3: MIG
1.1.6.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Pre-engineering of ward 27 Multi - purpose Sports Field
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Pre-engineering of ward 27 Multi - purpose Sports Field
PROJECT START DATE: | 2019-10-01
PROJECT COMPLETION DATE: | 2020-03-27
TOTAL APPROVED BUDGET: | 392149.69
SOURCE OF FUNDING: | MIG
· To ensure provision of sports field in ward 27 | [6 empty] | 1st Quarter 2: · Detailed design report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Consultant appointment | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of preliminery designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Submission and approval of detailed designs | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 0 | 0 | 0 | 0 | 100000 | 0 | 1st Quarter 1: 200000; 1st Quarter 3: 0; 2nd Quarter 2: 0; 3rd Quarter 1: 0; 3rd Quarter 3: 0; 4th Quarter 2: 300000; 4th Quarter 3: MIG
1.1.7.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovation and Maintenace of New Rest Sports Field - Ward 19
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovation and Maintenace of New Rest Sports Field - Ward 19
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovation | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Changing Rooms 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Concrete Fencing and Gates 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Tyre rubble 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 250000 |  | 1st Quarter 3: 250000; 3rd Quarter 3: 0; 4th Quarter 2: 500000; 4th Quarter 3: Equitable Share
1.1.7.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovation and Maintenace of Joe Slovo Sports Field - Ward 15
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovation and Maintenace of Joe Slovo Sports Field - Ward 15
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification Meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Changing Rooms 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Concrete Fencing and Gates 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Grass cutting 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 250000 |  | 1st Quarter 3: 250000; 3rd Quarter 3: 0; 4th Quarter 2: 500000; 4th Quarter 3: Equitable Share
1.1.7.3 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovation and Maintenace of Sgubudwini Sports Field - Ward 09
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovation and Maintenace of Sgubudwini Sports Field - Ward 09
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 20/12/2019
TOTAL APPROVED BUDGET: | 500000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Changing Rooms 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Concrete Fencing and Gates 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Grass cutting 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 3rd Quarter 3; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 250000 |  | 1st Quarter 3: 250000; 3rd Quarter 3: 0; 4th Quarter 2: 500000; 4th Quarter 3: Equitable Share
1.1.8.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | PLANT SITE
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | CONSTRUCTION OF PLANT SITE Ward 17
PROJECT START DATE: | 15/10/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 722780.5
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Construction | [5 empty] | . Handover minutes
· Close-out | [5 empty] | . EPWP Report
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site handovever | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site establishment and Clear and grabbing | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for fencing poles | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Erection of fencing wire and gate | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Excavation for guard house and storerom | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
. Plastering painting and finishings | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
. Plumbing and general cleaning | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
. Practical handover | [5 empty] | P.Nqezo | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
. Final site handover | [5 empty] | B.Tshitshi | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 130000 |  | 1st Quarter 1: 100000; 1st Quarter 3: 150000; 2nd Quarter 2: 100000; 3rd Quarter 1: 100000; 3rd Quarter 3: 142780.5; 4th Quarter 2: 722780.5; 4th Quarter 3: Equitable share
1.1.9.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Ward 2 community hall in Multi Purpose Sports Field
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Ward 2 community hall in Multi- Purpose Sports Field
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 3500000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Designs | [5 empty] | . Approved Specification
· Construction | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 1050000 |  | 1st Quarter 3: 1050000; 3rd Quarter 3: 1400000; 4th Quarter 2: 3500000; 4th Quarter 3: Equitable Share
1.1.10.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Flagstaff Town Hall - Phase 2
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Flagstaff Town Hall - Phase 2
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 3000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Designs | [5 empty] | . Approved Specification
· Construction | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Electrification 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Plumbing 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Paving 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Fencing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 900000 |  | 1st Quarter 3: 900000; 3rd Quarter 3: 1200000; 4th Quarter 2: 3000000; 4th Quarter 3: Equitable Share
1.1.10.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Lusikisi Town Hall - Phase 2
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Lusikisiki Town Hall - Phase 2
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 3000000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Designs | [5 empty] | . Approved Specification
· Construction | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Electrification 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Plumbing 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Paving 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Fencing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 900000 |  | 1st Quarter 3: 900000; 3rd Quarter 3: 1200000; 4th Quarter 2: 3000000; 4th Quarter 3: Equitable Share
1.1.11.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Construction of Lusikisi New Municipal Offices
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Construction of Lusikisiki New Municipal Offices
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 14600000
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Designs | [5 empty] | . Approved Specification
· Construction | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Approved Designs | [5 empty] | L. Mgudu | bar: 1st Quarter 1 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Signed Specification | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Site Establishment 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 3; 4th Quarter 2
· Demolitions and Site Clearence 10% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 1 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 2000000 |  |  | 0 |  | 1st Quarter 3: 500000; 3rd Quarter 3: 1210000; 4th Quarter 2: 12100000; 4th Quarter 3: Equitable Share
1.1.12.1 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Ngobozana Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Ngobozana Community Hall - Ward 14
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.12.2 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Hombe Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Hombe Community Hall - Ward 20
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.12.3 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Makhosi Ndzoyiya Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Makhosi Ndzoyiya - Ward 13
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.12.4 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Bisi Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Bisi Community Hal - Ward 07
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.12.5 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Mduduzi Nkwakhwa Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Mduduzi Nkwakhwa Community Hall - Ward 24
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.12.6 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Renovations of Thobile Ndabankulu Community Hall
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Renovations of Mduduzi Nkwakhwa Community Hall - Ward 24
PROJECT START DATE: | 01/09/2019
PROJECT COMPLETION DATE: | 30/06/2020
TOTAL APPROVED BUDGET: | 477500
SOURCE OF FUNDING: | Equitable Share
Project Objectives | [5 empty] | Project Key Performance Indicators
· Designs | [5 empty] | . Approved Specification
· Renovations | [5 empty] | . Monthly Reports
· Close-out | [5 empty] | . Final Completion Certificate
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Specification meeting | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Site Establidhment 20% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Foundations 40% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 1 to 3rd Quarter 2; 4th Quarter 2
· Walls 60% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2 to 4th Quarter 2
· Roofing 80% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out 100% | [5 empty] | L. Mgudu | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2 to 4th Quarter 3
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 159166.67 |  | 1st Quarter 3: 159166.67; 3rd Quarter 3: 159166.66; 4th Quarter 2: 477500; 4th Quarter 3: Equitable Share
1.1.13.1
PROJECT NAME: | Electrification of 100 h/h at Sigubudwini ext Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING SIGUBUDWINI OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 109737.7
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | 109737.7 | [5 empty] | 4th Quarter 2: 109737.7; 4th Quarter 3: INEP
1.1.13.2
PROJECT NAME: | Electrification of 120 h/h at Ngqayimbana Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NGQAYIMBANA OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 109737.7
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  | 0 | 0 |  | 4th Quarter 2: 0; 4th Quarter 3: INEP
1.1.13.3
PROJECT NAME: | Electrification of 41 h/h at Ndukudeni Ward 9
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NDUKUDENI OF WARD 9
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 109737.7
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure | [6 empty] | 4th Quarter 2: 0; 4th Quarter 3: INEP
1.1.13.4 | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
PROJECT NAME: | Electrification of 56 h/h at Fama Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING FAMA OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 146880.21
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 48960.01 |  |  | 97920.2 | 4th Quarter 2: 146880.21; 4th Quarter 3: INEP
1.1.13.5
PROJECT NAME: | Electrification of 57 h/h at Ntongwana Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NTONGWANA OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 146550.21
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 48630.01 |  |  | 97920.2 | 4th Quarter 2: 146550.21; 4th Quarter 3: INEP
1.1.13.6
PROJECT NAME: | Electrification of 20 h/h at Vabetsho Ward 18
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING VABETSHO OF WARD 18
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 146550.21
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Energizing | [5 empty] | . Monthly reports
· Close-out | [5 empty] | . Handover certificates
. PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Completion of construction | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Energizing | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 48630.01 |  |  | 97920.2 | 4th Quarter 2: 146550.21; 4th Quarter 3: INEP
1.1.13.7
PROJECT NAME: | Electrification of 12 h/h at Luphandlasi Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING LUPHANDLASI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 264000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 66000 |  |  | 66000 | 2nd Quarter 2: 66000; 4th Quarter 2: #REF!; 4th Quarter 3: INEP
1.1.13.8
PROJECT NAME: | Electrification of 15 h/h at Jaca Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING JACA OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/09/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 0 |  |  | 82500 |  | 1st Quarter 1: 82500; 2nd Quarter 2: 82500; 4th Quarter 2: 247500; 4th Quarter 3: INEP
1.1.13.9
PROJECT NAME: | Electrification of 21 h/h at Mhlanjeni Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MHLANJENI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 462000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  | 115500 |  | 115500 | 2nd Quarter 2: 115500; 4th Quarter 2: 346500; 4th Quarter 3: INEP
1.1.13.10
PROJECT NAME: | Electrification of 3 h/h at Meyisi Ext Ward 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MEYISI OF WARD 30
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 66000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 16500 |  | 1st Quarter 1: 16500; 2nd Quarter 2: 16500; 4th Quarter 2: 49500; 4th Quarter 3: INEP
1.1.13.11
PROJECT NAME: | Electrification of 15 h/h at Bala Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING BALA OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 82500 |  | 1st Quarter 1: 82500; 3rd Quarter 3: 82500; 4th Quarter 2: 247500; 4th Quarter 3: INEP
1.1.13.12
PROJECT NAME: | Electrification of 3 h/h at Ntlakweskolo Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING NTLAKWESKOLO OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 66000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  | 16500 |  | 16500 | 2nd Quarter 2: 16500; 4th Quarter 2: 49500; 4th Quarter 3: INEP
1.1.13.13
PROJECT NAME: | Electrification of 7 h/h at Gqina Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING GQINA OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 154000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 38500 |  |  | 38500 | 2nd Quarter 2: 38500; 4th Quarter 2: 115500; 4th Quarter 3: INEP
1.1.13.14
PROJECT NAME: | Electrification of 24 h/h at KuMathe Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING KUMATHE OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 528000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 132000 |  |  | 132000 | 2nd Quarter 2: 132000; 4th Quarter 2: 396000; 4th Quarter 3: INEP
1.1.13.15
PROJECT NAME: | Electrification of 18 h/h at OK Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING OK EXT OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 396000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 99000 |  |  | 99000 | 2nd Quarter 2: 99000; 4th Quarter 2: 297000; 4th Quarter 3: INEP
1.1.13.16
PROJECT NAME: | Electrification of 5 h/h at Sihlehleni Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING SIHLAHLENI OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 110000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 27500 |  |  | 27500 | 2nd Quarter 2: 27500; 4th Quarter 2: 82500; 4th Quarter 3: INEP
1.1.13.17
PROJECT NAME: | Electrification of 14 h/h at Cumngce Ext Ward 31
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING CUMNGCE OF WARD 31
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 308000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 77000 | 77000 | 2nd Quarter 2: 77000; 4th Quarter 2: 231000; 4th Quarter 3: INEP
1.1.13.18
PROJECT NAME: | Electrification of 100 h/h at Luthulini Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING LUTHULINI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 550000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 137500 |  |  | 137500 | 2nd Quarter 2: 137500; 4th Quarter 2: 412500; 4th Quarter 3: INEP
1.1.13.19
PROJECT NAME: | Electrification of 100 h/h at Mkhumbi Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MKHUMBI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 220000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 55000 |  |  | 55000 | 2nd Quarter 2: 55000; 4th Quarter 2: 165000; 4th Quarter 3: INEP
1.1.13.20
PROJECT NAME: | Electrification of 100 h/h at Gcinilifu Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING GCINILIFU OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 220000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 55000 |  |  | 55000 | 2nd Quarter 2: 55000; 4th Quarter 2: 165000; 4th Quarter 3: INEP
1.1.13.21
PROJECT NAME: | Electrification of 15 h/h at Mtshekelweni Ext Ward 8
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | ELECTRIFIYING MTSHEKELWENI OF WARD 8
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 15/12/2018
TOTAL APPROVED BUDGET: | 330000
SOURCE OF FUNDING: | INEP
Project Objectives | [5 empty] | Project Key Performance Indicators
· Construction | [5 empty] | . Monthly reports
· Energizing | [5 empty] | . Handover certificates
· Close-out | [5 empty] | . PCS(Project Customer Spreadsheet) file
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Site establishment | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Digging and planting | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 1st Quarter 3; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Dressing, stringing and tensioning | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Transformer mounting and earting | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Labeling | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 1 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· CNC inspection | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Outages | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Handover incl PCS (Project Customer Spreadsheet) file | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
· Close-out | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2 to 2nd Quarter 3; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 82500 |  |  | 82500 | 2nd Quarter 2: 82500; 4th Quarter 2: 247500; 4th Quarter 3: INEP
1.1.14.1
PROJECT NAME: | Construction of high school high mastlights at ward 1,10,11,16,20,23,24,25,26,27,28 and 30
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Erection of high masts at ward 1,10,11,16,20,23,24,25,26,27,28 and 30
PROJECT START DATE: | 30/07/2019
PROJECT COMPLETION DATE: | 15/12/2019
TOTAL APPROVED BUDGET: | 7200000
SOURCE OF FUNDING: | MIG
Project Objectives | [5 empty] | Project Key Performance Indicators
· Erection of high mast | [5 empty] | . Monthly reports
· Connection to point of supply | [5 empty] | . Completion certificate
· Commissioning | [5 empty] | .
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Custing of foundation and ordering of steel | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Erection of high mast | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Connection to point of supply | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Handover | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  | 360000 |  |  |  | 1st Quarter 1: 3240000; 3rd Quarter 3: 3600000; 4th Quarter 2: 7200000; 4th Quarter 3: MIG
1.1.17.1
PROJECT NAME: | Maintenance of Buildings electricity
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Maintenance of Buildings electricity
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 600000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators
· Repaired building wiring | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Ordering of material | [5 empty] | M. Gqada | bar: 1st Quarter 1 to 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
· Repairs | [5 empty] | M. Gqada | bar: 1st Quarter 2 to 4th Quarter 2
· | [5 empty] | M. Gqada | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  | 15000 |  |  | 15000 |  | 1st Quarter 3: 15000; 3rd Quarter 3: 5000; 4th Quarter 2: 50000; 4th Quarter 3: ES
1.1.17.2
PROJECT NAME: | Maintenance of standby generator
INSTITUION: | Ingquza Hill Local Municipality
LINE ITEM: | Maintenance of standby generator Ward 6, 19
PROJECT START DATE: | 01/07/2018
PROJECT COMPLETION DATE: | 30/06/2019
TOTAL APPROVED BUDGET: | 50000
SOURCE OF FUNDING: | ES
Project Objectives | [5 empty] | Project Key Performance Indicators
· Repaired building wiring | [5 empty] | . Monthly reports
. Signed Acceptance test plan
.
Key Milestones | [5 empty] | Responsible Official | 1st Quarter 1: Time Frames
[7 empty] | 1st Quarter |  |  | 2nd Quarter |  |  | 3rd Quarter |  |  | 4th Quarter
[7 empty] | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3 | 1 | 2 | 3
· Repairs | [5 empty] | M. Gqada
· | bar: 1st Quarter 2; 2nd Quarter 2; 3rd Quarter 2; 4th Quarter 2
Projections per milestone
|  |  | 2nd Quarter |  |  | 3rd Quarter | 2nd Quarter 2: 4th Quarter; 4th Quarter 2: Total; 4th Quarter 3: Source of Finance
| 2 | 3 | 1 | 2 | 3 | 1 | 1st Quarter 1: 2; 1st Quarter 3: 3; 2nd Quarter 2: 1; 3rd Quarter 1: 2; 3rd Quarter 3: 3
Project Expenditure |  |  |  |  | 15000 |  | 1st Quarter 1: 10000; 3rd Quarter 1: 10000; 4th Quarter 2: 35000; 4th Quarter 3: ES